## Start Here
OmniStackAI: finish the platform
Vision | A futuristic platform that turns a prompt into anything from one app to a whole ecosystem. Every app gets modern, latest UI and the maximum features the prompt implies, and can be customised afterwards.
Vibe Mode | Vibe Mode: prompt -> running app -> live URL, with all the machinery hidden. The API and database behind every feature are real, not only a pretty UI.
Engineering Mode | Engineering Mode: see the plan, choose the stack, import a repo, review diffs, see the verification report, open GitHub pull requests.
Stack policy | Web and admin panel: Next.js by default.
App requested without naming a stack (either mode): a React Native (Expo) app ready to publish on Google Play and the App Store, plus an installable PWA with a QR code.
App requested as native: Kotlin + Jetpack Compose (Android) and/or Swift + SwiftUI (iOS) is generated, best in class, through to store publishing. Until R-575/R-576 ship, the React Native app is built instead and the user is told why (the R-559 rule).
Accounts and keys (cloud, database, payments, email, Apple, Google, sandboxes) come last: all code and integrations are finished first, so go-live is only credentials.
Flutter and React.js: not offered. A request for either is answered with the nearest supported stack and the reason.
Backend: Python by default; Go and Node on request.
Database: PostgreSQL by default; MongoDB as an option.
LLM: NVIDIA nemotron-3-ultra through the NVIDIA API (key in .env only), with the existing providers and local Ollama as alternatives.
Focus rule | Work only from this folder's Work Queue, top to bottom. Other R_&_D plans and the v6 tracker are sources, not queues: every open item from them is already in 'All Tasks' with a pointer to the queue item that covers it. Do not start anything that is not in the queue until the queue is finished.
Strengthen | Where it is done
Local / offline models | PC-014
UI polish and 'wow in 30 seconds' | PC-006
Instant preview, one-click hosting, integrations | PC-007, PC-008, PC-013
Import an existing repo | R-578, R-579
Store-ready mobile apps | R-574 (React Native), R-575, R-576 (native)
A live product with real users | PC-009, PC-015
How to update | Edit tools/tasks_data.py (or write the task's CHANGELOG entry to mark it Completed) and run: python3 "R_&_D/Platform_Completion/tools/build_master_tasks.py"

## Work Queue
# | ID | Task | Phase | Mode | Status | Priority | Depends on | Covers | Notes
1 | PC-001 | Master task list: reconcile every R_&_D source into one queue | 0 Foundation | Platform | Completed | P0 |  |  | This document. Done when the founder approves it.
2 | PC-002 | Founder decisions that block later phases (see Decisions sheet) | 0 Foundation | Platform | Completed | P0 | PC-001 |  | Pricing/free tier, hosting cloud + region, payment processor, email verification, in-browser preview engine licence, app-store accounts. D-5, D-8, D-9 answered 2026-09-26.
3 | PC-062 | Native mobile preview: R&D and plan (open source first) | 0 Foundation | Both | Completed | P0 |  |  | NATIVE_MOBILE_PREVIEW_PLAN.md in this folder.
4 | PC-047 | NVIDIA model provider (nemotron-3-ultra) for builds, configured from .env | 0 Foundation | Platform | Completed | P0 |  |  | Founder's chosen LLM (D-9). OpenAI-compatible, so one provider entry plus the NVIDIA_MODEL_BASE_URL override, prices and tests. The key stays in .env only. Includes a first comparison against the providers we already support on the same build prompts.
5 | PC-093 | Intake repairs instead of rejecting: a model's status-change endpoint becomes a workflow transition, and an undeclared request-schema reference is fixed, not fatal | 0 Foundation | Both | Completed | P0 |  |  | Found by PC-047's comparison (2026-09-26): 3 of 6 real intake runs, on both NVIDIA and Gemini, were rejected for the same reason. Roughly half of real prompts fail at the first step whichever model runs, so this comes before everything else.
6 | PC-003 | Stack policy in code: an app request gets a store-ready React Native app AND an installable PWA with QR; Flutter and React.js refused with the reason | 0 Foundation | Both | Completed | P0 |  |  | R-562 already builds the React Native app; the PWA + QR half is R-573. Native Kotlin/Swift only after Phase 5. Uses the R-559 'nearest thing we can build, with a reason' path.
7 | R-591 | Complete auth for the Go backend: register, login, logout, me, forgot password, reset password | 1 Vibe Mode live | Both | Completed | P0 |  |  | A Go app with auth has no way for a real user to sign in. Parity with the Python backend's auth (R-461, R-463), companions included.
8 | R-590 | Workflow transitions as buttons on the generated screens | 1 Vibe Mode live | Both | Completed | P0 | R-588 |  | The user-visible half of R-566.
9 | R-573 | PWA really by default: manifest, service worker, icons, install prompt, QR | 1 Vibe Mode live | Vibe | Completed | P0 | PC-003 | ARCH-PWA | Works for templates only today; generated projects must install on a real phone.
10 | PC-004 | Real API + DB for every feature: a Vibe build fails if any screen or action is not wired to a real endpoint and table | 1 Vibe Mode live | Vibe | Completed | P0 | R-590 | ARCH-PIPELINE, SPEC-VIBE-01 | No mock data, no 501 stubs, no dead buttons. From specs/vibe-mode-pro. Found in R-590: the Node repositories silently fall back to an in-memory map on any database error and report success; a malformed id answers 500 instead of 404 on the Python backend.
11 | PC-005 | Vibe / Engineering mode switch in the Studio | 1 Vibe Mode live | Both | Completed | P0 |  | ARCH-STUDIO-MODES, BP-INTENT, SPEC-STUDIO-01 | From specs/studio-ux/01. Vibe hides the machinery; Engineering shows plan, stack, diffs, report, PRs.
12 | PC-006 | 'Wow in 30 seconds': first screen streams fast, latest modern UI, maximum polish per page | 1 Vibe Mode live | Vibe | Completed | P0 |  | BP-SWITCHER, SPEC-TS-01 | R-558 fixed the design system; still needs speed-to-first-screen and visual quality. From specs/table-stakes/01 and the buildout 'intent card' idea. Measured in PC-084: plan 20-29 s (model) and preview start ~14 s are the stages to cut; model-written pages cost ~80 s and their admin page failed to compile, so the repair loop must cover the admin app before model-written pages return to the default path. Speed half done 2026-09-26: preview start 17.7 -> 9.6 s (shared warm API environment, surfaces probed together), live prompt -> running app 12-15 s on Groq; fixed model navigation objects breaking pages. First screen done: tracker home, readable names, cards that say what you can do, header fits a phone. Follow-ups: preview during verification (~5 s), detail screens out of the top bar, auth User entity off home cards. The 'latest modern UI' half was not delivered: pages stayed template-only; carried by PC-097 to PC-101.
13 | PC-084 | Speed targets measured on every build and enforced: prompt -> preview under 90 s, prompt -> live URL under 3 min, as a dashboard and a regression gate | 1 Vibe Mode live | Vibe | Completed | P1 | PC-006 |  | The Targets sheet had numbers but no task measured them. Founder-approved 2026-09-26.
14 | PC-085 | Model quality evals and best-model routing: score every provider (NVIDIA, cloud, local) per task type and route each job to the best one | 1 Vibe Mode live | Both | Completed | P1 | PC-047 |  | NVIDIA nemotron is unproven for code; this keeps quality independent of one vendor. Founder-approved 2026-09-26. Done 2026-09-27: plan and code evals, scorecard routing; follow-ups: more code cases, score Gemini once its daily quota resets, route the build's repair step as a code job.
15 | PC-095 | Build fallback chain: Groq -> Gemini -> OpenRouter (free) -> NVIDIA -> local Ollama | 1 Vibe Mode live | Platform | Completed | P1 | PC-085 |  | Founder, 2026-09-26. A rate-limited or failing provider hands the build to the next one.
16 | PC-094 | Intake repairs, round 2: duplicate roles, a lifecycle for a missing entity, and a clean error (not a crash) for malformed plan parts | 1 Vibe Mode live | Both | Completed | P1 | PC-093 |  | Found testing weaker models on 2026-09-26: qwen3.8-27b crashed intake with an AttributeError; nemotron named a lifecycle for an entity it did not declare; qwen2.5-coder:7b declared the role 'user' twice. Each is repairable the way PC-093 repairs endpoints.
17 | PC-007 | Instant in-browser preview (no local toolchain needed) | 1 Vibe Mode live | Vibe | Completed | P0 |  | ARCH-WEBCONTAINER, BP-TURBO, R-174, SPEC-TS-02 | From specs/table-stakes/02 and tracker R-174. Built behind a preview-engine interface with an open-source engine first; a paid engine licence (D-6) is only a key at the end. Done 2026-09-27: engine switch + container engine (Docker only, gVisor where registered); the WebContainer engine is PC-096.
18 | PC-096 | In-browser WebContainer preview engine behind the PC-007 engine switch (Node in the visitor's browser; licence key supplied at PC-070) | 1 Vibe Mode live | Vibe | Pending | P2 | PC-007 |  | Blocked on the founder (2026-09-30): needs StackBlitz's commercial licence (decision D-6), a paid service - skipped by the queue until decided. Split out of PC-007 on 2026-09-27: PC-007 delivers the engine switch and the open-source container engine; WebContainer needs StackBlitz's commercial licence (D-6) and runs Node only, so Python/Go APIs still need a server-side engine behind it.
19 | PC-008 | One-click publish to a live URL: web, admin, API and database together, code complete and proven against local stand-ins | 1 Vibe Mode live | Vibe | Completed | P0 | PC-049 | BP-SHIPCHECK, R-048, R-509, R-510, SPEC-TS-03 | R-509/R-510 publish the web app only and were never run for real. From specs/table-stakes/03. Real accounts are plugged in at PC-070. Done 2026-09-27 against the local stand-in; a real server + domain is proven at PC-071.
20 | PC-009 | Hosted multi-tenant service: per-user isolation of builds, sessions and previews; quotas; egress policy | 1 Vibe Mode live | Platform | Completed | P0 |  | MULTI-TENANT, PG-05, R-071, R-100, R-175, R-214 | Today the Studio is one trusted operator's tool. Built cloud-neutral and proven locally (Colima); the cloud account (D-2) is plugged in at PC-070. Done 2026-09-27; left: per-user disk quotas, cloud account.
21 | PC-010 | Credit fairness: estimate before a build, no charge for internal retries, per-task budgets, cost guardrails | 1 Vibe Mode live | Platform | Completed | P0 |  | PG-13, R-025, R-046, R-047, R-104 | Done 2026-09-27; model prices beyond Groq are PC-011.
22 | PC-011 | Plans, entitlements, credit top-up and super_admin console (Phase E) | 1 Vibe Mode live | Platform | Completed | P0 |  | PG-16, PHASE-E, R-109 | Stripe and Razorpay adapters complete and tested in their test modes; live keys (D-3) at PC-070. Found in R-590: self-registered users get role 'user', which is not one of the plan's roles, so role-guarded actions need an admin to assign roles — include a role manager in the generated admin console. Done 2026-09-27; prices and live keys at PC-070.
23 | PC-012 | Legal and account basics: ToS, privacy, retention, deletion/export, email verification | 1 Vibe Mode live | Platform | Completed | P0 |  | GAP-LEGAL, PG-14, R-108, R-516 | Done 2026-09-27; emails go through Resend once keyed (PC-070), legal texts are drafts for counsel. Not built: cancelling a paid plan from Settings (deleting the account cancels it) — with billing go-live at PC-070.
24 | PC-013 | Verified integrations catalog with health tests | 1 Vibe Mode live | Vibe | Completed | P1 |  | R-055, R-056, R-511 | R-511 Connectors v1 exists. Done 2026-09-27 (also proves R-511 live); real-account checks of Resend/Stripe/Razorpay pass at PC-070.
25 | PC-097 | Compile repair covers every Next surface (admin console and ecosystem role surfaces), not only the main web app | 1 Vibe Mode live | Both | Completed | P1 | PC-008 |  | Found publishing a clinic app on 2026-09-27: the `provider` role surface shipped a model-written page with an invented import and misused components; the build never checked it. PC-008 now type-checks every Next surface and publish refuses a broken app with the compiler's reason; this task makes the repair loop fix or revert those pages as it does for web. First of the modern-UI block (added 2026-09-27, founder-approved): PC-098 turns model-written pages back on only once this holds, so no surface can ship a page that does not compile. Done 2026-09-28.
26 | PC-098 | Model-written pages back on for every Vibe build: fast template first, modern pages upgraded in the background, safe under chat edits | 1 Vibe Mode live | Both | Completed | P0 | PC-097 |  | PC-084 switched them off (80 s per build; its admin page did not compile), so every console build is template pages only: 1 model-written page across 33 projects on 2026-09-27. Must: (1) show the template preview as today, then replace pages one by one with model-written ones, each type-checked and repaired (PC-097) or kept as the template - never a broken page; (2) include the page-writing cost in the estimate before the build (PC-010); (3) chat edits update a model-written page instead of regenerating it from the template, so an edit never throws the modern page away; (4) pages still use only the app's real data hooks (PC-004); (5) say plainly which pages were upgraded and which kept the template; (6) task verify stays offline (templates only, 0 model calls); (7) a weak local model (PC-014) falls back cleanly. Measured in PC-097 (2026-09-28): on Groq's free tier the page-writing request is too large (413) for a real project even with compact grounding, and answers arrive truncated, so pages must be written from a much smaller prompt or on a larger-context model (Gemini wrote and repaired an admin page); most first drafts had 1-4 type errors, so the page prompt must shrink them. Done 2026-09-28 on free keys: a chain (Gemini 3.8 Flash, Gemini 3.5 Flash-Lite, OpenRouter free, NVIDIA, local Qwen2.5-Coder 14B) designed 8 of 8 pages of a food-delivery app in 7.5 min. A billed key later only goes first in the chain (PC-070).
27 | PC-099 | A design direction per project: colours, type, radius, density and layout style chosen from the prompt and the product's archetype | 1 Vibe Mode live | Both | Completed | P0 | PC-098 |  | Every project on 2026-09-27 shared one byte-identical tokens.css, so all apps look alike. Pick a coherent direction (palette with checked contrast, type pairing, shape, spacing, light/dark) from the prompt ('modern', 'playful', 'luxury', named brand colours) and the archetype; write it to brand.json and the tokens, and give it to the page writer. A deterministic default without a model; the same prompt gives the same direction. Shown and editable in the Plan view (PC-022) and later the brand kit (PC-020). Found in PC-098: a designed home page brings its own header and the app shell's navbar still renders above it - the direction covers the layout (one header), not only the page. Done 2026-09-29: ten styles, domain palettes, font pairs loaded from Google Fonts, saved in the plan; components and pages themed; ecosystems designed too. Not built: the Plan view and brand kit that edit it.
28 | PC-050 | Design System Pro: widen the LLM UI allowlist (motion, charts, rich text, command menu, drawer, toasts, tables, forms, maps, uploads) | 1 Vibe Mode live | Vibe | Completed | P0 |  | ARCH-ALLOWLIST | framer-motion, recharts, tiptap, cmdk, vaul, sonner, tanstack-table, react-hook-form + zod, date-fns, maplibre, uppy: pinned, validated, repaired like today's allowlist. From the architecture plan. Done 2026-09-29: framer-motion, recharts, @tanstack/react-table, react-hook-form + zod, date-fns, sonner, cmdk, vaul pinned for React 18 in every generated web and admin app, allowed and explained to the page writer; the type-check cache rebuilds when they change. Deferred: tiptap (rich text), maplibre (maps) and uppy (uploads) - heavy, and each needs a backend or tiles; add with the feature that uses them.
29 | PC-100 | A modern admin panel: redesign the generated admin console (dashboard with real metrics and charts, rich data tables, forms, filters, bulk actions, command menu) in the project's design direction | 1 Vibe Mode live | Both | Completed | P0 | PC-099, PC-050 |  | The admin console is one template for every project (21 of 27 admin layouts byte-identical on 2026-09-27). Keep every existing admin capability (roles manager, CRUD on every entity, auth) and its API wiring; model-written admin pages go through the same repair and fallback as the web app (PC-097, PC-098). Found in PC-098: the admin template shows invented figures ('99.98% system health', '< 24ms latency') - every number must come from the API or not be shown. Done 2026-09-29: an app shell (sidebar, top bar, Ctrl/Cmd+K command menu, phone drawer), a dashboard read only from the API, and a page per listable entity (server-sorted, searched and paginated table, bulk delete, CSV, create/edit drawer validated from the plan, related records picked by name, a map for coordinates); model pages with invented figures are refused. Found and fixed in the generated Python API: GET /orders answered 500 in every app with an Order entity, no foreign key could be written, and a declared created_at was required on create.
30 | PC-101 | UI quality gate for ordinary prompts: every Vibe build is screenshotted and checked (layout, contrast, spacing, phone width, empty/loading/error states) before it is called done | 1 Vibe Mode live | Both | Completed | P1 | PC-098, PC-099, PC-100 |  | PC-088's UI review covers packs only. Headless screenshots at phone and desktop widths of every surface; deterministic checks (contrast, overflow, broken images, console errors) always, a model review when a provider is set; a failing page is repaired or reported, never hidden. A fixed set of benchmark prompts (food delivery, clinic, store, SaaS, blog) is re-run so the UI is shown to improve and never regress. Seen in PC-099 for this gate to catch: in a preview served under a base path, a page's server-side API proxy route (/products) answered 503 'backend_unavailable' while the API itself answered 200; and the generated Expo app fails tsc on `process` (no Node types) in src/shared/api/client.ts. Seen in PC-050: a designed home page still showed invented trend figures ('+12.5% from last month') despite the rule against them (PC-100 now refuses those), and the preview console had a few static-resource 404s - PC-100 traced the ones it saw to screenshots taken on an app's raw port (a relative API path only resolves through the console) and one transient dev-server 404; check against a production build. Seen in PC-100: the proxy route reads BACKEND_INTERNAL_URL or NEXT_PUBLIC_API_URL, not the API_URL the preview sets, which is the 503 above; dev-mode HMR websockets fail through the console proxy; an app whose API has no sign-in routes still shows 'Sign in'. Seen in PC-102: the planner can declare a required <entity>_id for an entity it gives no API (a job posting's recruiter_id with no /recruiters), so no form can fill it, and an entity whose only create is nested (/job_postings/{id}/applications) gets no 'New' in the admin console. Done 2026-09-30: scripts/ui-check.mjs (every page, 390 and 1360 px: overflow, console, requests, images, contrast); every listed defect fixed, plus what the check found (previews without a base path, SSR crash with uploads, contrast, page warm-up). Benchmarks food/clinic/store/blog 0 failing pages. Runs on demand, not after every build; free-provider planning failures remain.
31 | PC-102 | Rich text and file uploads in generated apps: a rich-text field type edited with tiptap and rendered safely, and attachment fields uploaded to storage (uppy) | 1 Vibe Mode live | Both | Completed | P1 | PC-100 |  | Deferred from PC-050 and PC-100 because each needs more than a library. Rich text: a field type the planner can choose, stored as sanitized HTML (or Markdown), edited with tiptap in the admin console and rendered safely in the web and mobile apps. Uploads: attachment fields are a URL today and no backend (Python, Go, Node) has an upload endpoint or storage; needs a founder decision on storage (local disk on the API vs S3-compatible - MinIO locally, R2/S3 in production), then an upload endpoint with size/type limits in each backend and uppy in the console. Founder's decision 2026-09-29: Cloudflare R2 (dev and prod), AWS S3 as the production alternative, the local disk as the fallback; no MinIO. Done 2026-09-29 for the default Python backend and the web and admin apps: per-field rules from the requirement (planner or the field's name), content checked on the server, R2/S3/local chosen from the platform's .env (production needs keys only), Uppy with device, camera, web link and Google Drive / Dropbox / OneDrive / Box through a self-hosted Companion; proven in the preview and in a published production stack. Rich text moved to PC-104; Go and Node uploads to PC-105.
32 | PC-104 | Rich text in generated apps: a rich_text field type the planner can choose, edited with tiptap and rendered safely | 1 Vibe Mode live | Both | Completed | P1 | PC-102 |  | Split from PC-102. A field type the planner picks for long formatted content (descriptions, articles, notes); stored as HTML sanitized on the server (Python, Go and Node), edited with tiptap in the admin console and web forms, rendered with a second sanitizing pass in the web app and as plain text on mobile. Done 2026-09-29: rich_text type; nh3 / bluemonday / sanitize-html on every write; tiptap editor in web forms and the admin console; DOMPurify on display; plain words in tables and on mobile; the planner and the publication template use it, and a prompt that asks for formatting upgrades content fields deterministically.
33 | PC-107 | A preview is ready only once its pages are compiled; benchmark projects removed | 1 Vibe Mode live | Both | Completed | P2 | PC-106 |  | Left by PC-106: a page opened in the first minute of a preview, while the warm-up compiled routes, could meet a dev-server chunk error. And the PC-101 benchmark projects under bench-* test accounts are no longer needed. Done 2026-09-30: previews report ready after the warm-up; the real cause was the console proxy looking the preview up once per file (cached; control-plane connections kept); 21 benchmark projects deleted through the platform.
34 | PC-106 | Planning survives a provider failing mid-answer, and the UI check runs after every preview | 1 Vibe Mode live | Both | Completed | P1 | PC-101 |  | Left open by PC-101: builds failed when a free provider timed out or was rate-limited after its answer had started (the chain never switches mid-stream); the UI check ran only by hand; one task-tracker page failed with a Next chunk 404 that was not diagnosed. Done 2026-09-30: the planner starts again with the rest of the chain (and 413 fails over); the check runs after every preview and shows in the Studio; the 404 was the check racing the page warm-up.
35 | PC-105 | File uploads in the Go and Node backends | 1 Vibe Mode live | Both | Completed | P1 | PC-102 |  | Split from PC-102, which builds uploads for the default Python backend: the same /uploads and /files endpoints, the same per-field rules and content checks, and the same storage drivers (R2/S3/local) in Go and in Node (Express and Hono). Done 2026-09-29: both generate the Python contract (same checks, messages, settings, signed links); the generated Go, Express and Hono APIs each passed the 19 upload checks on disk and on S3, a Companion link import and the sign-in requirement.
36 | PC-103 | Go and Node backends: relations writable and audit timestamps optional, as the Python backend now is | 1 Vibe Mode live | Both | Completed | P1 | PC-100 |  | Found in PC-100 for the Python API (the default backend): no foreign key could be written (the model lacked it and inserts skipped it) and a declared created_at was required on create. The Go models have the same gap (type Order has no CustomerId); check the Node backend too, and run the admin console's create/edit against each. Done 2026-09-29: Go and Node read and write foreign keys and leave declared timestamps to the database; both generated servers created, read, updated and listed an order with its customer against Postgres. Found: the Node API failed tsc wherever it had accounts (fixed).
37 | PC-108 | Consumer-grade UI for generated apps: detail, landing, list and empty states that read as a finished product, not an operator's tool | 1 Vibe Mode live | Both | Completed | P1 | PC-101 |  | Seen in the PC-101 benchmark screenshots: a record's detail page offers an ID box, 'Copy ID', 'Export JSON' and prev/next buttons to visitors; the landing hero shows an empty image placeholder; public lists are admin-style tables with density toggles and CSV export; empty states are bare. The templates every build uses (model page design is optional) must look finished: cards and readable detail pages for visitors, the operator tools kept in the admin console. Proven with the UI check and screenshots on the benchmark prompts. Done 2026-09-30: card lists and reading views in the web app, operator pages kept in the admin app, no empty hero box; proven on the hiring portal and content hub with real records.
38 | PC-014 | Local/offline models as a first-class path: build fully on Ollama, recommend a model per machine | 1 Vibe Mode live | Both | Pending | P1 |  | GA-03, GA-04, GA-05, GAP-EVALS, PG-18, PG-19, R-080, R-194 | Ollama adapter exists (R-003/R-006). Found in PC-084: .env names qwen2.5-coder:14b but only 7b is installed, and the adapter refuses a pinned model it was not configured with — detect installed models instead of trusting the setting. PC-098 (2026-09-28): the founder replaced 7b with qwen2.5-coder:14b; the Ollama adapter now sends num_ctx (long prompts were cut silently) and page design sizes it to 16k context / 6k answer.
39 | R-574 | Store publishing for React Native apps: EAS build and submit to Play Store and App Store, proven with real accounts | 1 Vibe Mode live | Both | Pending | P1 | PC-003 | R-062, R-063, R-546 | R-546/R-547 generate the EAS config. Everything up to the upload is built and tested; the Apple and Google accounts (D-7) are plugged in at PC-070.
40 | PC-049 | Managed database for published apps: provision PostgreSQL (Neon, Supabase or self-hosted) and run migrations and seeds on publish | 1 Vibe Mode live | Vibe | Not Started | P0 |  | ARCH-SUPABASE | A live URL needs a live database. Provider interface with a local Docker implementation; MongoDB Atlas once PC-048 exists. From the architecture plan. PC-008 (2026-09-27) delivered the per-app PostgreSQL in Docker with a migration ledger; left: hosted providers (Neon/Supabase), backups, and follow-on migrations for schema changes after first publish (today a changed 0001_init.sql is not re-applied to a live database).
41 | PC-063 | Android emulator preview without Android Studio: SDK command-line bootstrap, headless emulator, auto-install, streamed into the Studio | 1 Vibe Mode live | Both | Not Started | P1 |  | R-052 | See NATIVE_MOBILE_PREVIEW_PLAN.md. Open source first; local on the founder's Mac, then hosted in PC-065.
42 | R-582 | Smarter IR synthesis: multi-pass planning and self-critique before generation | 2 Maximum features | Both | Not Started | P1 |  |  | Where 'more features per prompt' is won.
43 | R-580 | Domain knowledge in ecosystem detection ('logistics' implies drivers) | 2 Maximum features | Both | Not Started | P1
44 | R-570 | Permissions beyond role: ownership and row-level rules | 2 Maximum features | Both | Not Started | P1 |  | ARCH-DOMAIN-IR | 'A driver sees only their own orders'. Seen live 2026-09-27 (PC-008): a published notes app saved notes with created_by null, so private notes were not private.
45 | R-567 | Money: ledgers, payments, payouts, refunds, commission | 2 Maximum features | Both | Not Started | P1 |  | ARCH-PAYMENTS, R-512 | R-512 gives Stripe/Razorpay checkout; this is the ledger.
46 | R-568 | Background jobs and scheduling | 2 Maximum features | Both | Not Started | P1
47 | R-569 | Realtime channels: tracking, notifications, live status | 2 Maximum features | Both | Not Started | P1 |  | ARCH-REALTIME
48 | R-571 | Escape hatch: behaviour the IR declares and the model implements, verified | 2 Maximum features | Both | Not Started | P1 | R-560 |  | No hard ceiling, only a typed boundary.
49 | PC-016 | Edit a workflow by chat (add/rename states and transitions safely) | 2 Maximum features | Both | Not Started | P1 | R-584, R-590
50 | R-572 | Shared contract package: one generated packages/ for types, client, validation | 2 Maximum features | Both | Not Started | P1 |  | R-116, R-127, R-137, R-143, R-152, SPEC-PACK-06D | Also puts the /auth routes (R-591) into the generated OpenAPI contract.
51 | R-585 | Template customisation as a first-class flow | 2 Maximum features | Both | Not Started | P1 | R-584
52 | PC-017 | Pack framework core: manifest v2 schema, registry/loader, composer (merge, wire, validate, conflict rules) | 2 Maximum features | Both | Pending | P1 | R-572 | ARCH-GENERATORS, SPEC-PACK-01, SPEC-PACK-02 | Solution Pack manifests, registry and application exist (R-434..R-445); v2 adds ir_delta, state machines, page templates, dependencies. From specs/pack-framework 01, 02.
53 | PC-075 | Role-based app generator: a complete app per role (nav, pages, API scope, permissions) | 2 Maximum features | Both | Pending | P1 | PC-017, R-570 | SPEC-PACK-06B | R-555/R-562 already build one app per role; the spec asks for role-scoped pages and APIs. From specs/pack-framework/06b.
54 | PC-076 | Page template engine: domain pages from templates with IR slots (dispatch board, SOAP notes ...) | 2 Maximum features | Both | Not Started | P1 | PC-017 | SPEC-PACK-06C | From specs/pack-framework/06c.
55 | PC-077 | Rich seed data generator: realistic, domain-aware, deterministic demo data | 2 Maximum features | Both | Pending | P2 | PC-017 | SPEC-PACK-06E | Fixture seeds exist (R-248) and must stay deterministic (R-586). From specs/pack-framework/06e.
56 | PC-072 | Blueprint conversion: turn RideNow, Bazaar and CareClinic templates into blueprints that regenerate them (golden-file test) | 2 Maximum features | Both | Not Started | P1 | PC-017, PC-075, PC-076 | SPEC-PACK-05 | From specs/pack-framework/05.
57 | PC-088 | Pack quality bar: a pack counts as done only when it builds a working demo app on every surface, passes its generated tests and passes a UI review | 2 Maximum features | Both | Not Started | P1 | PC-017, PC-054 |  | 321 packs: a mediocre pack hurts more than a missing one. Applies to every wave. Founder-approved 2026-09-26.
58 | PC-073 | Horizontal packs, wave 1: the P0/P1 universal packs as manifest v2 packs that work alone and compose (HP-* rows) | 2 Maximum features | Both | Pending | P1 | PC-017 | ARCH-PACKS, HP-admin-crud, HP-ai-assistant, HP-api-core, HP-app-store-assets, HP-auth-rbac, HP-camera-qr, HP-database-pg, HP-deep-links, HP-design-system, HP-files-storage, HP-geolocation, HP-in-app-purchases, HP-maps-geo, HP-mobile-push, HP-multi-app, HP-multi-tenancy, HP-notifications, HP-offline-sync, HP-payments-core, HP-pwa, HP-queue-jobs, HP-rbac-advanced, HP-realtime-core, HP-rules-engine, HP-scheduling, HP-secure-storage, HP-testing, HP-wallet-ledger, HP-workflows-core, SPEC-PACK-03 | Core first (auth, database, API, design system, admin, payments, notifications, files, realtime, workflows), then the mobile & device and AI packs. Each pack packages a capability built by its own task. Full list: PACK_CATALOG.md.
59 | PC-074 | Vertical packs, wave 1: healthcare, mobility, commerce (VP-* rows) on every surface: API, web, app, admin panel | 2 Maximum features | Both | Pending | P1 | PC-073, PC-072 | ARCH-VERTICALS, SPEC-PACK-04, VP-affiliates, VP-appointments, VP-auctions-bidding, VP-background-checks, VP-billing-codes, VP-cart-checkout, VP-clinical-trials, VP-commissions, VP-deliveries, VP-dental-clinic, VP-dispatch, VP-drivers, VP-emr, VP-fleet, VP-fulfillment, VP-hipaa-compliance, VP-insurance-commercial, VP-inventory, VP-lab-integration, VP-lab-orders, VP-last-mile, VP-listings, VP-marketplace-seo, VP-mental-health, VP-orders, VP-parking, VP-patients, VP-pharmacy-integration, VP-prescriptions, VP-providers, VP-purchase-orders, VP-returns, VP-reviews, VP-rides, VP-subscriptions-commerce, VP-surge-pricing, VP-telehealth, VP-vehicle-rentals, VP-vendors, VP-wishlists-recommendations | Built from the CareClinic, RideNow and Bazaar templates.
60 | PC-078 | Horizontal packs, wave 2 (P2 HP-* rows) | 2 Maximum features | Both | Not Started | P2 | PC-073 | HP-accessibility, HP-activity-feed, HP-analytics-events, HP-api-docs, HP-approvals, HP-audit-log, HP-audit-trail, HP-background-tasks, HP-billing-metering, HP-biometrics, HP-calendar-sync, HP-charts-dashboards, HP-ci-cd, HP-cms-marketing-site, HP-communications, HP-compliance-gdpr, HP-compliance-hipaa, HP-config-env, HP-consent-management, HP-coupons-promotions, HP-crash-reporting, HP-crm, HP-custom-domains, HP-data-import-export, HP-data-tables, HP-database-mongo, HP-e-sign, HP-encryption, HP-forms-engine, HP-identity-verification, HP-integration-hub, HP-invoicing, HP-localization, HP-marketplace-payments, HP-moderation, HP-multi-currency, HP-observability, HP-onboarding-invitations, HP-ota-updates, HP-pdf-documents, HP-performance, HP-pricing-engine, HP-ratings-reviews, HP-reporting, HP-rich-text, HP-secrets, HP-security-headers, HP-seo, HP-subscriptions, HP-support-helpdesk, HP-task-management, HP-theming-branding, HP-vector-search, HP-video-calling, HP-webhooks | Full list: PACK_CATALOG.md.
61 | PC-080 | Vertical packs, wave 2: the PRD's blueprints (quick commerce, fintech, food, real estate, edtech, SaaS/B2B, logistics, home services, beauty & wellness, HR) on every surface | 2 Maximum features | Both | Not Started | P2 | PC-074 | VP-accounts, VP-agent-crm, VP-api-management, VP-assignments, VP-attendance-leave, VP-basket-reorder, VP-bill-payments-upi, VP-candidate-pipeline, VP-cards, VP-catering, VP-certificates, VP-client-profiles, VP-co-living-rentals, VP-cohorts, VP-compliance-aml, VP-compliance-education, VP-compliance-kyc, VP-contracts, VP-couriers, VP-courses, VP-credit-scoring, VP-customer-success, VP-customs, VP-dark-stores, VP-delivery-slots, VP-delivery-tracking, VP-digital-assets, VP-employee-onboarding, VP-enrollments, VP-entitlements, VP-escrow, VP-fleet-management, VP-food-orders, VP-freight-forwarding, VP-ghost-kitchens, VP-grading, VP-grocery-catalog, VP-inventory-wms, VP-investment-analysis, VP-job-lifecycle, VP-job-quotes, VP-jobs-ats, VP-kitchen, VP-last-mile-logistics, VP-ledger-core, VP-lending, VP-listings-re, VP-live-classes, VP-lms-admin, VP-loyalty, VP-marketplace-saas, VP-memberships-packages, VP-menus, VP-offers, VP-open-banking, VP-organizations, VP-payroll, VP-performance-reviews, VP-personal-finance, VP-procurement, VP-properties, VP-property-mgmt, VP-provider-matching, VP-quizzes-exams, VP-regulatory-reporting, VP-restaurants, VP-rider-batching, VP-salon-booking, VP-scim-provisioning, VP-seats, VP-service-catalog, VP-service-menu, VP-service-warranty, VP-shipments, VP-sso-oidc, VP-sso-saml, VP-staff-schedules, VP-substitutions, VP-supply-chain-visibility, VP-table-reservations, VP-teams, VP-tours, VP-trade-finance, VP-transfers, VP-transportation, VP-treasury, VP-usage-metering, VP-video-streaming, VP-warehouses, VP-wealth-management, VP-white-label, VP-yard-management | Each domain's templates (Pocket, FreshCart, Estately, LearnHub, FixIt, Glow) showcase it.
62 | PC-079 | Horizontal packs, wave 3 (P3 HP-* rows) | 2 Maximum features | Both | Not Started | P3 | PC-078 | HP-api-gateway, HP-backups-restore, HP-bluetooth-nfc, HP-cache-layer, HP-compliance-soc2, HP-data-archival, HP-developer-portal, HP-feature-flags, HP-forecasting, HP-fraud-risk, HP-gamification, HP-git-ops, HP-health-fitness-data, HP-iot-telematics, HP-mcp-gateway, HP-media-player-device, HP-ml-inference, HP-onboarding-tours, HP-plugin-system, HP-referrals-affiliates, HP-search-engine, HP-share-contacts, HP-storybook, HP-tax-compliance | Full list: PACK_CATALOG.md.
63 | PC-081 | Vertical packs, wave 3: 16 further industries (professional services, content, travel, events, fitness, social, insurance, automotive, POS, manufacturing, legal, civic, utilities, pets, schools, construction, agriculture) on every surface | 2 Maximum features | Both | Not Started | P3 | PC-080 | VP-agents-brokers, VP-agri-marketplace, VP-articles-cms, VP-attendance-school, VP-bids-estimates, VP-bill-of-materials, VP-channel-manager, VP-check-in, VP-citizen-services, VP-claims, VP-class-booking, VP-client-intake, VP-client-portal, VP-clubs-leagues, VP-community-comments, VP-compliance-ps, VP-construction-projects, VP-court-calendar, VP-creator-monetization, VP-customer-loyalty-pos, VP-dating-matching, VP-dealer-inventory, VP-donations-fundraising, VP-editorial-workflow, VP-ev-charging, VP-events, VP-farm-advisory, VP-farms-fields, VP-feeds-posts, VP-field-service, VP-forums-qa, VP-grants, VP-groups-communities, VP-gym-memberships, VP-hotel-pms, VP-invoicing-ps, VP-itineraries, VP-legal-documents, VP-maintenance-cmms, VP-matters-cases, VP-meter-reading, VP-newsletters, VP-outage-management, VP-parent-portal, VP-parts-catalog, VP-paywall-membership, VP-permits-licensing, VP-personal-training, VP-pet-profiles, VP-pet-services, VP-podcasts-video, VP-policies, VP-pos-terminal, VP-premium-billing, VP-production-orders, VP-profiles-social, VP-projects, VP-proposals, VP-quality-control, VP-quotes-underwriting, VP-resource-planning, VP-retainers, VP-school-admin, VP-school-transport, VP-seating-maps, VP-service-center, VP-shift-cash-management, VP-site-diary, VP-sponsors-exhibitors, VP-store-inventory, VP-subcontractors, VP-test-drives, VP-ticketing, VP-time-tracking, VP-tours-activities, VP-travel-booking, VP-utility-billing, VP-vehicle-history, VP-vet-clinic, VP-volunteers, VP-workout-plans | One industry at a time, ordered by what users actually build.
64 | PC-018 | Template marketplace v2: blueprint catalog and pack publishing | 2 Maximum features | Vibe | Not Started | P2 | PC-017 | ARCH-TEMPLATES-UX, SPEC-TPL-01 | From specs/template-marketplace/01.
65 | TPL-POCKET | Template: Pocket, digital wallet (fintech) | 2 Maximum features | Vibe | Not Started | P2 | R-567 |  | Template plan section 6.3.
66 | TPL-LEARNHUB | Template: LearnHub, LMS + course marketplace | 2 Maximum features | Vibe | Not Started | P2 |  |  | Template plan section 6.4.
67 | TPL-GLOW | Template: Glow, salon and spa booking | 2 Maximum features | Vibe | Not Started | P3 |  |  | Template plan section 6.5.
68 | TPL-FRESHCART | Template: FreshCart, quick-commerce grocery | 2 Maximum features | Vibe | Not Started | P3 | R-569 |  | Template plan section 6.6.
69 | TPL-ESTATELY | Template: Estately, property marketplace + agent CRM | 2 Maximum features | Vibe | Not Started | P3 |  |  | Template plan section 6.7.
70 | TPL-FIXIT | Template: FixIt, home-services marketplace | 2 Maximum features | Vibe | Not Started | P3 |  |  | Template plan section 6.8.
71 | TPL-INKWELL | Template: Inkwell Press, blogging/publishing | 2 Maximum features | Vibe | Not Started | P3 |  |  | Template plan section 6.9.
72 | PC-019 | Visual click-to-edit in the preview (design tokens and copy only) | 2 Maximum features | Vibe | Not Started | P2 |  | BP-CLICKEDIT | Buildout plan idea 'R-520'.
73 | PC-020 | Brand kit / Style DNA UI across all surfaces | 2 Maximum features | Vibe | Pending | P2 |  | ARCH-COMPONENT-BROWSER, BP-BRANDKIT | brand.json exists (R-548); needs the UI. Buildout idea 'R-526'. Edits the per-project design direction PC-099 creates.
74 | PC-021 | Screenshot or Figma to app | 2 Maximum features | Vibe | Not Started | P3 |  | BP-FIGMA | Buildout idea 'R-527'.
75 | PC-048 | Database choice: MongoDB as an option beside PostgreSQL (the default) | 2 Maximum features | Both | Not Started | P2 | R-570 | ARCH-DB-OPTIONS, R-075 | D-8. Every backend adapter needs a Mongo data layer; lifecycle and uniqueness rules move from SQL constraints to schema validation and indexes. Lifts the Phase T 'PostgreSQL only' gate.
76 | PC-052 | File uploads and storage in generated apps (S3-compatible, presigned URLs, image processing) | 2 Maximum features | Both | Superseded | P1 | PC-102, PC-105 | ARCH-FILES | Local MinIO-style store for dev; any S3 provider on publish. From the architecture plan. Superseded 2026-09-30: PC-102 (Python, per-field rules, content checks, R2/S3/local, cloud drives through Companion; the founder chose R2/S3 and no MinIO) and PC-105 (Go and Node) did it. Left for later: image processing (resizing, thumbnails).
77 | PC-053 | Notifications in generated apps: email, push (Expo and native), in-app, user preferences | 2 Maximum features | Both | Not Started | P1 | R-568 | ARCH-NOTIFY | R-516 gives email. From the architecture plan.
78 | PC-054 | Tests generated with every app: API contract, end-to-end (Playwright), unit | 2 Maximum features | Both | Not Started | P1 |  | ARCH-TESTS | Architecture-plan target: over 80% coverage of generated code.
79 | PC-059 | Form and wizard engine: multi-step, conditional fields, draft autosave | 2 Maximum features | Both | Not Started | P2 |  | ARCH-FORMS | From the architecture plan.
80 | PC-057 | Generated-app operations: rate limiting, signed webhooks with retries, audit log, error tracking and tracing hooks | 2 Maximum features | Both | Not Started | P2 |  | ARCH-OBSERVABILITY | From the architecture plan (api-gateway, webhooks, audit, observability packs).
81 | PC-055 | Internationalisation in generated apps (web, admin, mobile) | 2 Maximum features | Both | Not Started | P2 |  | ARCH-I18N | From the architecture plan.
82 | PC-064 | iOS Simulator preview: Xcode installed and driven from the command line, simulator streamed into the Studio (Mac only) | 2 Maximum features | Both | Not Started | P2 | PC-063 | R-053 | See NATIVE_MOBILE_PREVIEW_PLAN.md. No open-source iOS simulator exists; Xcode is free but Mac-only.
83 | PC-056 | Feature flags and A/B tests in generated apps | 2 Maximum features | Both | Not Started | P3 |  | ARCH-FLAGS | From the architecture plan.
84 | PC-058 | Search engine option (Meilisearch or Typesense) beyond keyword search | 2 Maximum features | Both | Not Started | P3 |  | ARCH-SEARCH | From the architecture plan.
85 | R-583 | Next.js static export mode | 2 Maximum features | Both | Not Started | P3 |  |  | The cheap answer to 'no SSR, no Vercel'.
86 | PC-022 | Plan view: see and edit the plan (apps, roles, entities, flows) before building | 3 Engineering Mode | Engineering | Not Started | P1 | PC-005 | ARCH-ENG-OPTIONS, SPEC-ENG-01 | Buildout idea 'intent cards'; specs/engineering-mode/01. Shows the design direction (PC-099) with the plan.
87 | PC-023 | Stack chooser: pick web/admin/mobile/backend, refused with a reason when unsupported | 3 Engineering Mode | Engineering | Pending | P1 | PC-005 | R-135 | R-565 carries the stack in the IR; needs the UI.
88 | R-577 | Agentic mode core: plan -> edit files -> verify -> repair, bounded, auditable | 3 Engineering Mode | Engineering | Not Started | P1 |  | R-042, R-176, R-177, R-178, R-179, R-180, R-183, R-184
89 | R-578 | Import an existing local project (agentic mode, not IR mode) | 3 Engineering Mode | Engineering | Not Started | P1 | R-577 | ARCH-IMPORT-MODES, R-018, R-076, SPEC-REPO-01, SPEC-STUDIO-02
90 | R-579 | GitHub import and push-back | 3 Engineering Mode | Engineering | Pending | P1 | R-578 | ARCH-IMPORT-SOURCES | R-501 can push a generated project; import is missing.
91 | PC-024 | Diff review per change, with change impact / blast radius | 3 Engineering Mode | Engineering | Not Started | P1 | R-577 | R-016, R-017, T-5
92 | PC-025 | Verification report view: per-surface compile, tests, security, in the Studio | 3 Engineering Mode | Engineering | Pending | P1 |  |  | R-560/R-561/R-508 produce the data; nothing shows it as a report.
93 | PC-026 | Open GitHub pull requests (branch per change, PR naming) | 3 Engineering Mode | Engineering | Not Started | P1 | R-579 | R-021, R-125
94 | R-581 | Memory across sessions: semantic project memory on pgvector | 3 Engineering Mode | Both | Not Started | P1 |  | R-019, R-027, R-057
95 | PC-027 | Version timeline and safe, non-destructive rollback | 3 Engineering Mode | Both | Not Started | P1 |  | BP-TIMELINE, R-022
96 | PC-051 | Graduation bridge: open a Vibe project in Engineering Mode with nothing lost, and back | 3 Engineering Mode | Both | Not Started | P1 | PC-005, PC-022 | ARCH-GRADUATION | Projects already keep ir.json, so the IR carries over; custom UI and history must too - model-written pages (PC-098) are kept as the project's own code, never regenerated. From the architecture plan.
97 | PC-028 | Cloud deploy adapters beyond Vercel/Netlify: containers, Kubernetes (Helm), Terraform | 3 Engineering Mode | Engineering | Not Started | P2 | PC-008 | ARCH-K8S, SPEC-DEPLOY-01 | From specs/deploy-adapters/01 and the architecture plan.
98 | PC-029 | Team collaboration: roles, approvals, preview comments | 3 Engineering Mode | Engineering | Pending | P2 |  | BP-COMMENTS, R-064, R-065 | R-515 gives teams.
99 | PC-030 | Tool registry and MCP gateway with a tool secret broker | 3 Engineering Mode | Engineering | Not Started | P2 | R-577 | R-185, R-186, R-187
100 | PC-031 | Backup, restore drills and disaster recovery | 4 Production ops | Platform | Not Started | P1 | PC-009 | PG-08, R-096, R-097
101 | PC-032 | Security audits: independent pen test, DAST, prompt-injection and MCP isolation tests | 4 Production ops | Platform | Not Started | P1 | PC-009 | GA-09, PG-04, PG-06, PG-21, R-069, R-098, R-213
102 | PC-033 | Observability: platform logs, metrics, task trace, SLOs, incident process | 4 Production ops | Platform | Not Started | P1 | PC-009 | PG-07, PG-10, R-043, R-044, R-094, R-102
103 | PC-034 | Load and capacity tests | 4 Production ops | Platform | Not Started | P1 | PC-009 | PG-09, R-103
104 | PC-035 | Compliance: SOC 2 readiness, SBOM + licence gate, OSS licence review | 4 Production ops | Platform | Not Started | P2 |  | GA-11, R-070, R-099, R-154, R-190, R-219
105 | PC-036 | Migration safety checks for generated schema changes | 4 Production ops | Both | Pending | P1 |  | GA-08, PG-20, R-040 | R-584 flags data loss; needs a real gate.
106 | PC-037 | Release quality: qualification suite, API contract tests, visual regression, performance budgets | 4 Production ops | Platform | Not Started | P2 |  | ARCH-PERF, GAP-TESTTOOLS, PG-02, PG-03, R-039, R-059, R-060, R-105
107 | PC-038 | Reliability of runs: crash-resume, no duplicate side effects, stream replay | 4 Production ops | Platform | Not Started | P2 | R-577 | R-182, R-210, R-211, R-212, R-216
108 | PC-039 | Unit economics dashboard | 4 Production ops | Platform | Not Started | P2 | PC-010 | PG-12, R-110
109 | PC-040 | Environments per project (dev / preview / prod) | 4 Production ops | Both | Not Started | P2 |  | GA-07, R-126
110 | PC-065 | Hosted Android emulators for every user: Linux + KVM pool, per-session isolation, browser streaming, metering | 4 Production ops | Both | Not Started | P2 | PC-009, PC-063 |  | See NATIVE_MOBILE_PREVIEW_PLAN.md. Built and proven on a local Linux VM; the server account is plugged in at PC-070.
111 | PC-067 | Production readiness sign-off: every blocking gate PG-01..PG-21 has evidence | 4 Production ops | Platform | Not Started | P1 | PC-031..PC-041 | GA-10, PG-01, PG-17 | The tracker's Production_Gates sheet. The platform is not called production-ready before this.
112 | PC-041 | HA control plane and canary platform releases | 4 Production ops | Platform | Not Started | P2 | PC-009 | GA-12, PG-11, R-095, R-106
113 | PC-042 | Native go-ahead gate: founder approval, toolchains, Apple and Google accounts | 5 Native mobile (last) | Both | Not Started | P2 | Phases 1-4 |  | Standing rule: stop and ask before native mobile work.
114 | R-575 | Native Android: Kotlin + Jetpack Compose, best in class | 5 Native mobile (last) | Both | Not Started | P2 | PC-042 | ARCH-NATIVE, R-035, R-144, R-145, SPEC-NATIVE-01
115 | R-576 | Native iOS: Swift + SwiftUI, best in class | 5 Native mobile (last) | Both | Not Started | P2 | PC-042 | R-036, R-146, R-147
116 | PC-043 | Native recommendation: when to offer native instead of PWA | 5 Native mobile (last) | Both | Not Started | P2 | R-575, R-576 | R-120
117 | PC-044 | Signed native builds (AAB/IPA), signing-key hardening, and store submission through the R-574 pipeline | 5 Native mobile (last) | Both | Not Started | P2 | R-575, R-576 | R-049, R-050, R-101
118 | PC-082 | Native implementations of every mobile & device pack and every vertical pack's app screens in Kotlin/Compose and Swift/SwiftUI | 5 Native mobile (last) | Both | Not Started | P2 | R-575, R-576 |  | PRD §5.1: packs are stack-aware; React Native implementations come first with the pack itself.
119 | PC-045 | Native modules and PWA-to-native migration | 5 Native mobile (last) | Both | Not Started | P3 | R-575, R-576 | R-163, R-165
120 | PC-066 | Hosted iOS simulators on Mac hosts (on demand, metered) | 5 Native mobile (last) | Both | Not Started | P3 | PC-064 |  | Apple allows macOS only on Apple hardware, so this needs Mac servers. See NATIVE_MOBILE_PREVIEW_PLAN.md.
121 | PC-046 | Local Mac agent for iOS builds and simulators | 5 Native mobile (last) | Engineering | Not Started | P3 | R-576 | R-054, R-161
122 | PC-070 | Credentials handover: founder supplies cloud, database, payment, email, Apple and Google accounts and keys; each is plugged in without code changes | 6 Go-live (credentials last) | Platform | Not Started | P0 | Phases 1-5 |  | Everything before this is built so that only keys and secrets are missing. Keys go into the secrets store (R-503) or .env, never into code, prompts or logs. D-2, D-3, D-6, D-7.
123 | PC-071 | Live proof of every 'Completed - needs live proof' item with the real accounts | 6 Go-live (credentials last) | Platform | Not Started | P0 | PC-070 |  | Publish to a real URL, a real payment, a real email, EAS/store uploads to both stores.
124 | PC-015 | Private beta with real users: product KPIs, minimal support tooling, feedback | 6 Go-live (credentials last) | Platform | Not Started | P0 | PC-071 | PG-15, R-051, R-107, R-513 | The platform is not 'live' until strangers use it.
125 | PC-083 | Head-to-head benchmark: the same 20 prompts on OmniStackAI, Lovable, Bolt, v0, Emergent and Replit; score UI quality, working features, build success and time | 7 Win the category | Both | Not Started | P1 | PC-015 |  | Without measurement 'best' is an opinion. Re-run every quarter (PC-087).
126 | PC-089 | Win on UI polish and speed against Lovable, Bolt and v0: iterate on the benchmark until we lead it | 7 Win the category | Vibe | Not Started | P1 | PC-083, PC-084 |  | Their whole focus, improved weekly; matching needs features, beating needs measurement.
127 | PC-090 | Engineering Mode positioning and proof: 'designs and builds structured multi-app platforms with verification', benchmarked against Cursor, Claude Code, Codex and Devin on platform-building tasks | 7 Win the category | Engineering | Not Started | P1 | PC-083 |  | We do not try to be a better general code editor; we win where they do not compete: whole platforms from a plan, verified.
128 | PC-091 | Native lead: match or beat the native Swift/Kotlin builders on quality and speed | 7 Win the category | Both | Not Started | P2 | R-575, R-576, PC-083 |  | Some builders already generate native apps; ours arrives in Phase 5.
129 | PC-086 | Public launch: docs site, tutorials and videos, pricing page, community, launch campaign | 7 Win the category | Platform | Not Started | P1 | PC-015 |  | The plan otherwise stops at a private beta.
130 | PC-092 | Users and brand: growth loops (referrals, template showcase, made-with gallery), partnerships, content, measured activation and retention | 7 Win the category | Platform | Not Started | P1 | PC-086 |  | Competitors already have millions of users.
131 | PC-087 | Quarterly competitor review: re-run the benchmark, update the plan and this queue | 7 Win the category | Platform | Not Started | P2 | PC-083 |  | Recurring; competitors ship weekly.

## All Tasks
ID | Task | Source | Area / Mode | Phase | Status | Priority | Tracked in | Done on | Notes
PC-096 | In-browser WebContainer preview engine behind the PC-007 engine switch (Node in the visitor's browser; licence key supplied at PC-070) | Platform_Completion queue | Vibe | 1 Vibe Mode live | Pending | P2 |  |  | Blocked on the founder (2026-09-30): needs StackBlitz's commercial licence (decision D-6), a paid service - skipped by the queue until decided. Split out of PC-007 on 2026-09-27: PC-007 delivers the engine switch and the open-source container engine; WebContainer needs StackBlitz's commercial licence (D-6) and runs Node only, so Python/Go APIs still need a server-side engine behind it.
PC-014 | Local/offline models as a first-class path: build fully on Ollama, recommend a model per machine | Platform_Completion queue | Both | 1 Vibe Mode live | Pending | P1 |  |  | Ollama adapter exists (R-003/R-006). Found in PC-084: .env names qwen2.5-coder:14b but only 7b is installed, and the adapter refuses a pinned model it was not configured with — detect installed models instead of trusting the setting. PC-098 (2026-09-28): the founder replaced 7b with qwen2.5-coder:14b; the Ollama adapter now sends num_ctx (long prompts were cut silently) and page design sizes it to 16k context / 6k answer.
R-574 | Store publishing for React Native apps: EAS build and submit to Play Store and App Store, proven with real accounts | Platform_Completion queue | Both | 1 Vibe Mode live | Pending | P1 |  |  | R-546/R-547 generate the EAS config. Everything up to the upload is built and tested; the Apple and Google accounts (D-7) are plugged in at PC-070.
PC-017 | Pack framework core: manifest v2 schema, registry/loader, composer (merge, wire, validate, conflict rules) | Platform_Completion queue | Both | 2 Maximum features | Pending | P1 |  |  | Solution Pack manifests, registry and application exist (R-434..R-445); v2 adds ir_delta, state machines, page templates, dependencies. From specs/pack-framework 01, 02.
PC-075 | Role-based app generator: a complete app per role (nav, pages, API scope, permissions) | Platform_Completion queue | Both | 2 Maximum features | Pending | P1 |  |  | R-555/R-562 already build one app per role; the spec asks for role-scoped pages and APIs. From specs/pack-framework/06b.
PC-077 | Rich seed data generator: realistic, domain-aware, deterministic demo data | Platform_Completion queue | Both | 2 Maximum features | Pending | P2 |  |  | Fixture seeds exist (R-248) and must stay deterministic (R-586). From specs/pack-framework/06e.
PC-073 | Horizontal packs, wave 1: the P0/P1 universal packs as manifest v2 packs that work alone and compose (HP-* rows) | Platform_Completion queue | Both | 2 Maximum features | Pending | P1 |  |  | Core first (auth, database, API, design system, admin, payments, notifications, files, realtime, workflows), then the mobile & device and AI packs. Each pack packages a capability built by its own task. Full list: PACK_CATALOG.md.
PC-074 | Vertical packs, wave 1: healthcare, mobility, commerce (VP-* rows) on every surface: API, web, app, admin panel | Platform_Completion queue | Both | 2 Maximum features | Pending | P1 |  |  | Built from the CareClinic, RideNow and Bazaar templates.
PC-020 | Brand kit / Style DNA UI across all surfaces | Platform_Completion queue | Vibe | 2 Maximum features | Pending | P2 |  |  | brand.json exists (R-548); needs the UI. Buildout idea 'R-526'. Edits the per-project design direction PC-099 creates.
PC-023 | Stack chooser: pick web/admin/mobile/backend, refused with a reason when unsupported | Platform_Completion queue | Engineering | 3 Engineering Mode | Pending | P1 |  |  | R-565 carries the stack in the IR; needs the UI.
R-579 | GitHub import and push-back | Platform_Completion queue | Engineering | 3 Engineering Mode | Pending | P1 |  |  | R-501 can push a generated project; import is missing.
PC-025 | Verification report view: per-surface compile, tests, security, in the Studio | Platform_Completion queue | Engineering | 3 Engineering Mode | Pending | P1 |  |  | R-560/R-561/R-508 produce the data; nothing shows it as a report.
PC-029 | Team collaboration: roles, approvals, preview comments | Platform_Completion queue | Engineering | 3 Engineering Mode | Pending | P2 |  |  | R-515 gives teams.
PC-036 | Migration safety checks for generated schema changes | Platform_Completion queue | Both | 4 Production ops | Pending | P1 |  |  | R-584 flags data loss; needs a real gate.
ARCH-DOMAIN-IR | Domain IR: guards, business rules, field masks, row filters, page templates | docs/ARCHITECTURE_MASTER_PLAN.md §5.2 |  | 2 Maximum features | Pending | P1 | R-570 |  | State machines done (R-566); field masks and row filters are R-570; guards and rules R-571.
ARCH-GENERATORS | Advanced generators: state machine, role app, page template, shared package, seed data, form wizard, realtime | docs/ARCHITECTURE_MASTER_PLAN.md §5.3 |  | 2 Maximum features | Pending | P1 | PC-017 |  | State machine done (R-566/588/589); shared package R-572; form wizard PC-059; realtime R-569.
ARCH-PIPELINE | Vibe pipeline: classify -> select packs -> compose IR -> generate -> provision -> preview in 90 s | docs/ARCHITECTURE_MASTER_PLAN.md §4.1 |  | Delivered | Pending | P0 | PC-004 |  | Generate and preview exist; provision is PC-049.
ARCH-PWA | PWA / offline support | docs/ARCHITECTURE_MASTER_PLAN.md §10 Phase 4 |  | Delivered | Pending | P0 | R-573
BP-BRANDKIT | Style DNA UI and brand kit studio | Platform_Buildout section 8 ('R-526') |  | 2 Maximum features | Pending | P2 | PC-020
BP-SWITCHER | Multi-app ecosystem switcher and persona simulator | Platform_Buildout section 8 ('R-521') |  | Delivered | Pending | P1 | PC-006 |  | Multi-app preview exists (R-520, R-553); personas do not.
GA-03 | First-class Ollama-compatible provider with quality eval | Tracker RND_Gap_Audit |  | 1 Vibe Mode live | Pending | P1 | PC-014 |  | Provider done (R-006); eval missing.
GA-04 | Per-model safe context registry, no silent truncation | Tracker RND_Gap_Audit |  | 1 Vibe Mode live | Pending | P1 | PC-014 |  | Safe input budget exists (R-522).
GA-05 | Route by measured task, eval, latency, context and cost | Tracker RND_Gap_Audit |  | 1 Vibe Mode live | Pending | P2 | PC-014
GA-07 | Environments local -> test -> preview -> staging -> prod with typed config | Tracker RND_Gap_Audit |  | 4 Production ops | Pending | P2 | PC-040
GA-11 | Pinned supply chain, SBOM/provenance, patch SLA | Tracker RND_Gap_Audit |  | 4 Production ops | Pending | P2 | PC-035 |  | Lockfiles pinned; SBOM missing.
GAP-TESTTOOLS | Pin the testing toolchain (Playwright, pytest, go test, k6) | V6_Review_and_Gap_Analysis section 3 |  | 4 Production ops | Pending | P2 | PC-037 |  | pytest/unittest, go test and Playwright (templates) are in use; k6 is not.
HP-accessibility | Horizontal pack accessibility: WCAG 2.1 AA, automated axe checks | spec | UI & experience | 2 Maximum features | Pending | P2 | PC-078 |  | Accessible UI exists (R-296).
HP-activity-feed | Horizontal pack activity-feed: Activity streams, timelines, follow/subscribe | new (registry dependency) | Realtime & communication | 2 Maximum features | Pending | P2 | PC-078 |  | Timeline component exists (R-336).
HP-admin-crud | Horizontal pack admin-crud: Generated admin: tables, filters, bulk actions, exports | spec | Core platform | 2 Maximum features | Pending | P1 | PC-073 |  | Admin app exists (R-542, R-270, R-271).
HP-analytics-events | Horizontal pack analytics-events: Event tracking, funnels, cohorts (PostHog/GA4) | spec, registry | Data & storage | 2 Maximum features | Pending | P2 | PC-078 |  | Published-app analytics exists (R-513).
HP-api-core | Horizontal pack api-core: REST API, validation, OpenAPI, errors, rate limiting | registry | Core platform | 2 Maximum features | Pending | P1 | PC-073 |  | Python/Go/Node APIs exist (R-229, R-230, R-517).
HP-api-docs | Horizontal pack api-docs: OpenAPI, Swagger UI, Postman collection, SDKs | spec | Core platform | 2 Maximum features | Pending | P2 | PC-078 |  | OpenAPI exists (R-260, R-588).
HP-app-store-assets | Horizontal pack app-store-assets: Icons, splash, screenshots, store listing metadata | new | Mobile & device (stack-aware: React Native, Kotlin, Swift) | 2 Maximum features | Pending | P1 | PC-073 |  | Icons and EAS config exist (R-546, R-547); R-574.
HP-auth-rbac | Horizontal pack auth-rbac: Login, register, roles, sessions, MFA, OAuth, passkeys | spec, registry | Core platform | 2 Maximum features | Pending | P1 | PC-073 |  | Auth exists (R-461, R-241..R-243); Go login R-591.
HP-camera-qr | Horizontal pack camera-qr: Camera, photo/video capture, QR and barcode scanning | PRD (+ registry 'barcode') | Mobile & device (stack-aware: React Native, Kotlin, Swift) | 2 Maximum features | Pending | P1 | PC-073 |  | QR generation exists (R-382).
HP-charts-dashboards | Horizontal pack charts-dashboards: Charts, dashboards, live series | registry | UI & experience | 2 Maximum features | Pending | P2 | PC-078 |  | Chart suite exists (R-370).
HP-ci-cd | Horizontal pack ci-cd: CI workflows, containers, Helm, preview environments | registry | Core platform | 2 Maximum features | Pending | P2 | PC-078 |  | CI/CD workflow generation exists (R-452).
HP-communications | Horizontal pack communications: 1:1 and group chat, threads, mentions, reactions, attachments | spec, registry | Realtime & communication | 2 Maximum features | Pending | P2 | PC-078 |  | Chat component exists (R-384).
HP-config-env | Horizontal pack config-env: Typed env config, secret references, multi-environment | registry | Core platform | 2 Maximum features | Pending | P2 | PC-078 |  | Credential templates exist (R-547).
HP-consent-management | Horizontal pack consent-management: Consent capture and ledger, cookie preferences | new (registry dependency) | Security & compliance | 2 Maximum features | Pending | P2 | PC-078 |  | Cookie consent component exists (R-402).
HP-custom-domains | Horizontal pack custom-domains: Custom domains, DNS, TLS certificates | new (registry dependency 'dns') | Core platform | 2 Maximum features | Pending | P2 | PC-078 |  | Custom domains exist for published apps (R-510).
HP-data-import-export | Horizontal pack data-import-export: CSV/Excel import with mapping and validation; bulk export | new | Data & storage | 2 Maximum features | Pending | P2 | PC-078 |  | CSV/JSON export exists (R-271, R-308).
HP-data-tables | Horizontal pack data-tables: Virtualised tables, grouping, column picker, export | registry | UI & experience | 2 Maximum features | Pending | P2 | PC-078 |  | Data grid exists (R-329).
HP-database-pg | Horizontal pack database-pg: PostgreSQL schema, migrations, seeds, row-level security | registry | Core platform | 2 Maximum features | Pending | P1 | PC-073 |  | Schema/migrations/seeds exist (R-238, R-248).
HP-design-system | Horizontal pack design-system: Design tokens, components, motion, dark mode | registry | UI & experience | 2 Maximum features | Pending | P1 | PC-073 |  | Design system exists (R-558, R-324, R-491).
HP-e-sign | Horizontal pack e-sign: Document signing, signer flows, certificates | new (registry dependency) | Business logic & workflow | 2 Maximum features | Pending | P2 | PC-078 |  | Signature pad exists (R-372).
HP-integration-hub | Horizontal pack integration-hub: Connectors (Slack, HubSpot, Salesforce ...), workflow builder | registry | Integration & AI | 2 Maximum features | Pending | P2 | PC-078 |  | Connectors v1 exist (R-511).
HP-maps-geo | Horizontal pack maps-geo: Maps, geocoding, geofences, routes, address autocomplete | registry ('mapping', listed under mobility), PRD | UI & experience | 2 Maximum features | Pending | P1 | PC-073 |  | Geo-map component exists (R-387).
HP-media-player-device | Horizontal pack media-player-device: Audio/video playback, background audio, casting | new | Mobile & device (stack-aware: React Native, Kotlin, Swift) | 2 Maximum features | Pending | P3 | PC-079 |  | Web media players exist (R-376, R-390).
HP-multi-app | Horizontal pack multi-app: Shared API, cross-app auth, preview proxy, deploy coordination | spec | Core platform | 2 Maximum features | Pending | P1 | PC-073 |  | Ecosystem monorepo exists (R-554, R-447, R-553).
HP-multi-currency | Horizontal pack multi-currency: Currencies, exchange rates, price lists | registry (listed under commerce) | Commerce & payments | 2 Maximum features | Pending | P2 | PC-078 |  | Currency input exists (R-409).
HP-notifications | Horizontal pack notifications: Email, SMS, push, in-app centre, preferences, digests | spec, registry | Realtime & communication | 2 Maximum features | Pending | P1 | PC-073 |  | Email exists (R-516); PC-053.
HP-onboarding-tours | Horizontal pack onboarding-tours: Product tours and spotlight guides | new | UI & experience | 2 Maximum features | Pending | P3 | PC-079 |  | Tour component exists (R-363).
HP-payments-core | Horizontal pack payments-core: Stripe/Razorpay/Paddle payments, refunds, disputes | spec, registry, PRD | Commerce & payments | 2 Maximum features | Pending | P1 | PC-073 |  | Checkout exists (R-512).
HP-pdf-documents | Horizontal pack pdf-documents: Document templates, PDF generation, document store | new (registry dependencies 'documents', 'pdf-generation') | Data & storage | 2 Maximum features | Pending | P2 | PC-078 |  | PDF viewer component exists (R-388).
HP-pwa | Horizontal pack pwa: Installable app, service worker, offline, push, QR | spec | UI & experience | 2 Maximum features | Pending | P0 | PC-073 |  | R-573.
HP-ratings-reviews | Horizontal pack ratings-reviews: Stars, reviews, moderation, aggregates | spec | Business logic & workflow | 2 Maximum features | Pending | P2 | PC-078 |  | Rating component exists (R-333).
HP-rich-text | Horizontal pack rich-text: Rich text editor, mentions, slash commands | registry | UI & experience | 2 Maximum features | Pending | P2 | PC-078 |  | Markdown editor exists (R-365).
HP-scheduling | Horizontal pack scheduling: Calendars, recurrence, conflicts, time zones, bookings, reminders | spec, registry | Business logic & workflow | 2 Maximum features | Pending | P1 | PC-073 |  | Calendar/time-picker components exist (R-366, R-371).
HP-search-engine | Horizontal pack search-engine: Meilisearch/Typesense, facets, typo tolerance | spec, registry | Data & storage | 2 Maximum features | Pending | P3 | PC-079 |  | Keyword search exists (R-261); PC-058.
HP-secrets | Horizontal pack secrets: Secret management, rotation, audit | spec | Security & compliance | 2 Maximum features | Pending | P2 | PC-078 |  | Platform secrets exist (R-503).
HP-seo | Horizontal pack seo: Metadata, sitemaps, structured data, AI-search readiness | new (registry dependency) | UI & experience | 2 Maximum features | Pending | P2 | PC-078 |  | SEO exists (R-505).
HP-task-management | Horizontal pack task-management: Tasks, assignees, due dates, boards | new (registry dependency 'tasks') | Business logic & workflow | 2 Maximum features | Pending | P2 | PC-078 |  | Kanban component exists (R-367).
HP-theming-branding | Horizontal pack theming-branding: Brand kit applied to every surface | new | UI & experience | 2 Maximum features | Pending | P2 | PC-078 |  | brand.json exists (R-548); PC-020.
HP-webhooks | Horizontal pack webhooks: Outgoing webhooks, retries, signatures, replay | spec, registry | Realtime & communication | 2 Maximum features | Pending | P2 | PC-078 |  | Cross-surface webhooks exist (R-448); PC-057.
HP-workflows-core | Horizontal pack workflows-core: State machines, transitions, guards, actions, audit | spec, registry | Business logic & workflow | 2 Maximum features | Pending | P1 | PC-073 |  | Transitions done (R-566, R-588, R-589); guards R-571; buttons R-590.
PG-17 | A fresh AI/developer session resumes the task from Git + durable state | Tracker Production_Gates |  | 4 Production ops | Pending | P1 | PC-067 |  | AGENTS.md, CURRENT_TASK.yaml and this queue exist; the formal drill does not.
PG-19 | Local model endpoint exposure/auth/network policy | Tracker Production_Gates |  | 1 Vibe Mode live | Pending | P1 | PC-014 |  | Ollama is loopback-only (R-003).
R-027 | pgvector initially | Execution_Tracker_v6 | Data | 3 Engineering Mode | Pending | P1 | R-581 |  | Extension installed, no embeddings table.
R-040 | Migration safety checks | Execution_Tracker_v6 | Testing | 4 Production ops | Pending | P1 | PC-036
R-055 | Verified integration catalog | Execution_Tracker_v6 | Integrations | Delivered | Pending | P1 | PC-013
R-062 | App Store / TestFlight automation | Execution_Tracker_v6 | Deployment | 1 Vibe Mode live | Pending | P1 | R-574 |  | React Native first; native reuses the pipeline (PC-044).
R-063 | Play Store automation | Execution_Tracker_v6 | Deployment | 1 Vibe Mode live | Pending | P1 | R-574 |  | React Native first; native reuses the pipeline (PC-044).
R-064 | RBAC + approvals | Execution_Tracker_v6 | Collaboration | 3 Engineering Mode | Pending | P2 | PC-029
R-080 | Self-hosted/local models | Execution_Tracker_v6 | Models | 1 Vibe Mode live | Pending | P1 | PC-014 |  | Ollama adapter exists (R-003, R-006).
R-126 | Organization > Workspace > Project > Environment model | Execution_Tracker_v6 | Product Foundation | 4 Production ops | Pending | P2 | PC-040 |  | Org, workspace and project exist (R-499, R-515).
R-135 | Stack selection wizard | Execution_Tracker_v6 | Framework Strategy | 3 Engineering Mode | Pending | P1 | PC-023
R-194 | Hybrid BYOK/local mode | Execution_Tracker_v6 | Execution | 1 Vibe Mode live | Pending | P1 | PC-014
SPEC-PACK-01 | Pack manifest v2 schema | specs/pack-framework/01 |  | 2 Maximum features | Pending | P1 | PC-017 |  | Draft spec (called R-600 inside).
SPEC-PACK-06B | Role-based app generator | specs/pack-framework/06b |  | 2 Maximum features | Pending | P1 | PC-075 |  | R-555 and R-562 build one app per role; the spec asks for more.
SPEC-PACK-06E | Rich seed data generator | specs/pack-framework/06e |  | 2 Maximum features | Pending | P2 | PC-077 |  | Seeds exist (R-248); the spec asks for realistic volume.
SPEC-TS-01 | Instant chat -> pretty UI | specs/table-stakes/01 |  | Delivered | Pending | P0 | PC-006 |  | Draft spec.
SPEC-TS-03 | One-click deploy | specs/table-stakes/03 |  | Delivered | Pending | P0 | PC-008 |  | Draft spec.
VP-appointments | Vertical pack appointments: Appointments, slots, reminders, waitlist | registry | Healthcare & life sciences (healthcare-core) | 2 Maximum features | Pending | P1 | PC-074 |  | CareClinic template.
VP-cart-checkout | Vertical pack cart-checkout: Cart, coupons, checkout sessions | registry | Marketplace & commerce (commerce-core) | 2 Maximum features | Pending | P1 | PC-074 |  | Bazaar template.
VP-commissions | Vertical pack commissions: Commission rules, splits, payout cycles | registry | Marketplace & commerce (commerce-core) | 2 Maximum features | Pending | P1 | PC-074 |  | Bazaar ledger.
VP-dispatch | Vertical pack dispatch: Zones, assignment rules, heatmaps | registry | Mobility & on-demand (mobility-core) | 2 Maximum features | Pending | P1 | PC-074 |  | RideNow template (partial).
VP-drivers | Vertical pack drivers: Drivers, vehicles, documents, earnings | registry | Mobility & on-demand (mobility-core) | 2 Maximum features | Pending | P1 | PC-074 |  | RideNow template.
VP-emr | Vertical pack emr: Encounters, notes, diagnoses, vitals | registry | Healthcare & life sciences (healthcare-core) | 2 Maximum features | Pending | P1 | PC-074 |  | CareClinic template (partial).
VP-listings | Vertical pack listings: Listings, categories, variants, media | registry | Marketplace & commerce (commerce-core) | 2 Maximum features | Pending | P1 | PC-074 |  | Bazaar template.
VP-orders | Vertical pack orders: Orders, line items, timelines | new (registry dependency) | Marketplace & commerce (commerce-core) | 2 Maximum features | Pending | P1 | PC-074 |  | Bazaar template.
VP-patients | Vertical pack patients: Patients, records, insurance, consent | registry | Healthcare & life sciences (healthcare-core) | 2 Maximum features | Pending | P1 | PC-074 |  | CareClinic template.
VP-prescriptions | Vertical pack prescriptions: Prescriptions, medications, pharmacies | registry | Healthcare & life sciences (healthcare-core) | 2 Maximum features | Pending | P1 | PC-074 |  | CareClinic template (partial).
VP-providers | Vertical pack providers: Providers, specialties, licences, schedules | registry | Healthcare & life sciences (healthcare-core) | 2 Maximum features | Pending | P1 | PC-074 |  | CareClinic template.
VP-rides | Vertical pack rides: Rides, routes, fares, matching, receipts | registry | Mobility & on-demand (mobility-core) | 2 Maximum features | Pending | P1 | PC-074 |  | RideNow template.
VP-telehealth | Vertical pack telehealth: Video consults, consent, technical checks | registry | Healthcare & life sciences (healthcare-core) | 2 Maximum features | Pending | P1 | PC-074 |  | CareClinic template.
VP-vendors | Vertical pack vendors: Vendors, storefronts, verification | registry | Marketplace & commerce (commerce-core) | 2 Maximum features | Pending | P1 | PC-074 |  | Bazaar template.
PC-049 | Managed database for published apps: provision PostgreSQL (Neon, Supabase or self-hosted) and run migrations and seeds on publish | Platform_Completion queue | Vibe | 1 Vibe Mode live | Not Started | P0 |  |  | A live URL needs a live database. Provider interface with a local Docker implementation; MongoDB Atlas once PC-048 exists. From the architecture plan. PC-008 (2026-09-27) delivered the per-app PostgreSQL in Docker with a migration ledger; left: hosted providers (Neon/Supabase), backups, and follow-on migrations for schema changes after first publish (today a changed 0001_init.sql is not re-applied to a live database).
PC-063 | Android emulator preview without Android Studio: SDK command-line bootstrap, headless emulator, auto-install, streamed into the Studio | Platform_Completion queue | Both | 1 Vibe Mode live | Not Started | P1 |  |  | See NATIVE_MOBILE_PREVIEW_PLAN.md. Open source first; local on the founder's Mac, then hosted in PC-065.
R-582 | Smarter IR synthesis: multi-pass planning and self-critique before generation | Platform_Completion queue | Both | 2 Maximum features | Not Started | P1 |  |  | Where 'more features per prompt' is won.
R-580 | Domain knowledge in ecosystem detection ('logistics' implies drivers) | Platform_Completion queue | Both | 2 Maximum features | Not Started | P1
R-570 | Permissions beyond role: ownership and row-level rules | Platform_Completion queue | Both | 2 Maximum features | Not Started | P1 |  |  | 'A driver sees only their own orders'. Seen live 2026-09-27 (PC-008): a published notes app saved notes with created_by null, so private notes were not private.
R-567 | Money: ledgers, payments, payouts, refunds, commission | Platform_Completion queue | Both | 2 Maximum features | Not Started | P1 |  |  | R-512 gives Stripe/Razorpay checkout; this is the ledger.
R-568 | Background jobs and scheduling | Platform_Completion queue | Both | 2 Maximum features | Not Started | P1
R-569 | Realtime channels: tracking, notifications, live status | Platform_Completion queue | Both | 2 Maximum features | Not Started | P1
R-571 | Escape hatch: behaviour the IR declares and the model implements, verified | Platform_Completion queue | Both | 2 Maximum features | Not Started | P1 |  |  | No hard ceiling, only a typed boundary.
PC-016 | Edit a workflow by chat (add/rename states and transitions safely) | Platform_Completion queue | Both | 2 Maximum features | Not Started | P1
R-572 | Shared contract package: one generated packages/ for types, client, validation | Platform_Completion queue | Both | 2 Maximum features | Not Started | P1 |  |  | Also puts the /auth routes (R-591) into the generated OpenAPI contract.
R-585 | Template customisation as a first-class flow | Platform_Completion queue | Both | 2 Maximum features | Not Started | P1
PC-076 | Page template engine: domain pages from templates with IR slots (dispatch board, SOAP notes ...) | Platform_Completion queue | Both | 2 Maximum features | Not Started | P1 |  |  | From specs/pack-framework/06c.
PC-072 | Blueprint conversion: turn RideNow, Bazaar and CareClinic templates into blueprints that regenerate them (golden-file test) | Platform_Completion queue | Both | 2 Maximum features | Not Started | P1 |  |  | From specs/pack-framework/05.
PC-088 | Pack quality bar: a pack counts as done only when it builds a working demo app on every surface, passes its generated tests and passes a UI review | Platform_Completion queue | Both | 2 Maximum features | Not Started | P1 |  |  | 321 packs: a mediocre pack hurts more than a missing one. Applies to every wave. Founder-approved 2026-09-26.
PC-078 | Horizontal packs, wave 2 (P2 HP-* rows) | Platform_Completion queue | Both | 2 Maximum features | Not Started | P2 |  |  | Full list: PACK_CATALOG.md.
PC-080 | Vertical packs, wave 2: the PRD's blueprints (quick commerce, fintech, food, real estate, edtech, SaaS/B2B, logistics, home services, beauty & wellness, HR) on every surface | Platform_Completion queue | Both | 2 Maximum features | Not Started | P2 |  |  | Each domain's templates (Pocket, FreshCart, Estately, LearnHub, FixIt, Glow) showcase it.
PC-079 | Horizontal packs, wave 3 (P3 HP-* rows) | Platform_Completion queue | Both | 2 Maximum features | Not Started | P3 |  |  | Full list: PACK_CATALOG.md.
PC-081 | Vertical packs, wave 3: 16 further industries (professional services, content, travel, events, fitness, social, insurance, automotive, POS, manufacturing, legal, civic, utilities, pets, schools, construction, agriculture) on every surface | Platform_Completion queue | Both | 2 Maximum features | Not Started | P3 |  |  | One industry at a time, ordered by what users actually build.
PC-018 | Template marketplace v2: blueprint catalog and pack publishing | Platform_Completion queue | Vibe | 2 Maximum features | Not Started | P2 |  |  | From specs/template-marketplace/01.
TPL-POCKET | Template: Pocket, digital wallet (fintech) | Platform_Completion queue | Vibe | 2 Maximum features | Not Started | P2 |  |  | Template plan section 6.3.
TPL-LEARNHUB | Template: LearnHub, LMS + course marketplace | Platform_Completion queue | Vibe | 2 Maximum features | Not Started | P2 |  |  | Template plan section 6.4.
TPL-GLOW | Template: Glow, salon and spa booking | Platform_Completion queue | Vibe | 2 Maximum features | Not Started | P3 |  |  | Template plan section 6.5.
TPL-FRESHCART | Template: FreshCart, quick-commerce grocery | Platform_Completion queue | Vibe | 2 Maximum features | Not Started | P3 |  |  | Template plan section 6.6.
TPL-ESTATELY | Template: Estately, property marketplace + agent CRM | Platform_Completion queue | Vibe | 2 Maximum features | Not Started | P3 |  |  | Template plan section 6.7.
TPL-FIXIT | Template: FixIt, home-services marketplace | Platform_Completion queue | Vibe | 2 Maximum features | Not Started | P3 |  |  | Template plan section 6.8.
TPL-INKWELL | Template: Inkwell Press, blogging/publishing | Platform_Completion queue | Vibe | 2 Maximum features | Not Started | P3 |  |  | Template plan section 6.9.
PC-019 | Visual click-to-edit in the preview (design tokens and copy only) | Platform_Completion queue | Vibe | 2 Maximum features | Not Started | P2 |  |  | Buildout plan idea 'R-520'.
PC-021 | Screenshot or Figma to app | Platform_Completion queue | Vibe | 2 Maximum features | Not Started | P3 |  |  | Buildout idea 'R-527'.
PC-048 | Database choice: MongoDB as an option beside PostgreSQL (the default) | Platform_Completion queue | Both | 2 Maximum features | Not Started | P2 |  |  | D-8. Every backend adapter needs a Mongo data layer; lifecycle and uniqueness rules move from SQL constraints to schema validation and indexes. Lifts the Phase T 'PostgreSQL only' gate.
PC-053 | Notifications in generated apps: email, push (Expo and native), in-app, user preferences | Platform_Completion queue | Both | 2 Maximum features | Not Started | P1 |  |  | R-516 gives email. From the architecture plan.
PC-054 | Tests generated with every app: API contract, end-to-end (Playwright), unit | Platform_Completion queue | Both | 2 Maximum features | Not Started | P1 |  |  | Architecture-plan target: over 80% coverage of generated code.
PC-059 | Form and wizard engine: multi-step, conditional fields, draft autosave | Platform_Completion queue | Both | 2 Maximum features | Not Started | P2 |  |  | From the architecture plan.
PC-057 | Generated-app operations: rate limiting, signed webhooks with retries, audit log, error tracking and tracing hooks | Platform_Completion queue | Both | 2 Maximum features | Not Started | P2 |  |  | From the architecture plan (api-gateway, webhooks, audit, observability packs).
PC-055 | Internationalisation in generated apps (web, admin, mobile) | Platform_Completion queue | Both | 2 Maximum features | Not Started | P2 |  |  | From the architecture plan.
PC-064 | iOS Simulator preview: Xcode installed and driven from the command line, simulator streamed into the Studio (Mac only) | Platform_Completion queue | Both | 2 Maximum features | Not Started | P2 |  |  | See NATIVE_MOBILE_PREVIEW_PLAN.md. No open-source iOS simulator exists; Xcode is free but Mac-only.
PC-056 | Feature flags and A/B tests in generated apps | Platform_Completion queue | Both | 2 Maximum features | Not Started | P3 |  |  | From the architecture plan.
PC-058 | Search engine option (Meilisearch or Typesense) beyond keyword search | Platform_Completion queue | Both | 2 Maximum features | Not Started | P3 |  |  | From the architecture plan.
R-583 | Next.js static export mode | Platform_Completion queue | Both | 2 Maximum features | Not Started | P3 |  |  | The cheap answer to 'no SSR, no Vercel'.
PC-022 | Plan view: see and edit the plan (apps, roles, entities, flows) before building | Platform_Completion queue | Engineering | 3 Engineering Mode | Not Started | P1 |  |  | Buildout idea 'intent cards'; specs/engineering-mode/01. Shows the design direction (PC-099) with the plan.
R-577 | Agentic mode core: plan -> edit files -> verify -> repair, bounded, auditable | Platform_Completion queue | Engineering | 3 Engineering Mode | Not Started | P1
R-578 | Import an existing local project (agentic mode, not IR mode) | Platform_Completion queue | Engineering | 3 Engineering Mode | Not Started | P1
PC-024 | Diff review per change, with change impact / blast radius | Platform_Completion queue | Engineering | 3 Engineering Mode | Not Started | P1
PC-026 | Open GitHub pull requests (branch per change, PR naming) | Platform_Completion queue | Engineering | 3 Engineering Mode | Not Started | P1
R-581 | Memory across sessions: semantic project memory on pgvector | Platform_Completion queue | Both | 3 Engineering Mode | Not Started | P1
PC-027 | Version timeline and safe, non-destructive rollback | Platform_Completion queue | Both | 3 Engineering Mode | Not Started | P1
PC-051 | Graduation bridge: open a Vibe project in Engineering Mode with nothing lost, and back | Platform_Completion queue | Both | 3 Engineering Mode | Not Started | P1 |  |  | Projects already keep ir.json, so the IR carries over; custom UI and history must too - model-written pages (PC-098) are kept as the project's own code, never regenerated. From the architecture plan.
PC-028 | Cloud deploy adapters beyond Vercel/Netlify: containers, Kubernetes (Helm), Terraform | Platform_Completion queue | Engineering | 3 Engineering Mode | Not Started | P2 |  |  | From specs/deploy-adapters/01 and the architecture plan.
PC-030 | Tool registry and MCP gateway with a tool secret broker | Platform_Completion queue | Engineering | 3 Engineering Mode | Not Started | P2
PC-031 | Backup, restore drills and disaster recovery | Platform_Completion queue | Platform | 4 Production ops | Not Started | P1
PC-032 | Security audits: independent pen test, DAST, prompt-injection and MCP isolation tests | Platform_Completion queue | Platform | 4 Production ops | Not Started | P1
PC-033 | Observability: platform logs, metrics, task trace, SLOs, incident process | Platform_Completion queue | Platform | 4 Production ops | Not Started | P1
PC-034 | Load and capacity tests | Platform_Completion queue | Platform | 4 Production ops | Not Started | P1
PC-035 | Compliance: SOC 2 readiness, SBOM + licence gate, OSS licence review | Platform_Completion queue | Platform | 4 Production ops | Not Started | P2
PC-037 | Release quality: qualification suite, API contract tests, visual regression, performance budgets | Platform_Completion queue | Platform | 4 Production ops | Not Started | P2
PC-038 | Reliability of runs: crash-resume, no duplicate side effects, stream replay | Platform_Completion queue | Platform | 4 Production ops | Not Started | P2
PC-039 | Unit economics dashboard | Platform_Completion queue | Platform | 4 Production ops | Not Started | P2
PC-040 | Environments per project (dev / preview / prod) | Platform_Completion queue | Both | 4 Production ops | Not Started | P2
PC-065 | Hosted Android emulators for every user: Linux + KVM pool, per-session isolation, browser streaming, metering | Platform_Completion queue | Both | 4 Production ops | Not Started | P2 |  |  | See NATIVE_MOBILE_PREVIEW_PLAN.md. Built and proven on a local Linux VM; the server account is plugged in at PC-070.
PC-067 | Production readiness sign-off: every blocking gate PG-01..PG-21 has evidence | Platform_Completion queue | Platform | 4 Production ops | Not Started | P1 |  |  | The tracker's Production_Gates sheet. The platform is not called production-ready before this.
PC-041 | HA control plane and canary platform releases | Platform_Completion queue | Platform | 4 Production ops | Not Started | P2
PC-042 | Native go-ahead gate: founder approval, toolchains, Apple and Google accounts | Platform_Completion queue | Both | 5 Native mobile (last) | Not Started | P2 |  |  | Standing rule: stop and ask before native mobile work.
R-575 | Native Android: Kotlin + Jetpack Compose, best in class | Platform_Completion queue | Both | 5 Native mobile (last) | Not Started | P2
R-576 | Native iOS: Swift + SwiftUI, best in class | Platform_Completion queue | Both | 5 Native mobile (last) | Not Started | P2
PC-043 | Native recommendation: when to offer native instead of PWA | Platform_Completion queue | Both | 5 Native mobile (last) | Not Started | P2
PC-044 | Signed native builds (AAB/IPA), signing-key hardening, and store submission through the R-574 pipeline | Platform_Completion queue | Both | 5 Native mobile (last) | Not Started | P2
PC-082 | Native implementations of every mobile & device pack and every vertical pack's app screens in Kotlin/Compose and Swift/SwiftUI | Platform_Completion queue | Both | 5 Native mobile (last) | Not Started | P2 |  |  | PRD §5.1: packs are stack-aware; React Native implementations come first with the pack itself.
PC-045 | Native modules and PWA-to-native migration | Platform_Completion queue | Both | 5 Native mobile (last) | Not Started | P3
PC-066 | Hosted iOS simulators on Mac hosts (on demand, metered) | Platform_Completion queue | Both | 5 Native mobile (last) | Not Started | P3 |  |  | Apple allows macOS only on Apple hardware, so this needs Mac servers. See NATIVE_MOBILE_PREVIEW_PLAN.md.
PC-046 | Local Mac agent for iOS builds and simulators | Platform_Completion queue | Engineering | 5 Native mobile (last) | Not Started | P3
PC-070 | Credentials handover: founder supplies cloud, database, payment, email, Apple and Google accounts and keys; each is plugged in without code changes | Platform_Completion queue | Platform | 6 Go-live (credentials last) | Not Started | P0 |  |  | Everything before this is built so that only keys and secrets are missing. Keys go into the secrets store (R-503) or .env, never into code, prompts or logs. D-2, D-3, D-6, D-7.
PC-071 | Live proof of every 'Completed - needs live proof' item with the real accounts | Platform_Completion queue | Platform | 6 Go-live (credentials last) | Not Started | P0 |  |  | Publish to a real URL, a real payment, a real email, EAS/store uploads to both stores.
PC-015 | Private beta with real users: product KPIs, minimal support tooling, feedback | Platform_Completion queue | Platform | 6 Go-live (credentials last) | Not Started | P0 |  |  | The platform is not 'live' until strangers use it.
PC-083 | Head-to-head benchmark: the same 20 prompts on OmniStackAI, Lovable, Bolt, v0, Emergent and Replit; score UI quality, working features, build success and time | Platform_Completion queue | Both | 7 Win the category | Not Started | P1 |  |  | Without measurement 'best' is an opinion. Re-run every quarter (PC-087).
PC-089 | Win on UI polish and speed against Lovable, Bolt and v0: iterate on the benchmark until we lead it | Platform_Completion queue | Vibe | 7 Win the category | Not Started | P1 |  |  | Their whole focus, improved weekly; matching needs features, beating needs measurement.
PC-090 | Engineering Mode positioning and proof: 'designs and builds structured multi-app platforms with verification', benchmarked against Cursor, Claude Code, Codex and Devin on platform-building tasks | Platform_Completion queue | Engineering | 7 Win the category | Not Started | P1 |  |  | We do not try to be a better general code editor; we win where they do not compete: whole platforms from a plan, verified.
PC-091 | Native lead: match or beat the native Swift/Kotlin builders on quality and speed | Platform_Completion queue | Both | 7 Win the category | Not Started | P2 |  |  | Some builders already generate native apps; ours arrives in Phase 5.
PC-086 | Public launch: docs site, tutorials and videos, pricing page, community, launch campaign | Platform_Completion queue | Platform | 7 Win the category | Not Started | P1 |  |  | The plan otherwise stops at a private beta.
PC-092 | Users and brand: growth loops (referrals, template showcase, made-with gallery), partnerships, content, measured activation and retention | Platform_Completion queue | Platform | 7 Win the category | Not Started | P1 |  |  | Competitors already have millions of users.
PC-087 | Quarterly competitor review: re-run the benchmark, update the plan and this queue | Platform_Completion queue | Platform | 7 Win the category | Not Started | P2 |  |  | Recurring; competitors ship weekly.
ARCH-ALLOWLIST | Expanded LLM UI import allowlist | docs/ARCHITECTURE_MASTER_PLAN.md §4.4 |  | Delivered | Not Started | P1 | PC-050
ARCH-COMPONENT-BROWSER | Component library browser | docs/ARCHITECTURE_MASTER_PLAN.md §7.3 |  | 2 Maximum features | Not Started | P3 | PC-020
ARCH-DB-OPTIONS | Database choice per project (the plan lists PG/MySQL/SQLite) | docs/ARCHITECTURE_MASTER_PLAN.md §7.2 |  | 2 Maximum features | Not Started | P2 | PC-048 |  | MongoDB first (D-8); others if they prove best.
ARCH-ENG-OPTIONS | Engineering options: IR editor, dependency graph, pack selector, per-app framework, CI/CD editor | docs/ARCHITECTURE_MASTER_PLAN.md §7.2 |  | 3 Engineering Mode | Not Started | P1 | PC-022 |  | Flutter in that list is dropped by the stack policy.
ARCH-FILES | File upload pipeline: S3 direct, processing, PDF generation | docs/ARCHITECTURE_MASTER_PLAN.md §10 Phase 3 |  | 2 Maximum features | Not Started | P1 | PC-052
ARCH-FLAGS | A/B testing and feature-flag runtime | docs/ARCHITECTURE_MASTER_PLAN.md §10 Phase 4 |  | 2 Maximum features | Not Started | P3 | PC-056
ARCH-FORMS | Form/wizard engine | docs/ARCHITECTURE_MASTER_PLAN.md §5.3 |  | 2 Maximum features | Not Started | P2 | PC-059
ARCH-GRADUATION | Graduation bridge Vibe <-> Engineering | docs/ARCHITECTURE_MASTER_PLAN.md §6 |  | 3 Engineering Mode | Not Started | P1 | PC-051
ARCH-I18N | i18n framework | docs/ARCHITECTURE_MASTER_PLAN.md §10 Phase 4 |  | 2 Maximum features | Not Started | P2 | PC-055
ARCH-IMPORT-MODES | Import modes: analyse only, add feature as PR, modernise UI, add mobile, full migration | docs/ARCHITECTURE_MASTER_PLAN.md §8.3 |  | 3 Engineering Mode | Not Started | P1 | R-578
ARCH-IMPORT-SOURCES | Import from GitHub/GitLab/Bitbucket, local folder, Vercel/Netlify, Supabase | docs/ARCHITECTURE_MASTER_PLAN.md §8.1 |  | 3 Engineering Mode | Not Started | P1 | R-579
ARCH-K8S | Kubernetes (Helm/Kustomize) and Terraform deploy generator | docs/ARCHITECTURE_MASTER_PLAN.md §10 Phase 3 |  | 3 Engineering Mode | Not Started | P2 | PC-028
ARCH-NATIVE | True native mobile (Kotlin/Compose + Swift/SwiftUI) | docs/ARCHITECTURE_MASTER_PLAN.md §10 Phase 3 |  | 5 Native mobile (last) | Not Started | P2 | R-575 |  | Also R-576.
ARCH-NOTIFY | Notification system: multi-channel, templates, preferences | docs/ARCHITECTURE_MASTER_PLAN.md §10 Phase 3 |  | 2 Maximum features | Not Started | P1 | PC-053
ARCH-OBSERVABILITY | Advanced observability for generated apps (tracing, dashboards) | docs/ARCHITECTURE_MASTER_PLAN.md §10 Phase 4 |  | 2 Maximum features | Not Started | P2 | PC-057
ARCH-PACKS | Pack manifest v2, composition engine, ~30 horizontal and ~80 vertical packs | docs/ARCHITECTURE_MASTER_PLAN.md §4.2, §5.1, §10 |  | 2 Maximum features | Not Started | P1 | PC-073
ARCH-PAYMENTS | Payment flow generator: Stripe Connect, webhooks, subscriptions | docs/ARCHITECTURE_MASTER_PLAN.md §10 Phase 3 |  | 2 Maximum features | Not Started | P1 | R-567
ARCH-PERF | Performance: bundle analysis, lazy loading, edge caching | docs/ARCHITECTURE_MASTER_PLAN.md §10 Phase 4 |  | 4 Production ops | Not Started | P2 | PC-037
ARCH-REALTIME | Realtime adapter: hooks, presence, optimistic UI | docs/ARCHITECTURE_MASTER_PLAN.md §5.3 |  | 2 Maximum features | Not Started | P1 | R-569
ARCH-SEARCH | Search/filter engine (Meilisearch) | docs/ARCHITECTURE_MASTER_PLAN.md §10 Phase 2 |  | 2 Maximum features | Not Started | P3 | PC-058
ARCH-STUDIO-MODES | Mode-aware Studio: Vibe shows only what matters, Engineering shows everything | docs/ARCHITECTURE_MASTER_PLAN.md §7 |  | Delivered | Not Started | P0 | PC-005
ARCH-SUPABASE | Real managed database for Vibe apps (Supabase in the plan; any managed PostgreSQL here) | docs/ARCHITECTURE_MASTER_PLAN.md §4.3 |  | 1 Vibe Mode live | Not Started | P0 | PC-049 |  | The plan's Supabase Auth/Storage are replaced by the generated backend's own auth and PC-052.
ARCH-TEMPLATES-UX | Template marketplace UX | docs/ARCHITECTURE_MASTER_PLAN.md §10 Phase 4 |  | 2 Maximum features | Not Started | P2 | PC-018
ARCH-TESTS | Generated tests with over 80% coverage | docs/ARCHITECTURE_MASTER_PLAN.md §12 |  | 2 Maximum features | Not Started | P1 | PC-054
ARCH-VERTICALS | Vertical packs for 10 domains (healthcare, mobility, commerce, fintech, food, real estate, education, SaaS, logistics, services) | docs/ARCHITECTURE_MASTER_PLAN.md §5.1 |  | 2 Maximum features | Not Started | P2 | PC-074
ARCH-WEBCONTAINER | WebContainer instant preview with a local Docker fallback | docs/ARCHITECTURE_MASTER_PLAN.md §4.1, §11 |  | Delivered | Not Started | P0 | PC-007
BP-CLICKEDIT | Visual click-to-edit mode | Platform_Buildout section 8 ('R-520') |  | 2 Maximum features | Not Started | P2 | PC-019
BP-COMMENTS | Preview-pinned comments and @Omni threads | Platform_Buildout section 8 ('R-528') |  | 3 Engineering Mode | Not Started | P2 | PC-029
BP-FIGMA | Screenshot and Figma to app | Platform_Buildout section 8 ('R-527') |  | 2 Maximum features | Not Started | P3 | PC-021
BP-INTENT | Simple vs Pro mode and 'What I understood' intent cards | Platform_Buildout section 8 ('R-519') |  | Delivered | Not Started | P0 | PC-005 |  | The buildout plan's R-518..R-529 numbers were reused for other tasks.
BP-SHIPCHECK | Pre-deployment 'safe to ship' health check | Platform_Buildout section 8 ('R-525') |  | Delivered | Not Started | P1 | PC-008
BP-TIMELINE | Version timeline and safe semantic undo | Platform_Buildout section 8 ('R-524') |  | 3 Engineering Mode | Not Started | P1 | PC-027
BP-TURBO | Instant preview preservation and fast-path edits | Platform_Buildout section 8 ('R-522') |  | Delivered | Not Started | P0 | PC-007
GA-08 | Expand/migrate/contract database releases | Tracker RND_Gap_Audit |  | 4 Production ops | Not Started | P1 | PC-036
GA-09 | Agentic threat model and red-team corpus | Tracker RND_Gap_Audit |  | 4 Production ops | Not Started | P1 | PC-032
GA-10 | Extended production evidence set | Tracker RND_Gap_Audit |  | 4 Production ops | Not Started | P1 | PC-067
GA-12 | Feature flags with owner/expiry, canary/blue-green | Tracker RND_Gap_Audit |  | 4 Production ops | Not Started | P2 | PC-041
GAP-EVALS | Model eval and benchmark suite for ai/evals | V6_Review_and_Gap_Analysis section 3 |  | 1 Vibe Mode live | Not Started | P2 | PC-014 |  | Needed to recommend a local model honestly.
GAP-LEGAL | Legal layer: ToS, DPA, code-handling agreement | V6_Review_and_Gap_Analysis section 3 |  | Delivered | Not Started | P0 | PC-012
HP-ai-assistant | Horizontal pack ai-assistant: In-app AI: chat assistant, summarise, extract, generate, over the app's own data | new | Integration & AI | 2 Maximum features | Not Started | P1 | PC-073 |  | Uses the platform's model gateway pattern; keys at PC-070.
HP-api-gateway | Horizontal pack api-gateway: Rate limits, API keys, transformations | registry | Integration & AI | 2 Maximum features | Not Started | P3 | PC-079
HP-approvals | Horizontal pack approvals: Multi-step approval chains, escalation, delegation | registry | Business logic & workflow | 2 Maximum features | Not Started | P2 | PC-078
HP-audit-log | Horizontal pack audit-log: Append-only, tamper-evident audit log with query API | registry | Security & compliance | 2 Maximum features | Not Started | P2 | PC-078 |  | PC-057.
HP-audit-trail | Horizontal pack audit-trail: Entity history, diffs, point-in-time queries | registry | Business logic & workflow | 2 Maximum features | Not Started | P2 | PC-078
HP-background-tasks | Horizontal pack background-tasks: Background fetch, scheduled local work | new | Mobile & device (stack-aware: React Native, Kotlin, Swift) | 2 Maximum features | Not Started | P2 | PC-078
HP-backups-restore | Horizontal pack backups-restore: Point-in-time backups and self-service restore for generated apps | new | Data & storage | 2 Maximum features | Not Started | P3 | PC-079
HP-billing-metering | Horizontal pack billing-metering: Usage metering, rating, invoicing, dunning | registry | Business logic & workflow | 2 Maximum features | Not Started | P2 | PC-078
HP-biometrics | Horizontal pack biometrics: Face ID / Touch ID / BiometricPrompt, passkeys | PRD | Mobile & device (stack-aware: React Native, Kotlin, Swift) | 2 Maximum features | Not Started | P2 | PC-078
HP-bluetooth-nfc | Horizontal pack bluetooth-nfc: Bluetooth LE and NFC | new | Mobile & device (stack-aware: React Native, Kotlin, Swift) | 2 Maximum features | Not Started | P3 | PC-079
HP-cache-layer | Horizontal pack cache-layer: Redis/Valkey caching, invalidation, locks | spec, registry | Data & storage | 2 Maximum features | Not Started | P3 | PC-079
HP-calendar-sync | Horizontal pack calendar-sync: Google/Outlook/iCal sync | new (registry dependency 'calendar') | Business logic & workflow | 2 Maximum features | Not Started | P2 | PC-078
HP-cms-marketing-site | Horizontal pack cms-marketing-site: Landing pages, blog, CMS for non-developers | new | UI & experience | 2 Maximum features | Not Started | P2 | PC-078
HP-compliance-gdpr | Horizontal pack compliance-gdpr: Data export, deletion, consent, retention | registry | Security & compliance | 2 Maximum features | Not Started | P2 | PC-078 |  | PC-012.
HP-compliance-hipaa | Horizontal pack compliance-hipaa: PHI masking, access audit, breach notification | registry | Security & compliance | 2 Maximum features | Not Started | P2 | PC-078
HP-compliance-soc2 | Horizontal pack compliance-soc2: Control mapping, evidence collection, access reviews | registry | Security & compliance | 2 Maximum features | Not Started | P3 | PC-079
HP-coupons-promotions | Horizontal pack coupons-promotions: Coupons, discounts, promotions, gift cards | new | Commerce & payments | 2 Maximum features | Not Started | P2 | PC-078
HP-crash-reporting | Horizontal pack crash-reporting: Crash and ANR reporting with symbolication | new | Mobile & device (stack-aware: React Native, Kotlin, Swift) | 2 Maximum features | Not Started | P2 | PC-078
HP-crm | Horizontal pack crm: Contacts, companies, leads, pipeline, activities | new (registry dependency) | Business logic & workflow | 2 Maximum features | Not Started | P2 | PC-078
HP-data-archival | Horizontal pack data-archival: Tiered storage, retention, legal hold | registry | Data & storage | 2 Maximum features | Not Started | P3 | PC-079
HP-database-mongo | Horizontal pack database-mongo: MongoDB collections, schema validation, indexes, seeds | new | Core platform | 2 Maximum features | Not Started | P2 | PC-078 |  | Founder decision D-8; built by PC-048.
HP-deep-links | Horizontal pack deep-links: Universal/app links, share links into screens | new | Mobile & device (stack-aware: React Native, Kotlin, Swift) | 2 Maximum features | Not Started | P1 | PC-073
HP-developer-portal | Horizontal pack developer-portal: API keys, docs, usage for third-party developers | new (registry dependency) | Integration & AI | 2 Maximum features | Not Started | P3 | PC-079
HP-encryption | Horizontal pack encryption: Field-level encryption, key rotation, KMS | registry | Security & compliance | 2 Maximum features | Not Started | P2 | PC-078
HP-feature-flags | Horizontal pack feature-flags: Flags, rollouts, experiments, kill switches | spec, registry | Business logic & workflow | 2 Maximum features | Not Started | P3 | PC-079 |  | PC-056.
HP-files-storage | Horizontal pack files-storage: S3-compatible uploads, presigned URLs, image transforms, CDN | spec, registry | Data & storage | 2 Maximum features | Not Started | P1 | PC-073 |  | PC-052.
HP-forecasting | Horizontal pack forecasting: Demand and cash forecasts from history | new (registry dependency) | Business logic & workflow | 2 Maximum features | Not Started | P3 | PC-079
HP-forms-engine | Horizontal pack forms-engine: Multi-step wizards, conditional fields, drafts | registry | UI & experience | 2 Maximum features | Not Started | P2 | PC-078 |  | PC-059.
HP-fraud-risk | Horizontal pack fraud-risk: Risk scoring, velocity rules, device fingerprints, blocklists | new | Security & compliance | 2 Maximum features | Not Started | P3 | PC-079
HP-gamification | Horizontal pack gamification: Points, badges, levels, leaderboards, streaks | new (registry dependency) | Business logic & workflow | 2 Maximum features | Not Started | P3 | PC-079
HP-geolocation | Horizontal pack geolocation: Foreground/background location, live tracking | PRD | Mobile & device (stack-aware: React Native, Kotlin, Swift) | 2 Maximum features | Not Started | P1 | PC-073 |  | Needs R-569.
HP-git-ops | Horizontal pack git-ops: Conventional commits, changelog, releases | registry | Core platform | 2 Maximum features | Not Started | P3 | PC-079
HP-health-fitness-data | Horizontal pack health-fitness-data: HealthKit and Health Connect | new | Mobile & device (stack-aware: React Native, Kotlin, Swift) | 2 Maximum features | Not Started | P3 | PC-079
HP-identity-verification | Horizontal pack identity-verification: KYC/KYB, document and selfie checks, verification status | new (registry dependency 'verification') | Security & compliance | 2 Maximum features | Not Started | P2 | PC-078
HP-in-app-purchases | Horizontal pack in-app-purchases: Apple and Google in-app purchases and subscriptions | new | Mobile & device (stack-aware: React Native, Kotlin, Swift) | 2 Maximum features | Not Started | P1 | PC-073 |  | Required by store rules for digital goods; keys at PC-070.
HP-invoicing | Horizontal pack invoicing: Invoices, PDFs, recurring invoices, reminders | registry | Commerce & payments | 2 Maximum features | Not Started | P2 | PC-078
HP-iot-telematics | Horizontal pack iot-telematics: Device registry, telemetry ingestion, alerts | new (registry dependencies 'iot', 'telematics') | Integration & AI | 2 Maximum features | Not Started | P3 | PC-079
HP-localization | Horizontal pack localization: i18n, RTL, currency and date formatting | spec | UI & experience | 2 Maximum features | Not Started | P2 | PC-078 |  | PC-055.
HP-marketplace-payments | Horizontal pack marketplace-payments: Split payments, escrow, payouts, seller onboarding | spec ('marketplace-core'), registry | Commerce & payments | 2 Maximum features | Not Started | P2 | PC-078 |  | R-567; Bazaar shows the shape.
HP-mcp-gateway | Horizontal pack mcp-gateway: MCP server exposing the app's tools to AI agents | registry | Integration & AI | 2 Maximum features | Not Started | P3 | PC-079
HP-ml-inference | Horizontal pack ml-inference: Model inference endpoints for scoring and classification | new (registry dependency) | Integration & AI | 2 Maximum features | Not Started | P3 | PC-079
HP-mobile-push | Horizontal pack mobile-push: Push notifications (Expo, FCM, APNs), deep-link on tap | PRD | Mobile & device (stack-aware: React Native, Kotlin, Swift) | 2 Maximum features | Not Started | P1 | PC-073 |  | PC-053.
HP-moderation | Horizontal pack moderation: Content moderation (AI + human queue), reports, bans | new (registry dependency) | Security & compliance | 2 Maximum features | Not Started | P2 | PC-078
HP-multi-tenancy | Horizontal pack multi-tenancy: Tenant isolation, per-tenant data, tenant switching | new (registry dependency) | Core platform | 2 Maximum features | Not Started | P1 | PC-073
HP-observability | Horizontal pack observability: Logs, metrics, traces, error tracking, alerting | spec, registry | Core platform | 2 Maximum features | Not Started | P2 | PC-078 |  | PC-057.
HP-offline-sync | Horizontal pack offline-sync: Offline-first storage, sync queue, conflict resolution | new | Mobile & device (stack-aware: React Native, Kotlin, Swift) | 2 Maximum features | Not Started | P1 | PC-073
HP-onboarding-invitations | Horizontal pack onboarding-invitations: Sign-up flows, invitations, first-run checklists | new (registry dependency) | Core platform | 2 Maximum features | Not Started | P2 | PC-078
HP-ota-updates | Horizontal pack ota-updates: Over-the-air updates and in-app update prompts | new | Mobile & device (stack-aware: React Native, Kotlin, Swift) | 2 Maximum features | Not Started | P2 | PC-078
HP-performance | Horizontal pack performance: Bundle analysis, Core Web Vitals, Lighthouse CI | spec | UI & experience | 2 Maximum features | Not Started | P2 | PC-078 |  | PC-037.
HP-plugin-system | Horizontal pack plugin-system: Sandboxed plugins and extension marketplace | registry | Integration & AI | 2 Maximum features | Not Started | P3 | PC-079
HP-pricing-engine | Horizontal pack pricing-engine: Price rules, tiers, dynamic pricing, quotes | new (registry dependencies 'pricing', 'rate-engine') | Business logic & workflow | 2 Maximum features | Not Started | P2 | PC-078
HP-queue-jobs | Horizontal pack queue-jobs: Background jobs, retries, schedules, dead letter | spec, registry | Data & storage | 2 Maximum features | Not Started | P1 | PC-073 |  | R-568.
HP-rbac-advanced | Horizontal pack rbac-advanced: Ownership rules, row-level and field-level permissions, org hierarchies, impersonation | spec | Security & compliance | 2 Maximum features | Not Started | P1 | PC-073 |  | R-570.
HP-realtime-core | Horizontal pack realtime-core: Live updates, presence, broadcast | spec, registry | Realtime & communication | 2 Maximum features | Not Started | P1 | PC-073 |  | R-569.
HP-referrals-affiliates | Horizontal pack referrals-affiliates: Referral codes, tracking, rewards | spec | Business logic & workflow | 2 Maximum features | Not Started | P3 | PC-079
HP-reporting | Horizontal pack reporting: Scheduled reports, report builder, PDF/Excel delivery | new (registry dependency) | Data & storage | 2 Maximum features | Not Started | P2 | PC-078
HP-rules-engine | Horizontal pack rules-engine: Business rules on create/update/transition | new (architecture plan) | Business logic & workflow | 2 Maximum features | Not Started | P1 | PC-073 |  | R-571.
HP-secure-storage | Horizontal pack secure-storage: Keychain/Keystore-backed storage for tokens and secrets | PRD | Mobile & device (stack-aware: React Native, Kotlin, Swift) | 2 Maximum features | Not Started | P1 | PC-073
HP-security-headers | Horizontal pack security-headers: CSP, HSTS, permissions policy, nonces | registry | Security & compliance | 2 Maximum features | Not Started | P2 | PC-078
HP-share-contacts | Horizontal pack share-contacts: Share sheet, contacts picker, calendar events | new (registry dependency 'sharing') | Mobile & device (stack-aware: React Native, Kotlin, Swift) | 2 Maximum features | Not Started | P3 | PC-079
HP-storybook | Horizontal pack storybook: Component docs and visual playground | spec | UI & experience | 2 Maximum features | Not Started | P3 | PC-079
HP-subscriptions | Horizontal pack subscriptions: Plans, trials, proration, pausing, dunning | spec, registry | Commerce & payments | 2 Maximum features | Not Started | P2 | PC-078 |  | R-567.
HP-support-helpdesk | Horizontal pack support-helpdesk: Tickets, knowledge base, live-chat widget, SLAs | new | Realtime & communication | 2 Maximum features | Not Started | P2 | PC-078
HP-tax-compliance | Horizontal pack tax-compliance: VAT/GST/sales tax calculation and validation | registry | Commerce & payments | 2 Maximum features | Not Started | P3 | PC-079
HP-testing | Horizontal pack testing: Generated unit, contract and end-to-end tests | spec | Quality | 2 Maximum features | Not Started | P1 | PC-073 |  | PC-054.
HP-vector-search | Horizontal pack vector-search: Embeddings and semantic search on pgvector | new | Data & storage | 2 Maximum features | Not Started | P2 | PC-078
HP-video-calling | Horizontal pack video-calling: WebRTC calls, screen share, recording, transcripts | registry | Realtime & communication | 2 Maximum features | Not Started | P2 | PC-078
HP-wallet-ledger | Horizontal pack wallet-ledger: Double-entry ledger, accounts, transfers, reconciliation | registry, PRD | Commerce & payments | 2 Maximum features | Not Started | P1 | PC-073 |  | R-567.
MULTI-TENANT | Per-user backend multi-tenancy of the Studio server | Commercial_Platform_Kickoff section 3 |  | Delivered | Not Started | P0 | PC-009 |  | 'A single trusted operator's tool that looks like a SaaS.'
PG-01 | All P0 MVP architecture requirements complete | Tracker Production_Gates |  | 4 Production ops | Not Started | P1 | PC-067
PG-02 | Critical flows have automated E2E and regression tests | Tracker Production_Gates |  | 4 Production ops | Not Started | P1 | PC-037
PG-03 | Release qualification suite passes across supported target versions | Tracker Production_Gates |  | 4 Production ops | Not Started | P2 | PC-037
PG-04 | No unresolved critical/high security findings | Tracker Production_Gates |  | 4 Production ops | Not Started | P1 | PC-032
PG-05 | Tenant isolation test suite passes | Tracker Production_Gates |  | Delivered | Not Started | P0 | PC-009
PG-06 | External penetration test completed, critical items fixed | Tracker Production_Gates |  | 4 Production ops | Not Started | P1 | PC-032
PG-07 | On-call, incident runbooks, status page, postmortems | Tracker Production_Gates |  | 4 Production ops | Not Started | P2 | PC-033
PG-08 | Backup restore drill completed | Tracker Production_Gates |  | 4 Production ops | Not Started | P1 | PC-031
PG-09 | Load test meets target concurrent builds/previews | Tracker Production_Gates |  | 4 Production ops | Not Started | P1 | PC-034
PG-10 | SLOs and alerting live | Tracker Production_Gates |  | 4 Production ops | Not Started | P1 | PC-033
PG-11 | Canary/rollback platform release process proven | Tracker Production_Gates |  | 4 Production ops | Not Started | P2 | PC-041
PG-12 | Usage ledger reconciles with provider invoices | Tracker Production_Gates |  | 4 Production ops | Not Started | P2 | PC-039
PG-13 | Spending caps and anomaly kill switches tested | Tracker Production_Gates |  | Delivered | Not Started | P0 | PC-010
PG-14 | Deletion/export/retention workflows tested | Tracker Production_Gates |  | Delivered | Not Started | P0 | PC-012
PG-15 | Redacted diagnostic bundle and support workflow | Tracker Production_Gates |  | 6 Go-live (credentials last) | Not Started | P1 | PC-015
PG-16 | Plan entitlements and quota enforcement tested | Tracker Production_Gates |  | Delivered | Not Started | P0 | PC-011
PG-18 | Local/cloud model providers pass conformance and quality evals | Tracker Production_Gates |  | 1 Vibe Mode live | Not Started | P1 | PC-014
PG-20 | Expand/migrate/contract migration and rollback rehearsal | Tracker Production_Gates |  | 4 Production ops | Not Started | P1 | PC-036
PG-21 | Prompt/tool poisoning, secret exfiltration, replay tests | Tracker Production_Gates |  | 4 Production ops | Not Started | P1 | PC-032
PHASE-E | Plan-gated features, credit top-up, super_admin console | Commercial_Platform_Kickoff section 3 |  | Delivered | Not Started | P0 | PC-011
R-016 | Change Impact Engine v1 | Execution_Tracker_v6 | Change Safety | 3 Engineering Mode | Not Started | P1 | PC-024
R-017 | Blast-radius policy | Execution_Tracker_v6 | Change Safety | 3 Engineering Mode | Not Started | P1 | PC-024
R-018 | Repository index | Execution_Tracker_v6 | Code Intelligence | 3 Engineering Mode | Not Started | P1 | R-578
R-019 | Semantic context retrieval | Execution_Tracker_v6 | Code Intelligence | 3 Engineering Mode | Not Started | P1 | R-581
R-021 | Branch per task | Execution_Tracker_v6 | Git | 3 Engineering Mode | Not Started | P1 | PC-026
R-022 | Non-destructive rollback | Execution_Tracker_v6 | Git | 3 Engineering Mode | Not Started | P1 | PC-027
R-025 | Per-task budgets | Execution_Tracker_v6 | Models | Delivered | Not Started | P0 | PC-010 |  | Usage and cost are recorded; no per-task budget.
R-035 | Android build verification | Execution_Tracker_v6 | Android | 5 Native mobile (last) | Not Started | P2 | R-575
R-036 | Cloud macOS compile verification | Execution_Tracker_v6 | iOS | 5 Native mobile (last) | Not Started | P2 | R-576
R-039 | API contract tests | Execution_Tracker_v6 | Testing | 4 Production ops | Not Started | P2 | PC-037 |  | OpenAPI exists (R-260); no contract tests.
R-042 | Prompt/tool policy | Execution_Tracker_v6 | Security | 3 Engineering Mode | Not Started | P1 | R-577
R-043 | Task trace | Execution_Tracker_v6 | Observability | 4 Production ops | Not Started | P2 | PC-033
R-044 | Platform logs/metrics | Execution_Tracker_v6 | Observability | 4 Production ops | Not Started | P1 | PC-033
R-046 | Pre-task estimate | Execution_Tracker_v6 | Billing | Delivered | Not Started | P0 | PC-010
R-047 | No charge for internal failed retries | Execution_Tracker_v6 | Billing | Delivered | Not Started | P0 | PC-010
R-049 | Android APK/AAB build | Execution_Tracker_v6 | Deployment | 5 Native mobile (last) | Not Started | P2 | PC-044
R-050 | iOS IPA build pipeline | Execution_Tracker_v6 | Deployment | 5 Native mobile (last) | Not Started | P2 | PC-044
R-051 | Core product KPIs | Execution_Tracker_v6 | Analytics | 6 Go-live (credentials last) | Not Started | P0 | PC-015
R-052 | Interactive Android emulator streaming | Execution_Tracker_v6 | Preview | 1 Vibe Mode live | Not Started | P1 | PC-063 |  | Android emulator streaming (founder asked for it).
R-053 | Interactive iOS simulator streaming | Execution_Tracker_v6 | Preview | 2 Maximum features | Not Started | P2 | PC-064 |  | iOS Simulator streaming.
R-054 | Local Mac Agent | Execution_Tracker_v6 | iOS | 5 Native mobile (last) | Not Started | P3 | PC-046
R-056 | Integration health tests | Execution_Tracker_v6 | Integrations | Delivered | Not Started | P1 | PC-013
R-057 | Long-project memory compaction | Execution_Tracker_v6 | Context | 3 Engineering Mode | Not Started | P1 | R-581
R-059 | Visual regression | Execution_Tracker_v6 | Quality | 4 Production ops | Not Started | P2 | PC-037
R-060 | Performance budgets | Execution_Tracker_v6 | Quality | 4 Production ops | Not Started | P2 | PC-037
R-065 | Comments/review workflow | Execution_Tracker_v6 | Collaboration | 3 Engineering Mode | Not Started | P2 | PC-029
R-069 | DAST | Execution_Tracker_v6 | Security | 4 Production ops | Not Started | P1 | PC-032
R-070 | SBOM + license policy | Execution_Tracker_v6 | Security | 4 Production ops | Not Started | P2 | PC-035
R-071 | Egress policy | Execution_Tracker_v6 | Security | Delivered | Not Started | P0 | PC-009
R-075 | Database profiles | Execution_Tracker_v6 | Data | 2 Maximum features | Not Started | P2 | PC-048 |  | MongoDB as an option (D-8).
R-076 | Existing repo import | Execution_Tracker_v6 | Developer UX | 3 Engineering Mode | Not Started | P1 | R-578
R-094 | SLO/SLA framework | Execution_Tracker_v6 | Reliability | 4 Production ops | Not Started | P1 | PC-033
R-095 | HA control plane | Execution_Tracker_v6 | Reliability | 4 Production ops | Not Started | P2 | PC-041
R-096 | Backup + restore drills | Execution_Tracker_v6 | Reliability | 4 Production ops | Not Started | P1 | PC-031
R-097 | Disaster recovery | Execution_Tracker_v6 | Reliability | 4 Production ops | Not Started | P1 | PC-031
R-098 | Independent penetration test | Execution_Tracker_v6 | Security | 4 Production ops | Not Started | P1 | PC-032
R-099 | SOC 2 readiness controls | Execution_Tracker_v6 | Security | 4 Production ops | Not Started | P2 | PC-035
R-100 | Tenant isolation validation | Execution_Tracker_v6 | Security | Delivered | Not Started | P0 | PC-009
R-101 | Signing-key hardening | Execution_Tracker_v6 | Security | 5 Native mobile (last) | Not Started | P2 | PC-044
R-102 | 24x7 incident process | Execution_Tracker_v6 | Operations | 4 Production ops | Not Started | P2 | PC-033
R-103 | Capacity/load tests | Execution_Tracker_v6 | Operations | 4 Production ops | Not Started | P1 | PC-034
R-104 | Cost guardrails | Execution_Tracker_v6 | Operations | Delivered | Not Started | P0 | PC-010
R-105 | Release qualification suite | Execution_Tracker_v6 | Quality | 4 Production ops | Not Started | P2 | PC-037
R-106 | Canary platform releases | Execution_Tracker_v6 | Quality | 4 Production ops | Not Started | P2 | PC-041
R-107 | Support tooling | Execution_Tracker_v6 | Support | 6 Go-live (credentials last) | Not Started | P0 | PC-015
R-108 | Privacy + retention controls | Execution_Tracker_v6 | Legal/Privacy | Delivered | Not Started | P0 | PC-012
R-109 | Plan entitlements | Execution_Tracker_v6 | Business | Delivered | Not Started | P0 | PC-011
R-110 | Unit economics dashboard | Execution_Tracker_v6 | Business | 4 Production ops | Not Started | P2 | PC-039
R-116 | Shared-code policy | Execution_Tracker_v6 | Architecture | 2 Maximum features | Not Started | P1 | R-572
R-120 | Native recommendation profile | Execution_Tracker_v6 | Framework Strategy | 5 Native mobile (last) | Not Started | P2 | PC-043
R-125 | Branch + PR naming convention | Execution_Tracker_v6 | Git/Repository | 3 Engineering Mode | Not Started | P1 | PC-026
R-127 | Shared contracts package | Execution_Tracker_v6 | Architecture | 2 Maximum features | Not Started | P1 | R-572 |  | packages/contracts is an empty folder.
R-137 | Code sharing policy | Execution_Tracker_v6 | Architecture | 2 Maximum features | Not Started | P1 | R-572
R-143 | React Native shared TS packages | Execution_Tracker_v6 | Templates | 2 Maximum features | Not Started | P1 | R-572
R-144 | Native Android lean template | Execution_Tracker_v6 | Templates | 5 Native mobile (last) | Not Started | P2 | R-575
R-145 | Native Android scaled modules | Execution_Tracker_v6 | Templates | 5 Native mobile (last) | Not Started | P2 | R-575
R-146 | Native iOS lean template | Execution_Tracker_v6 | Templates | 5 Native mobile (last) | Not Started | P2 | R-576
R-147 | Native iOS scaled Swift Packages | Execution_Tracker_v6 | Templates | 5 Native mobile (last) | Not Started | P2 | R-576
R-152 | Generated client matrix | Execution_Tracker_v6 | Contracts | 2 Maximum features | Not Started | P1 | R-572
R-154 | Approved dependency catalog | Execution_Tracker_v6 | Dependencies | 4 Production ops | Not Started | P2 | PC-035
R-161 | Local Mac Agent productized | Execution_Tracker_v6 | Preview | 5 Native mobile (last) | Not Started | P3 | PC-046
R-163 | Native module adapter path | Execution_Tracker_v6 | Framework Strategy | 5 Native mobile (last) | Not Started | P3 | PC-045
R-165 | Cross-platform to native migration engine | Execution_Tracker_v6 | Migration | 5 Native mobile (last) | Not Started | P3 | PC-045
R-174 | Browser runtime PoC | Execution_Tracker_v6 | Runtime | Delivered | Not Started | P0 | PC-007
R-175 | Runtime quotas and metering | Execution_Tracker_v6 | Runtime | Delivered | Not Started | P0 | PC-009
R-176 | Durable run state machine | Execution_Tracker_v6 | Agents | 3 Engineering Mode | Not Started | P1 | R-577
R-177 | Checkpoint and resume | Execution_Tracker_v6 | Agents | 3 Engineering Mode | Not Started | P1 | R-577
R-178 | Tool idempotency keys | Execution_Tracker_v6 | Agents | 3 Engineering Mode | Not Started | P1 | R-577
R-179 | Agent event ledger | Execution_Tracker_v6 | Observability | 3 Engineering Mode | Not Started | P1 | R-577
R-180 | Orchestrator Adapter | Execution_Tracker_v6 | Agents | 3 Engineering Mode | Not Started | P1 | R-577
R-182 | WebSocket reconnect and replay | Execution_Tracker_v6 | Realtime | 4 Production ops | Not Started | P2 | PC-038
R-183 | Risk classification L0-L4 | Execution_Tracker_v6 | Approvals | 3 Engineering Mode | Not Started | P1 | R-577
R-184 | Approval object and immutable audit | Execution_Tracker_v6 | Approvals | 3 Engineering Mode | Not Started | P1 | R-577
R-185 | First-party Tool Registry | Execution_Tracker_v6 | Tools | 3 Engineering Mode | Not Started | P2 | PC-030
R-186 | MCP Gateway foundation | Execution_Tracker_v6 | Tools | 3 Engineering Mode | Not Started | P2 | PC-030
R-187 | Tool secret broker | Execution_Tracker_v6 | Tools | 3 Engineering Mode | Not Started | P2 | PC-030
R-190 | Open-source license review | Execution_Tracker_v6 | Governance | 4 Production ops | Not Started | P2 | PC-035
R-210 | Crash-resume production test | Execution_Tracker_v6 | Reliability | 4 Production ops | Not Started | P2 | PC-038
R-211 | Duplicate side-effect prevention test | Execution_Tracker_v6 | Reliability | 4 Production ops | Not Started | P2 | PC-038
R-212 | WebSocket replay correctness SLO | Execution_Tracker_v6 | Realtime | 4 Production ops | Not Started | P2 | PC-038
R-213 | MCP isolation and prompt-injection test | Execution_Tracker_v6 | Security | 4 Production ops | Not Started | P1 | PC-032
R-214 | Sandbox tenant isolation test | Execution_Tracker_v6 | Security | Delivered | Not Started | P0 | PC-009
R-216 | Approval auditability test | Execution_Tracker_v6 | Governance | 4 Production ops | Not Started | P2 | PC-038
R-219 | OSS license and SBOM gate | Execution_Tracker_v6 | Compliance | 4 Production ops | Not Started | P2 | PC-035
SPEC-DEPLOY-01 | Cloud deploy adapters | specs/deploy-adapters/01 |  | 3 Engineering Mode | Not Started | P2 | PC-028 |  | Draft spec.
SPEC-ENG-01 | Multi-app architect (Engineering Mode core) | specs/engineering-mode/01 |  | 3 Engineering Mode | Not Started | P1 | PC-022 |  | Draft spec.
SPEC-NATIVE-01 | True native mobile (Kotlin/Compose + Swift/SwiftUI) | specs/native-mobile/01 |  | 5 Native mobile (last) | Not Started | P2 | R-575 |  | Draft spec. Covers R-575 and R-576.
SPEC-PACK-02 | Pack composer: merge, wire, validate | specs/pack-framework/02 |  | 2 Maximum features | Not Started | P1 | PC-017 |  | Draft spec.
SPEC-PACK-03 | Horizontal packs registry (the spec says 30; its table lists 31) | specs/pack-framework/03 |  | 2 Maximum features | Not Started | P1 | PC-073 |  | Draft spec.
SPEC-PACK-04 | MVP vertical packs (first 10) | specs/pack-framework/04 |  | 2 Maximum features | Not Started | P1 | PC-074 |  | Draft spec.
SPEC-PACK-05 | Blueprint structure and template-to-blueprint conversion | specs/pack-framework/05 |  | 2 Maximum features | Not Started | P1 | PC-072 |  | Draft spec.
SPEC-PACK-06C | Page template engine | specs/pack-framework/06c |  | 2 Maximum features | Not Started | P1 | PC-076 |  | Draft spec.
SPEC-PACK-06D | Shared package generator | specs/pack-framework/06d |  | 2 Maximum features | Not Started | P1 | R-572 |  | Draft spec.
SPEC-REPO-01 | Repo intelligence: import, analyse, edit | specs/repo-intelligence/01 |  | 3 Engineering Mode | Not Started | P1 | R-578 |  | Draft spec.
SPEC-STUDIO-01 | Unified Studio UX: mode-aware interface | specs/studio-ux/01 |  | Delivered | Not Started | P0 | PC-005 |  | Draft spec.
SPEC-STUDIO-02 | Existing repo import + edit (both modes) | specs/studio-ux/02 |  | 3 Engineering Mode | Not Started | P1 | R-578 |  | Draft spec.
SPEC-TPL-01 | Template marketplace: blueprint catalog and pack publishing | specs/template-marketplace/01 |  | 2 Maximum features | Not Started | P2 | PC-018 |  | Draft spec.
SPEC-TS-02 | Live in-browser preview | specs/table-stakes/02 |  | Delivered | Not Started | P0 | PC-007 |  | Draft spec.
SPEC-VIBE-01 | Vibe Mode Pro: AI builds it with a real backend | specs/vibe-mode-pro/01 |  | Delivered | Not Started | P0 | PC-004 |  | Draft spec.
T-5 | Workspace upgrades: editable code, diff per edit, API explorer | Template_Marketplace_Plan section 7 |  | 3 Engineering Mode | Not Started | P1 | PC-024
VP-accounts | Vertical pack accounts: Accounts, holders, beneficiaries, limits | registry | FinTech & banking (fintech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-affiliates | Vertical pack affiliates: Affiliate links, conversions, tiers | registry | Marketplace & commerce (commerce-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-agent-crm | Vertical pack agent-crm: Agent leads, pipelines, follow-ups | new (template Estately) | Real estate & proptech (real-estate-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-agents-brokers | Vertical pack agents-brokers: Agents, commissions, books | new | Insurance (insurance-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-agri-marketplace | Vertical pack agri-marketplace: Produce listings, buyers, logistics | new | Agriculture (agri-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-api-management | Vertical pack api-management: API products, keys, monetisation | registry | SaaS & B2B (saas-b2b-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-articles-cms | Vertical pack articles-cms: Articles, authors, categories, SEO | new | Content, media & publishing (content-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-assignments | Vertical pack assignments: Assignments, submissions, rubrics, peer review | registry (+ dependencies 'submissions', 'plagiarism') | Education & edtech (edtech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-attendance-leave | Vertical pack attendance-leave: Attendance, shifts, leave requests | spec | HR & recruiting (hr-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-attendance-school | Vertical pack attendance-school: Attendance and absence alerts | new | Schools & childcare (K-12) (schools-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-auctions-bidding | Vertical pack auctions-bidding: Auctions, bids, reserve prices | new | Marketplace & commerce (commerce-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-background-checks | Vertical pack background-checks: Driver checks, adverse actions | registry | Mobility & on-demand (mobility-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-basket-reorder | Vertical pack basket-reorder: Reorder, smart baskets | new | Quick commerce & grocery (quick-commerce-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-bids-estimates | Vertical pack bids-estimates: Estimates, bids, change orders | new | Construction & property services (construction-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-bill-of-materials | Vertical pack bill-of-materials: BOMs, versions, costing | new | Manufacturing & field operations (manufacturing-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-bill-payments-upi | Vertical pack bill-payments-upi: Bill payments, UPI, QR payments | new | FinTech & banking (fintech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-billing-codes | Vertical pack billing-codes: Claims, codes, payers, remittance | registry | Healthcare & life sciences (healthcare-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-candidate-pipeline | Vertical pack candidate-pipeline: Stages, interviews, scorecards, offers | new | HR & recruiting (hr-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-cards | Vertical pack cards: Card issuing, authorisations, disputes | registry | FinTech & banking (fintech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-catering | Vertical pack catering: Catering orders, proposals, deposits | registry | Food delivery & hospitality (food-delivery-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-certificates | Vertical pack certificates: Certificates, verifiable credentials | registry | Education & edtech (edtech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-channel-manager | Vertical pack channel-manager: Rates and availability across channels | new | Travel & hospitality (travel-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-check-in | Vertical pack check-in: Scan-in, badges, capacity | new | Events & ticketing (events-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-citizen-services | Vertical pack citizen-services: Service requests, status tracking | new | Nonprofit & civic (civic-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-claims | Vertical pack claims: FNOL, adjusting, settlement | new | Insurance (insurance-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-class-booking | Vertical pack class-booking: Classes, instructors, capacity, waitlists | new | Fitness & sports (fitness-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-client-intake | Vertical pack client-intake: Intake forms, conflict checks | new | Legal (legal-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-client-portal | Vertical pack client-portal: Client portal, approvals, reports | registry (+ dependencies 'customer-portal', 'clients') | Professional services & agencies (professional-services-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-client-profiles | Vertical pack client-profiles: Client history, preferences, before/after photos | new | Beauty, salon & wellness (beauty-wellness-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-clinical-trials | Vertical pack clinical-trials: Trials, protocols, enrolment, adverse events | registry | Healthcare & life sciences (healthcare-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-clubs-leagues | Vertical pack clubs-leagues: Teams, fixtures, standings | new | Fitness & sports (fitness-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-co-living-rentals | Vertical pack co-living-rentals: Rooms, short stays, house rules | new | Real estate & proptech (real-estate-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-cohorts | Vertical pack cohorts: Cohorts, mentors, leaderboards | registry | Education & edtech (edtech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-community-comments | Vertical pack community-comments: Comments, reactions, moderation | new | Content, media & publishing (content-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-compliance-aml | Vertical pack compliance-aml: AML alerts, cases, watchlists | registry (+ dependency 'case-management') | FinTech & banking (fintech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-compliance-education | Vertical pack compliance-education: FERPA/COPPA consent and audit | registry | Education & edtech (edtech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-compliance-kyc | Vertical pack compliance-kyc: KYC profiles, verification, risk rating | registry | FinTech & banking (fintech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-compliance-ps | Vertical pack compliance-ps: Engagement letters, conflict checks | registry | Professional services & agencies (professional-services-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-construction-projects | Vertical pack construction-projects: Projects, phases, site teams | new | Construction & property services (construction-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-contracts | Vertical pack contracts: Contracts, clauses, addenda | registry (+ dependency 'compliance-re') | Real estate & proptech (real-estate-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-couriers | Vertical pack couriers: Couriers, shifts, earnings, incentives | registry | Food delivery & hospitality (food-delivery-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-courses | Vertical pack courses: Courses, modules, lessons, prerequisites | registry | Education & edtech (edtech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-court-calendar | Vertical pack court-calendar: Hearings, filings, reminders | new | Legal (legal-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-creator-monetization | Vertical pack creator-monetization: Tips, subscriptions, paid content | new | Social & community (social-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-credit-scoring | Vertical pack credit-scoring: Score models, decisions | registry | FinTech & banking (fintech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-customer-loyalty-pos | Vertical pack customer-loyalty-pos: In-store loyalty and offers | new | Retail & restaurant POS (pos-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-customer-success | Vertical pack customer-success: Health scores, renewals, churn signals | new | SaaS & B2B (saas-b2b-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-customs | Vertical pack customs: Entries, HS classification, duty | registry (+ dependency 'hs-codes') | Logistics & supply chain (logistics-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-dark-stores | Vertical pack dark-stores: Dark stores, picking, packing | PRD | Quick commerce & grocery (quick-commerce-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-dating-matching | Vertical pack dating-matching: Matching, swipes, safety tools | new | Social & community (social-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-dealer-inventory | Vertical pack dealer-inventory: Vehicles for sale, specs, photos | new | Automotive (automotive-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-deliveries | Vertical pack deliveries: Packages, pickups, drop-offs, proof of delivery | registry (+ dependency 'proof-of-delivery') | Mobility & on-demand (mobility-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-delivery-slots | Vertical pack delivery-slots: Delivery slots and capacity | PRD | Quick commerce & grocery (quick-commerce-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-delivery-tracking | Vertical pack delivery-tracking: Live location, ETA, share links | registry (+ dependency 'tracking') | Food delivery & hospitality (food-delivery-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-dental-clinic | Vertical pack dental-clinic: Dental charts, treatment plans, recalls | new | Healthcare & life sciences (healthcare-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-digital-assets | Vertical pack digital-assets: Wallets, custody, transfers | registry (+ dependency 'custody') | FinTech & banking (fintech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-donations-fundraising | Vertical pack donations-fundraising: Donations, campaigns, receipts | new | Nonprofit & civic (civic-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-editorial-workflow | Vertical pack editorial-workflow: Draft -> review -> scheduled -> published | new | Content, media & publishing (content-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-employee-onboarding | Vertical pack employee-onboarding: Onboarding checklists, documents | spec | HR & recruiting (hr-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-enrollments | Vertical pack enrollments: Enrolments, progress, completion | registry | Education & edtech (edtech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-entitlements | Vertical pack entitlements: Per-feature and per-seat entitlements | registry | SaaS & B2B (saas-b2b-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-escrow | Vertical pack escrow: Escrow accounts, disbursements | registry | Real estate & proptech (real-estate-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-ev-charging | Vertical pack ev-charging: Chargers, sessions, billing | new | Utilities & energy (utilities-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-events | Vertical pack events: Events, agendas, speakers, venues | new | Events & ticketing (events-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-farm-advisory | Vertical pack farm-advisory: Weather, advisories, input orders | new | Agriculture (agri-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-farms-fields | Vertical pack farms-fields: Farms, fields, crops, seasons | new | Agriculture (agri-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-feeds-posts | Vertical pack feeds-posts: Posts, media, feeds, ranking | new | Social & community (social-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-field-service | Vertical pack field-service: Technician dispatch, job sheets, signatures | new | Manufacturing & field operations (manufacturing-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-fleet | Vertical pack fleet: Fleet, vehicles, maintenance, inspections | registry (+ dependencies 'vehicles', 'maintenance') | Mobility & on-demand (mobility-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-fleet-management | Vertical pack fleet-management: Assets, fuel, utilisation, TCO | registry (+ dependency 'fuel-cards') | Logistics & supply chain (logistics-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-food-orders | Vertical pack food-orders: Orders, kitchen tickets, timelines | registry ('orders') | Food delivery & hospitality (food-delivery-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-forums-qa | Vertical pack forums-qa: Forums, Q&A, accepted answers | new | Social & community (social-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-freight-forwarding | Vertical pack freight-forwarding: Quotes, bookings, milestones | registry | Logistics & supply chain (logistics-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-fulfillment | Vertical pack fulfillment: Fulfilment orders, shipments, labels, tracking | registry (+ dependency 'shipping') | Marketplace & commerce (commerce-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-ghost-kitchens | Vertical pack ghost-kitchens: Virtual brands, capacity | registry | Food delivery & hospitality (food-delivery-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-grading | Vertical pack grading: Gradebooks, schemes, exports | registry (+ dependency 'gradebook') | Education & edtech (edtech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-grants | Vertical pack grants: Grant applications and reporting | new | Nonprofit & civic (civic-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-grocery-catalog | Vertical pack grocery-catalog: Grocery catalogue, weights, substitutions | PRD | Quick commerce & grocery (quick-commerce-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-groups-communities | Vertical pack groups-communities: Groups, roles, rules | new | Social & community (social-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-gym-memberships | Vertical pack gym-memberships: Memberships, access, freezes | new | Fitness & sports (fitness-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-hipaa-compliance | Vertical pack hipaa-compliance: Access logs, breach reports, risk assessments | registry | Healthcare & life sciences (healthcare-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-hotel-pms | Vertical pack hotel-pms: Rooms, reservations, housekeeping, folios | new | Travel & hospitality (travel-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-insurance-commercial | Vertical pack insurance-commercial: Commercial policies, claims | registry (+ dependency 'insurance') | Mobility & on-demand (mobility-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-inventory | Vertical pack inventory: Stock levels, reservations, reorder points | registry | Marketplace & commerce (commerce-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-inventory-wms | Vertical pack inventory-wms: Locations, cycle counts, pick paths | registry (+ dependencies 'rfid', 'voice-picking') | Logistics & supply chain (logistics-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-investment-analysis | Vertical pack investment-analysis: Pro formas, cash flow, IRR | registry | Real estate & proptech (real-estate-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-invoicing-ps | Vertical pack invoicing-ps: Progress and milestone invoicing | registry | Professional services & agencies (professional-services-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-itineraries | Vertical pack itineraries: Trips, itineraries, documents | new | Travel & hospitality (travel-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-job-lifecycle | Vertical pack job-lifecycle: Booked -> en route -> in progress -> done | PRD | On-demand home services (home-services-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-job-quotes | Vertical pack job-quotes: Quotes, estimates, approvals | PRD | On-demand home services (home-services-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-jobs-ats | Vertical pack jobs-ats: Job posts, applicant tracking | spec | HR & recruiting (hr-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-kitchen | Vertical pack kitchen: Kitchen display, stations, prep times | registry | Food delivery & hospitality (food-delivery-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-lab-integration | Vertical pack lab-integration: Lab interfaces, HL7 mapping, QC | registry | Healthcare & life sciences (healthcare-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-lab-orders | Vertical pack lab-orders: Lab orders, specimens, results | registry | Healthcare & life sciences (healthcare-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-last-mile | Vertical pack last-mile: Route plans, stop sequencing, time windows | registry (+ dependency 'routing') | Mobility & on-demand (mobility-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-last-mile-logistics | Vertical pack last-mile-logistics: Routes, stops, exceptions | registry | Logistics & supply chain (logistics-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-ledger-core | Vertical pack ledger-core: Journals, periods, reconciliation | registry | FinTech & banking (fintech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-legal-documents | Vertical pack legal-documents: Templates, clause library, versions | new | Legal (legal-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-lending | Vertical pack lending: Loan origination, underwriting, amortisation | registry | FinTech & banking (fintech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-listings-re | Vertical pack listings-re: Property listings, price history, disclosures | registry | Real estate & proptech (real-estate-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-live-classes | Vertical pack live-classes: Live classes, attendance, recordings | new | Education & edtech (edtech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-lms-admin | Vertical pack lms-admin: Schools, departments, instructors | registry | Education & edtech (edtech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-loyalty | Vertical pack loyalty: Points, tiers, rewards | registry | Food delivery & hospitality (food-delivery-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-maintenance-cmms | Vertical pack maintenance-cmms: Assets, preventive maintenance | new | Manufacturing & field operations (manufacturing-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-marketplace-saas | Vertical pack marketplace-saas: App listings, provisioning | registry (+ dependency 'provisioning') | SaaS & B2B (saas-b2b-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-marketplace-seo | Vertical pack marketplace-seo: Programmatic SEO, structured data | registry | Marketplace & commerce (commerce-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-matters-cases | Vertical pack matters-cases: Matters, parties, deadlines | new | Legal (legal-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-memberships-packages | Vertical pack memberships-packages: Memberships, packages, prepaid sessions | new | Beauty, salon & wellness (beauty-wellness-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-mental-health | Vertical pack mental-health: Therapy sessions, journals, assessments | new | Healthcare & life sciences (healthcare-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-menus | Vertical pack menus: Menus, modifiers, allergens, nutrition | registry | Food delivery & hospitality (food-delivery-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-meter-reading | Vertical pack meter-reading: Meters, readings, anomalies | new | Utilities & energy (utilities-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-newsletters | Vertical pack newsletters: Newsletters, subscribers, campaigns | new | Content, media & publishing (content-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-offers | Vertical pack offers: Offers, counters, contingencies | registry | Real estate & proptech (real-estate-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-open-banking | Vertical pack open-banking: Consent, data access, payment initiation | registry | FinTech & banking (fintech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-organizations | Vertical pack organizations: Organisations, memberships, domains | registry | SaaS & B2B (saas-b2b-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-outage-management | Vertical pack outage-management: Outages, crews, notifications | new | Utilities & energy (utilities-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-parent-portal | Vertical pack parent-portal: Parent messages, report cards, payments | new | Schools & childcare (K-12) (schools-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-parking | Vertical pack parking: Parking spots, bookings, enforcement | new | Mobility & on-demand (mobility-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-parts-catalog | Vertical pack parts-catalog: Parts catalogue, fitment | new | Automotive (automotive-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-payroll | Vertical pack payroll: Payroll runs, payslips, deductions | spec | HR & recruiting (hr-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-paywall-membership | Vertical pack paywall-membership: Paywalls, memberships, metered access | new | Content, media & publishing (content-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-performance-reviews | Vertical pack performance-reviews: Goals, reviews, feedback | spec (+ registry dependencies 'people', 'skills') | HR & recruiting (hr-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-permits-licensing | Vertical pack permits-licensing: Applications, inspections, licences | new | Nonprofit & civic (civic-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-personal-finance | Vertical pack personal-finance: Budgets, expense categorisation, savings goals | new (registry dependencies 'budgeting', 'expenses') | FinTech & banking (fintech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-personal-training | Vertical pack personal-training: Trainers, sessions, packages | new | Fitness & sports (fitness-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-pet-profiles | Vertical pack pet-profiles: Pets, vaccinations, records | new | Pets & veterinary (pets-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-pet-services | Vertical pack pet-services: Grooming, boarding, walking | new | Pets & veterinary (pets-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-pharmacy-integration | Vertical pack pharmacy-integration: Formulary, dispense, interaction checks | registry | Healthcare & life sciences (healthcare-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-podcasts-video | Vertical pack podcasts-video: Episodes, feeds, players | new | Content, media & publishing (content-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-policies | Vertical pack policies: Policies, coverages, endorsements | new | Insurance (insurance-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-pos-terminal | Vertical pack pos-terminal: Point of sale, receipts, cash drawer | new | Retail & restaurant POS (pos-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-premium-billing | Vertical pack premium-billing: Premium schedules, collections | new | Insurance (insurance-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-procurement | Vertical pack procurement: Requisitions, POs, three-way match | registry (+ dependency 'spend-analysis') | Logistics & supply chain (logistics-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-production-orders | Vertical pack production-orders: Work orders, routings | new | Manufacturing & field operations (manufacturing-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-profiles-social | Vertical pack profiles-social: Profiles, follows, blocks | new | Social & community (social-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-projects | Vertical pack projects: Projects, phases, milestones, budgets | registry | Professional services & agencies (professional-services-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-properties | Vertical pack properties: Properties, units, amenities, valuations | registry | Real estate & proptech (real-estate-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-property-mgmt | Vertical pack property-mgmt: Leases, tenants, maintenance, rent | registry (+ dependencies 'portals', 'accounting') | Real estate & proptech (real-estate-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-proposals | Vertical pack proposals: Proposals, SOWs, e-sign | registry (+ dependency 'crm-integration') | Professional services & agencies (professional-services-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-provider-matching | Vertical pack provider-matching: Match jobs to nearby qualified pros | PRD | On-demand home services (home-services-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-purchase-orders | Vertical pack purchase-orders: B2B purchase orders and approvals | new (registry dependency) | Marketplace & commerce (commerce-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-quality-control | Vertical pack quality-control: Inspections, non-conformances | new | Manufacturing & field operations (manufacturing-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-quizzes-exams | Vertical pack quizzes-exams: Question banks, timed exams, proctoring | new | Education & edtech (edtech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-quotes-underwriting | Vertical pack quotes-underwriting: Quotes, rating, underwriting rules | new | Insurance (insurance-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-regulatory-reporting | Vertical pack regulatory-reporting: Regulatory reports and filings | registry | FinTech & banking (fintech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-resource-planning | Vertical pack resource-planning: Allocations, capacity, skills | registry | Professional services & agencies (professional-services-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-restaurants | Vertical pack restaurants: Restaurants, hours, locations | registry (+ dependency 'multi-location') | Food delivery & hospitality (food-delivery-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-retainers | Vertical pack retainers: Retainer balances, drawdowns | registry (+ dependency 'retainer') | Professional services & agencies (professional-services-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-returns | Vertical pack returns: Returns, inspections, refunds, exchanges | registry | Marketplace & commerce (commerce-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-reviews | Vertical pack reviews: Verified-purchase reviews, moderation | registry | Marketplace & commerce (commerce-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-rider-batching | Vertical pack rider-batching: Batching orders per rider | PRD | Quick commerce & grocery (quick-commerce-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-salon-booking | Vertical pack salon-booking: Service booking with staff and chairs | PRD | Beauty, salon & wellness (beauty-wellness-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-school-admin | Vertical pack school-admin: Students, classes, timetables, fees | new | Schools & childcare (K-12) (schools-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-school-transport | Vertical pack school-transport: Bus routes and live tracking | new | Schools & childcare (K-12) (schools-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-scim-provisioning | Vertical pack scim-provisioning: SCIM user provisioning | new | SaaS & B2B (saas-b2b-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-seating-maps | Vertical pack seating-maps: Seat maps and reservations | new | Events & ticketing (events-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-seats | Vertical pack seats: Seats, assignment, true-ups | registry | SaaS & B2B (saas-b2b-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-service-catalog | Vertical pack service-catalog: Services, pricing, service areas | PRD | On-demand home services (home-services-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-service-center | Vertical pack service-center: Service bookings, job cards, parts | new | Automotive (automotive-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-service-menu | Vertical pack service-menu: Services, durations, add-ons | PRD | Beauty, salon & wellness (beauty-wellness-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-service-warranty | Vertical pack service-warranty: Warranties, callbacks, disputes | new | On-demand home services (home-services-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-shift-cash-management | Vertical pack shift-cash-management: Shifts, cash-ups, variances | new | Retail & restaurant POS (pos-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-shipments | Vertical pack shipments: Shipments, legs, bills of lading | registry | Logistics & supply chain (logistics-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-site-diary | Vertical pack site-diary: Daily logs, photos, safety incidents | new | Construction & property services (construction-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-sponsors-exhibitors | Vertical pack sponsors-exhibitors: Sponsors, booths, leads | new | Events & ticketing (events-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-sso-oidc | Vertical pack sso-oidc: OIDC SSO | registry | SaaS & B2B (saas-b2b-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-sso-saml | Vertical pack sso-saml: SAML SSO, JIT provisioning | registry | SaaS & B2B (saas-b2b-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-staff-schedules | Vertical pack staff-schedules: Stylist schedules, commissions | PRD | Beauty, salon & wellness (beauty-wellness-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-store-inventory | Vertical pack store-inventory: Store stock, transfers, counts | new | Retail & restaurant POS (pos-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-subcontractors | Vertical pack subcontractors: Subcontractors, compliance, payments | new | Construction & property services (construction-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-subscriptions-commerce | Vertical pack subscriptions-commerce: Subscription boxes, physical + digital | registry | Marketplace & commerce (commerce-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-substitutions | Vertical pack substitutions: Out-of-stock substitution approval | new | Quick commerce & grocery (quick-commerce-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-supply-chain-visibility | Vertical pack supply-chain-visibility: Control tower, ETAs, risk scores | registry | Logistics & supply chain (logistics-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-surge-pricing | Vertical pack surge-pricing: Demand/supply signals, multipliers | registry | Mobility & on-demand (mobility-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-table-reservations | Vertical pack table-reservations: Tables, reservations, waitlist | new | Food delivery & hospitality (food-delivery-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-teams | Vertical pack teams: Teams, members, channels | registry | SaaS & B2B (saas-b2b-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-test-drives | Vertical pack test-drives: Test-drive booking | new | Automotive (automotive-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-ticketing | Vertical pack ticketing: Ticket types, sales, QR tickets | new | Events & ticketing (events-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-time-tracking | Vertical pack time-tracking: Time entries, timers, approvals | registry | Professional services & agencies (professional-services-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-tours | Vertical pack tours: Tour scheduling, self-guided, virtual | registry (+ dependency 'virtual-tours') | Real estate & proptech (real-estate-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-tours-activities | Vertical pack tours-activities: Experiences, guides, capacity | new | Travel & hospitality (travel-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-trade-finance | Vertical pack trade-finance: Letters of credit, guarantees | registry (+ dependency 'letters-of-credit') | FinTech & banking (fintech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-transfers | Vertical pack transfers: Transfers, ACH/SEPA/UPI, FX | registry (+ dependency 'transactions') | FinTech & banking (fintech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-transportation | Vertical pack transportation: Loads, carriers, tenders, rates | registry (+ dependency 'compliance-dot') | Logistics & supply chain (logistics-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-travel-booking | Vertical pack travel-booking: Flights/stays/packages search and booking | new | Travel & hospitality (travel-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-treasury | Vertical pack treasury: Cash positions, forecasts, sweeps | registry | FinTech & banking (fintech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-usage-metering | Vertical pack usage-metering: Meters, quotas, alerts | registry | SaaS & B2B (saas-b2b-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-utility-billing | Vertical pack utility-billing: Tariffs, bills, payments | new | Utilities & energy (utilities-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-vehicle-history | Vertical pack vehicle-history: Ownership and service history | new | Automotive (automotive-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-vehicle-rentals | Vertical pack vehicle-rentals: Car/bike/scooter rental, unlock, trip billing | new | Mobility & on-demand (mobility-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-vet-clinic | Vertical pack vet-clinic: Vet appointments, treatments | new | Pets & veterinary (pets-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-video-streaming | Vertical pack video-streaming: Video lessons, captions, DRM | registry (+ dependency 'drm') | Education & edtech (edtech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-volunteers | Vertical pack volunteers: Volunteer shifts and hours | new | Nonprofit & civic (civic-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-warehouses | Vertical pack warehouses: Warehouses, zones, slotting, labour | registry (+ dependencies 'warehouse', 'slotting', 'labor') | Logistics & supply chain (logistics-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-wealth-management | Vertical pack wealth-management: Portfolios, rebalancing, goals | registry (+ dependency 'portfolio') | FinTech & banking (fintech-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-white-label | Vertical pack white-label: Brands, custom domains, rollouts | registry | SaaS & B2B (saas-b2b-core) | 2 Maximum features | Not Started | P2 | PC-080
VP-wishlists-recommendations | Vertical pack wishlists-recommendations: Wishlists, recently viewed, recommendations | new | Marketplace & commerce (commerce-core) | 2 Maximum features | Not Started | P1 | PC-074
VP-workout-plans | Vertical pack workout-plans: Programs, workouts, progress | new | Fitness & sports (fitness-core) | 2 Maximum features | Not Started | P3 | PC-081
VP-yard-management | Vertical pack yard-management: Yard slots, gate check-in, docks | new | Logistics & supply chain (logistics-core) | 2 Maximum features | Not Started | P2 | PC-080
PC-052 | File uploads and storage in generated apps (S3-compatible, presigned URLs, image processing) | Platform_Completion queue | Both | 2 Maximum features | Superseded | P1 |  |  | Local MinIO-style store for dev; any S3 provider on publish. From the architecture plan. Superseded 2026-09-30: PC-102 (Python, per-field rules, content checks, R2/S3/local, cloud drives through Companion; the founder chose R2/S3 and no MinIO) and PC-105 (Go and Node) did it. Left for later: image processing (resizing, thumbnails).
GAP-WIREFRAMES | Console wireframes | V6_Review_and_Gap_Analysis section 3 |  | Delivered | Superseded |  | R-491 |  | The console was built directly (R-491..R-497).
R-010 | Native iOS Agent | Execution_Tracker_v6 | Agents | Delivered | Superseded |  | R-576 |  | Native iOS is built by the R-576 adapter, not a separate agent.
R-011 | Web/Admin Agent | Execution_Tracker_v6 | Agents | Delivered | Superseded |  | R-227 |  | IR + deterministic adapters replaced per-surface agents.
R-012 | Backend Agent | Execution_Tracker_v6 | Agents | Delivered | Superseded |  | R-229 |  | Python/Go/Node backend adapters.
R-013 | Database Agent | Execution_Tracker_v6 | Agents | Delivered | Superseded |  | R-238 |  | Schema and migrations generated from the IR.
R-014 | QA Agent | Execution_Tracker_v6 | Agents | Delivered | Superseded |  | R-560 |  | Compile-verify-repair loop in the build path.
R-015 | Security Review Agent | Execution_Tracker_v6 | Agents | Delivered | Superseded |  | R-508 |  | Security scanning and automated tests.
R-111 | Cross-platform Mobile Agent | Execution_Tracker_v6 | Framework Strategy | Delivered | Superseded |  | R-514
R-132 | Framework-specific repo templates | Execution_Tracker_v6 | Git/Repository | Delivered | Superseded |  | R-232 |  | Adapters generate the project; no separate repo templates.
R-136 | Recommendation score model | Execution_Tracker_v6 | Framework Strategy | Delivered | Superseded |  | R-559
R-224 | Next.js console upgrade | Execution_Tracker_v6 | Console | Delivered | Superseded |  | R-470 | 2026-09-06 | The Next.js console shipped in R-470 and R-491..R-497.
SPEC-PACK-06A | State machine codegen | specs/pack-framework/06a |  | Delivered | Superseded |  | R-566 |  | Delivered by R-566, R-588, R-589.
ARCH-ENTERPRISE | Enterprise: SSO (SAML/OIDC), SCIM, audit export, data residency | docs/ARCHITECTURE_MASTER_PLAN.md §10 Phase 4 |  | Post-launch | Deferred | P3 |  |  | After launch.
R-028 | Redis | Execution_Tracker_v6 | Data | Post-launch | Deferred | P3 |  |  | Redis: no need until load says so.
R-029 | NATS / managed queue | Execution_Tracker_v6 | Data | Post-launch | Deferred | P3 |  |  | NATS / managed queue: no need yet.
R-030 | S3-compatible object storage | Execution_Tracker_v6 | Data | Post-launch | Deferred | P2 |  |  | Object storage: needed when generated apps store files at scale.
R-058 | Language-specific structured editors | Execution_Tracker_v6 | Code Editing | Post-launch | Deferred | P3 |  |  | Language-specific structured editors.
R-061 | Environment parity | Execution_Tracker_v6 | Deployment | Post-launch | Deferred | P3
R-068 | Project health score | Execution_Tracker_v6 | Analytics | Post-launch | Deferred | P3 |  |  | Project health score.
R-072 | Build artifact caching | Execution_Tracker_v6 | Reliability | Post-launch | Deferred | P3 |  |  | Build artifact caching.
R-073 | Incremental test selection | Execution_Tracker_v6 | Reliability | Post-launch | Deferred | P3 |  |  | Incremental test selection.
R-079 | Model benchmark service | Execution_Tracker_v6 | Models | Post-launch | Deferred | P3
R-081 | Specialist agent marketplace | Execution_Tracker_v6 | Agents | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-082 | Physical device cloud | Execution_Tracker_v6 | Testing | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-083 | MicroVM sandbox | Execution_Tracker_v6 | Infrastructure | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-084 | Multi-region build/control plane | Execution_Tracker_v6 | Infrastructure | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-085 | BYOC | Execution_Tracker_v6 | Enterprise | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-086 | Data residency controls | Execution_Tracker_v6 | Enterprise | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-087 | Policy-as-code | Execution_Tracker_v6 | Enterprise | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-088 | Cross-platform consistency checker | Execution_Tracker_v6 | Architecture | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-089 | Automated refactoring planner | Execution_Tracker_v6 | Architecture | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-090 | Mutation/fuzz testing | Execution_Tracker_v6 | Quality | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-091 | Predictive capacity scheduler | Execution_Tracker_v6 | Cost | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-092 | Spot/preemptible optimization | Execution_Tracker_v6 | Cost | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-093 | Quality trend analytics | Execution_Tracker_v6 | Analytics | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-124 | Repository naming convention | Execution_Tracker_v6 | Git/Repository | Post-launch | Deferred | P3 |  |  | Repository naming convention.
R-129 | Repository split decision policy | Execution_Tracker_v6 | Git/Repository | Post-launch | Deferred | P3
R-130 | Enterprise multi-repo support | Execution_Tracker_v6 | Git/Repository | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-131 | CODEOWNERS + protected paths | Execution_Tracker_v6 | Git/Repository | Post-launch | Deferred | P3 |  |  | CODEOWNERS + protected paths.
R-134 | Repository/build health metrics | Execution_Tracker_v6 | Analytics | Post-launch | Deferred | P3
R-157 | Runner manager boundary | Execution_Tracker_v6 | Platform Architecture | Post-launch | Deferred | P3 |  |  | services/runner-manager is empty; sandbox drivers cover it for now.
R-159 | Immutable build promotion | Execution_Tracker_v6 | CI/CD | Post-launch | Deferred | P3
R-160 | Framework upgrade workflow | Execution_Tracker_v6 | Developer Experience | Post-launch | Deferred | P3
R-162 | Interactive cloud simulator metering | Execution_Tracker_v6 | Preview | Post-launch | Deferred | P3
R-164 | Template/repo health dashboard | Execution_Tracker_v6 | Analytics | Post-launch | Deferred | P3
R-166 | Cross-repo task coordinator | Execution_Tracker_v6 | Git/Repository | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-167 | BYOC / private runners | Execution_Tracker_v6 | Infrastructure | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-168 | Physical device cloud integration | Execution_Tracker_v6 | Testing | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-169 | Template support lifecycle | Execution_Tracker_v6 | Templates | Post-launch | Deferred | P3
R-170 | Framework/toolchain production SLO | Execution_Tracker_v6 | Reliability | Post-launch | Deferred | P3
R-189 | Build-vs-Buy benchmark process | Execution_Tracker_v6 | Architecture | Post-launch | Deferred | P3
R-191 | Shared engineering glossary | Execution_Tracker_v6 | Team | Post-launch | Deferred | P3
R-192 | Verified MCP install flow | Execution_Tracker_v6 | Tools | Post-launch | Deferred | P3
R-193 | Cross-platform Local Agent | Execution_Tracker_v6 | Execution | Post-launch | Deferred | P3 |  |  | The platform already runs locally.
R-196 | Sandbox snapshots and warm pools | Execution_Tracker_v6 | Runtime | Post-launch | Deferred | P3
R-197 | Agent time-travel debugging | Execution_Tracker_v6 | Developer Experience | Post-launch | Deferred | P3
R-198 | Tool marketplace verification | Execution_Tracker_v6 | Tools | Post-launch | Deferred | P3
R-199 | Runtime provider cost-latency routing | Execution_Tracker_v6 | Routing | Post-launch | Deferred | P3
R-201 | Customer private MCP servers | Execution_Tracker_v6 | Tools | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-202 | Private BYOC runners | Execution_Tracker_v6 | Execution | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-203 | Cross-region runtime scheduler | Execution_Tracker_v6 | Runtime | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-204 | Hardened microVM runner fleet | Execution_Tracker_v6 | Runtime | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-205 | Multi-provider sandbox failover | Execution_Tracker_v6 | Reliability | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-206 | Policy-as-code approvals | Execution_Tracker_v6 | Governance | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-207 | Two-person critical approval | Execution_Tracker_v6 | Governance | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-208 | Customer private model endpoints | Execution_Tracker_v6 | Models | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-209 | Automated provider benchmark suite | Execution_Tracker_v6 | Architecture | Post-launch | Deferred | P3 |  |  | Advanced / enterprise: after launch.
R-215 | Runtime provider outage failover | Execution_Tracker_v6 | Reliability | Post-launch | Deferred | P3
R-218 | Local Agent security lifecycle | Execution_Tracker_v6 | Security | Post-launch | Deferred | P3
BP-FLUTTER | Flutter mobile adapter | Platform_Buildout section 8 ('R-529') |  | Post-launch | Dropped |  |  |  | Removed by the stack policy.
R-077 | Flutter target (GA baseline) | Execution_Tracker_v6 | Mobile | Post-launch | Dropped |  |  |  | Flutter: removed by the stack policy.
R-118 | Flutter Web optional profile | Execution_Tracker_v6 | Web/Admin | Post-launch | Dropped |  |  |  | Flutter Web: removed by the stack policy.
R-119 | React Native Web optional profile | Execution_Tracker_v6 | Web/Admin | Post-launch | Dropped |  |  |  | React Native Web: removed by the stack policy.
R-140 | Flutter lean template | Execution_Tracker_v6 | Templates | Post-launch | Dropped |  |  |  | Flutter: removed by the stack policy.
R-141 | Flutter scaled template | Execution_Tracker_v6 | Templates | Post-launch | Dropped |  |  |  | Flutter: removed by the stack policy.
R-188 | Rapid BaaS profile design | Execution_Tracker_v6 | Backend Strategy | Post-launch | Dropped |  |  |  | BaaS profile: generated apps own a real API + DB.
R-200 | BaaS provider expansion | Execution_Tracker_v6 | Backend Strategy | Post-launch | Dropped |  |  |  | BaaS expansion: see R-188.
R-217 | BaaS to custom migration test | Execution_Tracker_v6 | Backend Strategy | Post-launch | Dropped |  |  |  | BaaS migration: see R-188.
PC-001 | Master task list: reconcile every R_&_D source into one queue | Platform_Completion queue | Platform | 0 Foundation | Completed | P0 |  | 2026-09-26 | This document. Done when the founder approves it.
PC-002 | Founder decisions that block later phases (see Decisions sheet) | Platform_Completion queue | Platform | 0 Foundation | Completed | P0 |  | 2026-09-26 | Pricing/free tier, hosting cloud + region, payment processor, email verification, in-browser preview engine licence, app-store accounts. D-5, D-8, D-9 answered 2026-09-26.
PC-062 | Native mobile preview: R&D and plan (open source first) | Platform_Completion queue | Both | 0 Foundation | Completed | P0 |  | 2026-09-26 | NATIVE_MOBILE_PREVIEW_PLAN.md in this folder.
PC-047 | NVIDIA model provider (nemotron-3-ultra) for builds, configured from .env | Platform_Completion queue | Platform | 0 Foundation | Completed | P0 |  | 2026-09-26 | Founder's chosen LLM (D-9). OpenAI-compatible, so one provider entry plus the NVIDIA_MODEL_BASE_URL override, prices and tests. The key stays in .env only. Includes a first comparison against the providers we already support on the same build prompts.
PC-093 | Intake repairs instead of rejecting: a model's status-change endpoint becomes a workflow transition, and an undeclared request-schema reference is fixed, not fatal | Platform_Completion queue | Both | 0 Foundation | Completed | P0 |  | 2026-09-26 | Found by PC-047's comparison (2026-09-26): 3 of 6 real intake runs, on both NVIDIA and Gemini, were rejected for the same reason. Roughly half of real prompts fail at the first step whichever model runs, so this comes before everything else.
PC-003 | Stack policy in code: an app request gets a store-ready React Native app AND an installable PWA with QR; Flutter and React.js refused with the reason | Platform_Completion queue | Both | 0 Foundation | Completed | P0 |  | 2026-09-26 | R-562 already builds the React Native app; the PWA + QR half is R-573. Native Kotlin/Swift only after Phase 5. Uses the R-559 'nearest thing we can build, with a reason' path.
R-591 | Complete auth for the Go backend: register, login, logout, me, forgot password, reset password | Platform_Completion queue | Both | 1 Vibe Mode live | Completed | P0 |  | 2026-09-26 | A Go app with auth has no way for a real user to sign in. Parity with the Python backend's auth (R-461, R-463), companions included.
R-590 | Workflow transitions as buttons on the generated screens | Platform_Completion queue | Both | 1 Vibe Mode live | Completed | P0 |  | 2026-09-26 | The user-visible half of R-566.
R-573 | PWA really by default: manifest, service worker, icons, install prompt, QR | Platform_Completion queue | Vibe | 1 Vibe Mode live | Completed | P0 |  | 2026-09-26 | Works for templates only today; generated projects must install on a real phone.
PC-004 | Real API + DB for every feature: a Vibe build fails if any screen or action is not wired to a real endpoint and table | Platform_Completion queue | Vibe | 1 Vibe Mode live | Completed | P0 |  | 2026-09-26 | No mock data, no 501 stubs, no dead buttons. From specs/vibe-mode-pro. Found in R-590: the Node repositories silently fall back to an in-memory map on any database error and report success; a malformed id answers 500 instead of 404 on the Python backend.
PC-005 | Vibe / Engineering mode switch in the Studio | Platform_Completion queue | Both | 1 Vibe Mode live | Completed | P0 |  | 2026-09-26 | From specs/studio-ux/01. Vibe hides the machinery; Engineering shows plan, stack, diffs, report, PRs.
PC-006 | 'Wow in 30 seconds': first screen streams fast, latest modern UI, maximum polish per page | Platform_Completion queue | Vibe | 1 Vibe Mode live | Completed | P0 |  | 2026-09-26 | R-558 fixed the design system; still needs speed-to-first-screen and visual quality. From specs/table-stakes/01 and the buildout 'intent card' idea. Measured in PC-084: plan 20-29 s (model) and preview start ~14 s are the stages to cut; model-written pages cost ~80 s and their admin page failed to compile, so the repair loop must cover the admin app before model-written pages return to the default path. Speed half done 2026-09-26: preview start 17.7 -> 9.6 s (shared warm API environment, surfaces probed together), live prompt -> running app 12-15 s on Groq; fixed model navigation objects breaking pages. First screen done: tracker home, readable names, cards that say what you can do, header fits a phone. Follow-ups: preview during verification (~5 s), detail screens out of the top bar, auth User entity off home cards. The 'latest modern UI' half was not delivered: pages stayed template-only; carried by PC-097 to PC-101.
PC-084 | Speed targets measured on every build and enforced: prompt -> preview under 90 s, prompt -> live URL under 3 min, as a dashboard and a regression gate | Platform_Completion queue | Vibe | 1 Vibe Mode live | Completed | P1 |  | 2026-09-26 | The Targets sheet had numbers but no task measured them. Founder-approved 2026-09-26.
PC-085 | Model quality evals and best-model routing: score every provider (NVIDIA, cloud, local) per task type and route each job to the best one | Platform_Completion queue | Both | 1 Vibe Mode live | Completed | P1 |  | 2026-09-27 | NVIDIA nemotron is unproven for code; this keeps quality independent of one vendor. Founder-approved 2026-09-26. Done 2026-09-27: plan and code evals, scorecard routing; follow-ups: more code cases, score Gemini once its daily quota resets, route the build's repair step as a code job.
PC-095 | Build fallback chain: Groq -> Gemini -> OpenRouter (free) -> NVIDIA -> local Ollama | Platform_Completion queue | Platform | 1 Vibe Mode live | Completed | P1 |  | 2026-09-26 | Founder, 2026-09-26. A rate-limited or failing provider hands the build to the next one.
PC-094 | Intake repairs, round 2: duplicate roles, a lifecycle for a missing entity, and a clean error (not a crash) for malformed plan parts | Platform_Completion queue | Both | 1 Vibe Mode live | Completed | P1 |  | 2026-09-27 | Found testing weaker models on 2026-09-26: qwen3.8-27b crashed intake with an AttributeError; nemotron named a lifecycle for an entity it did not declare; qwen2.5-coder:7b declared the role 'user' twice. Each is repairable the way PC-093 repairs endpoints.
PC-007 | Instant in-browser preview (no local toolchain needed) | Platform_Completion queue | Vibe | 1 Vibe Mode live | Completed | P0 |  | 2026-09-27 | From specs/table-stakes/02 and tracker R-174. Built behind a preview-engine interface with an open-source engine first; a paid engine licence (D-6) is only a key at the end. Done 2026-09-27: engine switch + container engine (Docker only, gVisor where registered); the WebContainer engine is PC-096.
PC-008 | One-click publish to a live URL: web, admin, API and database together, code complete and proven against local stand-ins | Platform_Completion queue | Vibe | 1 Vibe Mode live | Completed | P0 |  | 2026-09-27 | R-509/R-510 publish the web app only and were never run for real. From specs/table-stakes/03. Real accounts are plugged in at PC-070. Done 2026-09-27 against the local stand-in; a real server + domain is proven at PC-071.
PC-009 | Hosted multi-tenant service: per-user isolation of builds, sessions and previews; quotas; egress policy | Platform_Completion queue | Platform | 1 Vibe Mode live | Completed | P0 |  | 2026-09-27 | Today the Studio is one trusted operator's tool. Built cloud-neutral and proven locally (Colima); the cloud account (D-2) is plugged in at PC-070. Done 2026-09-27; left: per-user disk quotas, cloud account.
PC-010 | Credit fairness: estimate before a build, no charge for internal retries, per-task budgets, cost guardrails | Platform_Completion queue | Platform | 1 Vibe Mode live | Completed | P0 |  | 2026-09-27 | Done 2026-09-27; model prices beyond Groq are PC-011.
PC-011 | Plans, entitlements, credit top-up and super_admin console (Phase E) | Platform_Completion queue | Platform | 1 Vibe Mode live | Completed | P0 |  | 2026-09-27 | Stripe and Razorpay adapters complete and tested in their test modes; live keys (D-3) at PC-070. Found in R-590: self-registered users get role 'user', which is not one of the plan's roles, so role-guarded actions need an admin to assign roles — include a role manager in the generated admin console. Done 2026-09-27; prices and live keys at PC-070.
PC-012 | Legal and account basics: ToS, privacy, retention, deletion/export, email verification | Platform_Completion queue | Platform | 1 Vibe Mode live | Completed | P0 |  | 2026-09-27 | Done 2026-09-27; emails go through Resend once keyed (PC-070), legal texts are drafts for counsel. Not built: cancelling a paid plan from Settings (deleting the account cancels it) — with billing go-live at PC-070.
PC-013 | Verified integrations catalog with health tests | Platform_Completion queue | Vibe | 1 Vibe Mode live | Completed | P1 |  | 2026-09-27 | R-511 Connectors v1 exists. Done 2026-09-27 (also proves R-511 live); real-account checks of Resend/Stripe/Razorpay pass at PC-070.
PC-097 | Compile repair covers every Next surface (admin console and ecosystem role surfaces), not only the main web app | Platform_Completion queue | Both | 1 Vibe Mode live | Completed | P1 |  | 2026-09-28 | Found publishing a clinic app on 2026-09-27: the `provider` role surface shipped a model-written page with an invented import and misused components; the build never checked it. PC-008 now type-checks every Next surface and publish refuses a broken app with the compiler's reason; this task makes the repair loop fix or revert those pages as it does for web. First of the modern-UI block (added 2026-09-27, founder-approved): PC-098 turns model-written pages back on only once this holds, so no surface can ship a page that does not compile. Done 2026-09-28.
PC-098 | Model-written pages back on for every Vibe build: fast template first, modern pages upgraded in the background, safe under chat edits | Platform_Completion queue | Both | 1 Vibe Mode live | Completed | P0 |  | 2026-09-28 | PC-084 switched them off (80 s per build; its admin page did not compile), so every console build is template pages only: 1 model-written page across 33 projects on 2026-09-27. Must: (1) show the template preview as today, then replace pages one by one with model-written ones, each type-checked and repaired (PC-097) or kept as the template - never a broken page; (2) include the page-writing cost in the estimate before the build (PC-010); (3) chat edits update a model-written page instead of regenerating it from the template, so an edit never throws the modern page away; (4) pages still use only the app's real data hooks (PC-004); (5) say plainly which pages were upgraded and which kept the template; (6) task verify stays offline (templates only, 0 model calls); (7) a weak local model (PC-014) falls back cleanly. Measured in PC-097 (2026-09-28): on Groq's free tier the page-writing request is too large (413) for a real project even with compact grounding, and answers arrive truncated, so pages must be written from a much smaller prompt or on a larger-context model (Gemini wrote and repaired an admin page); most first drafts had 1-4 type errors, so the page prompt must shrink them. Done 2026-09-28 on free keys: a chain (Gemini 3.8 Flash, Gemini 3.5 Flash-Lite, OpenRouter free, NVIDIA, local Qwen2.5-Coder 14B) designed 8 of 8 pages of a food-delivery app in 7.5 min. A billed key later only goes first in the chain (PC-070).
PC-099 | A design direction per project: colours, type, radius, density and layout style chosen from the prompt and the product's archetype | Platform_Completion queue | Both | 1 Vibe Mode live | Completed | P0 |  | 2026-09-29 | Every project on 2026-09-27 shared one byte-identical tokens.css, so all apps look alike. Pick a coherent direction (palette with checked contrast, type pairing, shape, spacing, light/dark) from the prompt ('modern', 'playful', 'luxury', named brand colours) and the archetype; write it to brand.json and the tokens, and give it to the page writer. A deterministic default without a model; the same prompt gives the same direction. Shown and editable in the Plan view (PC-022) and later the brand kit (PC-020). Found in PC-098: a designed home page brings its own header and the app shell's navbar still renders above it - the direction covers the layout (one header), not only the page. Done 2026-09-29: ten styles, domain palettes, font pairs loaded from Google Fonts, saved in the plan; components and pages themed; ecosystems designed too. Not built: the Plan view and brand kit that edit it.
PC-050 | Design System Pro: widen the LLM UI allowlist (motion, charts, rich text, command menu, drawer, toasts, tables, forms, maps, uploads) | Platform_Completion queue | Vibe | 1 Vibe Mode live | Completed | P0 |  | 2026-09-29 | framer-motion, recharts, tiptap, cmdk, vaul, sonner, tanstack-table, react-hook-form + zod, date-fns, maplibre, uppy: pinned, validated, repaired like today's allowlist. From the architecture plan. Done 2026-09-29: framer-motion, recharts, @tanstack/react-table, react-hook-form + zod, date-fns, sonner, cmdk, vaul pinned for React 18 in every generated web and admin app, allowed and explained to the page writer; the type-check cache rebuilds when they change. Deferred: tiptap (rich text), maplibre (maps) and uppy (uploads) - heavy, and each needs a backend or tiles; add with the feature that uses them.
PC-100 | A modern admin panel: redesign the generated admin console (dashboard with real metrics and charts, rich data tables, forms, filters, bulk actions, command menu) in the project's design direction | Platform_Completion queue | Both | 1 Vibe Mode live | Completed | P0 |  | 2026-09-29 | The admin console is one template for every project (21 of 27 admin layouts byte-identical on 2026-09-27). Keep every existing admin capability (roles manager, CRUD on every entity, auth) and its API wiring; model-written admin pages go through the same repair and fallback as the web app (PC-097, PC-098). Found in PC-098: the admin template shows invented figures ('99.98% system health', '< 24ms latency') - every number must come from the API or not be shown. Done 2026-09-29: an app shell (sidebar, top bar, Ctrl/Cmd+K command menu, phone drawer), a dashboard read only from the API, and a page per listable entity (server-sorted, searched and paginated table, bulk delete, CSV, create/edit drawer validated from the plan, related records picked by name, a map for coordinates); model pages with invented figures are refused. Found and fixed in the generated Python API: GET /orders answered 500 in every app with an Order entity, no foreign key could be written, and a declared created_at was required on create.
PC-101 | UI quality gate for ordinary prompts: every Vibe build is screenshotted and checked (layout, contrast, spacing, phone width, empty/loading/error states) before it is called done | Platform_Completion queue | Both | 1 Vibe Mode live | Completed | P1 |  | 2026-09-30 | PC-088's UI review covers packs only. Headless screenshots at phone and desktop widths of every surface; deterministic checks (contrast, overflow, broken images, console errors) always, a model review when a provider is set; a failing page is repaired or reported, never hidden. A fixed set of benchmark prompts (food delivery, clinic, store, SaaS, blog) is re-run so the UI is shown to improve and never regress. Seen in PC-099 for this gate to catch: in a preview served under a base path, a page's server-side API proxy route (/products) answered 503 'backend_unavailable' while the API itself answered 200; and the generated Expo app fails tsc on `process` (no Node types) in src/shared/api/client.ts. Seen in PC-050: a designed home page still showed invented trend figures ('+12.5% from last month') despite the rule against them (PC-100 now refuses those), and the preview console had a few static-resource 404s - PC-100 traced the ones it saw to screenshots taken on an app's raw port (a relative API path only resolves through the console) and one transient dev-server 404; check against a production build. Seen in PC-100: the proxy route reads BACKEND_INTERNAL_URL or NEXT_PUBLIC_API_URL, not the API_URL the preview sets, which is the 503 above; dev-mode HMR websockets fail through the console proxy; an app whose API has no sign-in routes still shows 'Sign in'. Seen in PC-102: the planner can declare a required <entity>_id for an entity it gives no API (a job posting's recruiter_id with no /recruiters), so no form can fill it, and an entity whose only create is nested (/job_postings/{id}/applications) gets no 'New' in the admin console. Done 2026-09-30: scripts/ui-check.mjs (every page, 390 and 1360 px: overflow, console, requests, images, contrast); every listed defect fixed, plus what the check found (previews without a base path, SSR crash with uploads, contrast, page warm-up). Benchmarks food/clinic/store/blog 0 failing pages. Runs on demand, not after every build; free-provider planning failures remain.
PC-102 | Rich text and file uploads in generated apps: a rich-text field type edited with tiptap and rendered safely, and attachment fields uploaded to storage (uppy) | Platform_Completion queue | Both | 1 Vibe Mode live | Completed | P1 |  | 2026-09-29 | Deferred from PC-050 and PC-100 because each needs more than a library. Rich text: a field type the planner can choose, stored as sanitized HTML (or Markdown), edited with tiptap in the admin console and rendered safely in the web and mobile apps. Uploads: attachment fields are a URL today and no backend (Python, Go, Node) has an upload endpoint or storage; needs a founder decision on storage (local disk on the API vs S3-compatible - MinIO locally, R2/S3 in production), then an upload endpoint with size/type limits in each backend and uppy in the console. Founder's decision 2026-09-29: Cloudflare R2 (dev and prod), AWS S3 as the production alternative, the local disk as the fallback; no MinIO. Done 2026-09-29 for the default Python backend and the web and admin apps: per-field rules from the requirement (planner or the field's name), content checked on the server, R2/S3/local chosen from the platform's .env (production needs keys only), Uppy with device, camera, web link and Google Drive / Dropbox / OneDrive / Box through a self-hosted Companion; proven in the preview and in a published production stack. Rich text moved to PC-104; Go and Node uploads to PC-105.
PC-104 | Rich text in generated apps: a rich_text field type the planner can choose, edited with tiptap and rendered safely | Platform_Completion queue | Both | 1 Vibe Mode live | Completed | P1 |  | 2026-09-29 | Split from PC-102. A field type the planner picks for long formatted content (descriptions, articles, notes); stored as HTML sanitized on the server (Python, Go and Node), edited with tiptap in the admin console and web forms, rendered with a second sanitizing pass in the web app and as plain text on mobile. Done 2026-09-29: rich_text type; nh3 / bluemonday / sanitize-html on every write; tiptap editor in web forms and the admin console; DOMPurify on display; plain words in tables and on mobile; the planner and the publication template use it, and a prompt that asks for formatting upgrades content fields deterministically.
PC-107 | A preview is ready only once its pages are compiled; benchmark projects removed | Platform_Completion queue | Both | 1 Vibe Mode live | Completed | P2 |  | 2026-09-30 | Left by PC-106: a page opened in the first minute of a preview, while the warm-up compiled routes, could meet a dev-server chunk error. And the PC-101 benchmark projects under bench-* test accounts are no longer needed. Done 2026-09-30: previews report ready after the warm-up; the real cause was the console proxy looking the preview up once per file (cached; control-plane connections kept); 21 benchmark projects deleted through the platform.
PC-106 | Planning survives a provider failing mid-answer, and the UI check runs after every preview | Platform_Completion queue | Both | 1 Vibe Mode live | Completed | P1 |  | 2026-09-30 | Left open by PC-101: builds failed when a free provider timed out or was rate-limited after its answer had started (the chain never switches mid-stream); the UI check ran only by hand; one task-tracker page failed with a Next chunk 404 that was not diagnosed. Done 2026-09-30: the planner starts again with the rest of the chain (and 413 fails over); the check runs after every preview and shows in the Studio; the 404 was the check racing the page warm-up.
PC-105 | File uploads in the Go and Node backends | Platform_Completion queue | Both | 1 Vibe Mode live | Completed | P1 |  | 2026-09-29 | Split from PC-102, which builds uploads for the default Python backend: the same /uploads and /files endpoints, the same per-field rules and content checks, and the same storage drivers (R2/S3/local) in Go and in Node (Express and Hono). Done 2026-09-29: both generate the Python contract (same checks, messages, settings, signed links); the generated Go, Express and Hono APIs each passed the 19 upload checks on disk and on S3, a Companion link import and the sign-in requirement.
PC-103 | Go and Node backends: relations writable and audit timestamps optional, as the Python backend now is | Platform_Completion queue | Both | 1 Vibe Mode live | Completed | P1 |  | 2026-09-29 | Found in PC-100 for the Python API (the default backend): no foreign key could be written (the model lacked it and inserts skipped it) and a declared created_at was required on create. The Go models have the same gap (type Order has no CustomerId); check the Node backend too, and run the admin console's create/edit against each. Done 2026-09-29: Go and Node read and write foreign keys and leave declared timestamps to the database; both generated servers created, read, updated and listed an order with its customer against Postgres. Found: the Node API failed tsc wherever it had accounts (fixed).
PC-108 | Consumer-grade UI for generated apps: detail, landing, list and empty states that read as a finished product, not an operator's tool | Platform_Completion queue | Both | 1 Vibe Mode live | Completed | P1 |  | 2026-09-30 | Seen in the PC-101 benchmark screenshots: a record's detail page offers an ID box, 'Copy ID', 'Export JSON' and prev/next buttons to visitors; the landing hero shows an empty image placeholder; public lists are admin-style tables with density toggles and CSV export; empty states are bare. The templates every build uses (model page design is optional) must look finished: cards and readable detail pages for visitors, the operator tools kept in the admin console. Proven with the UI check and screenshots on the benchmark prompts. Done 2026-09-30: card lists and reading views in the web app, operator pages kept in the admin app, no empty hero box; proven on the hiring portal and content hub with real records.
BP-AUTOFIX | Error detect -> fix -> verify -> retry loop | Platform_Buildout section 8 ('R-523') |  | Delivered | Completed |  | R-560 |  | R-560, R-561.
GA-01 | Portable AI start contract (AGENTS.md + adapters) | Tracker RND_Gap_Audit |  | Delivered | Completed |  |  |  | AGENTS.md, CLAUDE.md.
GA-02 | Work resume: PROJECT_STATE + CURRENT_TASK + handoff | Tracker RND_Gap_Audit |  | Delivered | Completed
GA-06 | doctor / bootstrap / status / handoff commands | Tracker RND_Gap_Audit |  | Delivered | Completed |  | R-551
GAP-OPENAPI | A worked OpenAPI contract example | V6_Review_and_Gap_Analysis section 3 |  | Delivered | Completed |  | R-260 |  | Every generated project ships openapi.json.
R-001 | Platform monorepo bootstrap | Execution_Tracker_v6 | Foundation | Delivered | Completed |  |  | 2026-09-06
R-002 | PostgreSQL + pgvector local bootstrap | Execution_Tracker_v6 | Data | Delivered | Completed |  |  | 2026-09-06
R-003 | Local Ollama Stage 0 bootstrap | Execution_Tracker_v6 | Models | Delivered | Completed |  |  | 2026-09-06
R-004 | Go control-plane foundation | Execution_Tracker_v6 | Backend | Delivered | Completed |  |  | 2026-09-06
R-005 | ModelProvider contract and registry | Execution_Tracker_v6 | Models | Delivered | Completed |  |  | 2026-09-06
R-006 | Loopback Ollama provider adapter | Execution_Tracker_v6 | Models | Delivered | Completed |  |  | 2026-09-06
R-007 | Balanced Model Gateway router | Execution_Tracker_v6 | Models | Delivered | Completed |  |  | 2026-09-06
R-008 | Cloud API-key provider adapters | Execution_Tracker_v6 | Models | Delivered | Completed |  |  | 2026-09-06
R-009 | Usage and cost accounting | Execution_Tracker_v6 | Models | Delivered | Completed |  |  | 2026-09-06
R-020 | Structured patch engine | Execution_Tracker_v6 | Code Editing | Delivered | Completed |  | R-237 |  | IR diff -> patch (R-237, R-246, R-584).
R-023 | Model gateway | Execution_Tracker_v6 | Models | Delivered | Completed |  | R-005 |  | Model gateway (R-005..R-009).
R-024 | Routing + fallback | Execution_Tracker_v6 | Models | Delivered | Completed |  | R-221 |  | Routing, fallback, circuit breaker (R-007, R-221, R-223).
R-026 | PostgreSQL | Execution_Tracker_v6 | Data | Delivered | Completed |  | R-002 |  | PostgreSQL.
R-031 | Ephemeral Linux sandbox | Execution_Tracker_v6 | Sandbox | Delivered | Completed |  | R-486 |  | Sandbox drivers (R-486..R-489).
R-032 | Secret broker | Execution_Tracker_v6 | Sandbox | Delivered | Completed |  | R-503 |  | Encrypted per-project secrets.
R-033 | Application-IR browser preview | Execution_Tracker_v6 | Preview | Delivered | Completed |  | R-421 |  | Studio preview.
R-034 | Web/Admin live preview | Execution_Tracker_v6 | Preview | Delivered | Completed |  | R-500 |  | Multi-process preview.
R-037 | Unit + integration baseline | Execution_Tracker_v6 | Testing | Delivered | Completed |  |  |  | Offline test suite runs in every gate.
R-038 | Regression gate | Execution_Tracker_v6 | Testing | Delivered | Completed |  |  |  | scripts/verify.sh gate and CI.
R-041 | SAST + dependency scanning | Execution_Tracker_v6 | Security | Delivered | Completed |  | R-508 |  | Plus scripts/security-quick.sh.
R-045 | Usage ledger | Execution_Tracker_v6 | Billing | Delivered | Completed |  | R-472 |  | Credit ledger with real cost debiting.
R-048 | Web/backend deployment | Execution_Tracker_v6 | Deployment | Delivered | Completed - needs live proof | P0 | PC-008 |  | R-509 publish.
R-066 | BYOK | Execution_Tracker_v6 | Billing | Delivered | Completed |  | R-504 |  | BYOK.
R-067 | Auto-recovery agent | Execution_Tracker_v6 | Recovery | Delivered | Completed |  | R-560 |  | Hybrid repair loop (R-466, R-560).
R-074 | Backend stack profiles | Execution_Tracker_v6 | Multi-stack | Delivered | Completed |  | R-565 |  | Python, Go, Node backends (R-229, R-230, R-517, R-565).
R-078 | React Native target (GA/beta by team capacity) | Execution_Tracker_v6 | Mobile | Delivered | Completed |  | R-514 |  | React Native (Expo) is a default for app requests (D-5).
R-112 | Framework recommendation engine | Execution_Tracker_v6 | Framework Strategy | Delivered | Completed |  | R-559 |  | resolve_stack recommends and substitutes with a reason.
R-113 | Auto / Recommended project mode | Execution_Tracker_v6 | Framework Strategy | Delivered | Completed |  | R-559
R-114 | Manual framework override | Execution_Tracker_v6 | Framework Strategy | Delivered | Completed |  | R-565
R-115 | Framework adapter contract | Execution_Tracker_v6 | Architecture | Delivered | Completed |  | R-559 |  | AdapterRegistry.
R-117 | Next.js web + admin default | Execution_Tracker_v6 | Web/Admin | Delivered | Completed |  | R-227
R-121 | Platform modular monorepo | Execution_Tracker_v6 | Git/Repository | Delivered | Completed |  | R-001
R-122 | One Git repo per customer project | Execution_Tracker_v6 | Git/Repository | Delivered | Completed |  | R-228
R-123 | Customer project monorepo default | Execution_Tracker_v6 | Git/Repository | Delivered | Completed |  | R-554
R-128 | Cross-language monorepo orchestration | Execution_Tracker_v6 | Git/Repository | Delivered | Completed |  |  |  | Taskfile.yml orchestrates Go, Python and Node.
R-133 | Atomic cross-platform change set | Execution_Tracker_v6 | Change Safety | Delivered | Completed |  | R-563 |  | Ecosystem edits (R-563, R-584).
R-138 | Canonical generated project root | Execution_Tracker_v6 | Architecture | Delivered | Completed |  | R-232
R-139 | Root task commands | Execution_Tracker_v6 | Developer Experience | Delivered | Completed |  | R-552 |  | Generated README and run plan.
R-142 | React Native TypeScript template | Execution_Tracker_v6 | Templates | Delivered | Completed |  | R-514
R-148 | Next.js public web template | Execution_Tracker_v6 | Templates | Delivered | Completed |  | R-227
R-149 | Next.js admin template | Execution_Tracker_v6 | Templates | Delivered | Completed |  | R-542
R-150 | Go backend standard template | Execution_Tracker_v6 | Templates | Delivered | Completed |  | R-230
R-151 | Python backend standard template | Execution_Tracker_v6 | Templates | Delivered | Completed |  | R-229
R-153 | Template manifest + maturity | Execution_Tracker_v6 | Templates | Delivered | Completed |  | R-519
R-155 | Go control plane modular monolith | Execution_Tracker_v6 | Platform Architecture | Delivered | Completed |  | R-004
R-156 | Python agent engine boundary | Execution_Tracker_v6 | Platform Architecture | Delivered | Completed |  | R-472
R-158 | Unified PR pipeline | Execution_Tracker_v6 | CI/CD | Delivered | Completed |  |  |  | .github/workflows/ci.yml runs scripts/verify.sh.
R-171 | SandboxProvider abstraction | Execution_Tracker_v6 | Runtime | Delivered | Completed |  | R-486
R-172 | Managed Linux sandbox adapter | Execution_Tracker_v6 | Runtime | Delivered | Completed |  | R-486
R-173 | Capability resolver | Execution_Tracker_v6 | Runtime | Delivered | Completed |  | R-490
R-181 | Platform event protocol | Execution_Tracker_v6 | Realtime | Delivered | Completed |  | R-484 |  | SSE build streaming.
R-195 | Second sandbox provider adapter | Execution_Tracker_v6 | Runtime | Delivered | Completed |  | R-487
R-220 | Cloud streaming (Server-Sent Events) | Execution_Tracker_v6 | Models | Delivered | Completed |  |  | 2026-09-06
R-221 | Cross-provider fallback and circuit breaking | Execution_Tracker_v6 | Models | Delivered | Completed |  |  | 2026-09-06
R-222 | Platform console slice (model & cost overview) | Execution_Tracker_v6 | Console | Delivered | Completed |  |  | 2026-09-06
R-223 | Env-driven fallback & circuit-breaker wiring | Execution_Tracker_v6 | Models | Delivered | Completed |  |  | 2026-09-06
R-225 | Application IR v1 (framework-neutral) | Execution_Tracker_v6 | Product | Delivered | Completed |  |  | 2026-09-06
R-226 | Framework adapter contract + file-set model | Execution_Tracker_v6 | Product | Delivered | Completed |  |  | 2026-09-06
R-227 | Next.js web code adapter (IR -> app) | Execution_Tracker_v6 | Product | Delivered | Completed |  |  | 2026-09-06
R-228 | Git service (materialize project -> owned repo) | Execution_Tracker_v6 | Product | Delivered | Completed |  |  | 2026-09-06
R-229 | Python (FastAPI) backend adapter (IR -> backend) | Execution_Tracker_v6 | Product | Delivered | Completed |  |  | 2026-09-06
R-230 | Go backend adapter (IR -> Go net/http service) | Execution_Tracker_v6 | Product | Delivered | Completed |  |  | 2026-09-06
R-231 | IR validator/normalizer + example fixtures | Execution_Tracker_v6 | Product | Delivered | Completed |  |  | 2026-09-06
R-232 | Customer project assembler (IR -> monorepo) | Execution_Tracker_v6 | Product | Delivered | Completed |  |  | 2026-09-06
R-233 | Runtime & deploy provider layer (Tier 0-3) | Execution_Tracker_v6 | Runtime | Delivered | Completed |  |  | 2026-09-07
R-234 | Tier switch + cloud provider drivers | Execution_Tracker_v6 | Runtime | Delivered | Completed |  |  | 2026-09-07
R-235 | Verifiable-engineering verify plans (per-target gate ladders) | Execution_Tracker_v6 | Verify | Delivered | Completed |  |  | 2026-09-07
R-236 | Expand model-provider catalog + custom OpenAI-compatible providers | Execution_Tracker_v6 | Model Fabric | Delivered | Completed |  |  | 2026-09-07
R-237 | IR-diff -> patch-apply edit loop (edit an existing app) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-07
R-238 | PostgreSQL schema/migration generation from the Application IR | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-07
R-239 | Data-access/repository layer for the generated backends | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-07
R-240 | Route wiring: handlers call the repositories (real CRUD) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-07
R-241 | Authentication guards from the IR (enforce endpoint auth flag) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-07
R-242 | Real JWT verification in the generated auth guard (HS256) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-07
R-243 | Per-endpoint role enforcement (IR required_roles -> 403) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-07
R-244 | Sub-collection route wiring (parent-scoped lists) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-07
R-245 | Combined project-plan surface (preview + verify + deploy per app) | Execution_Tracker_v6 | Runtime | Delivered | Completed |  |  | 2026-09-07
R-246 | Richer edit-loop diffs (hunk-level + rename detection) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-07
R-247 | Render the project plan and unified edit patch in the static console | Execution_Tracker_v6 | Console | Delivered | Completed |  |  | 2026-09-08
R-248 | Application IR fixtures + honest migrations/0002_seed.sql | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-249 | IR indexes + unique constraints in the generated PostgreSQL schema | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-250 | Richer field validation (max_length + enum) into schema + FastAPI models | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-251 | Field validation for Go + numeric min/max (all schema/model targets) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-252 | Enforce go-playground validation in the generated Go create handlers | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-253 | Wire PATCH/update handlers with validation in Go and FastAPI backends | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-254 | Field-level validation error bodies (structured JSON errors instead of flat string) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-255 | Query parameter pagination (limit & offset) for LIST and LIST_BY in Go and FastAPI backends | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-256 | Wire PUT handlers (full-replace update) with validation in Go and FastAPI backends | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-257 | Full-Stack Connectivity: Next.js Typed API Client (`lib/api.ts`) & Backend CORS Middleware | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-258 | Query Parameter Sorting (`sort` & `order=asc¦desc`) on LIST Endpoints with SQL Injection Whitelist Protection | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-259 | Total Count Queries & `X-Total-Count` Header on LIST Endpoints | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-260 | OpenAPI 3.1 Specification Generation from Application IR | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-261 | Full-Text / Keyword Search Filtering on LIST Endpoints | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-262 | React Data-Fetching & Mutation Hooks Generator (apps/web/lib/hooks.ts) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-263 | Interactive Screen Component Generator with Real Data Binding (apps/web/app/<screen>/page.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-264 | Field-Level Validation & Error Feedback in Generated Next.js Forms | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-265 | Subcollection Navigation & Master-Detail Views in Generated Screens | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-266 | Update/Edit Mode in Generated Next.js Forms & Collection Screen Edit Actions | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-267 | Foreign-Key Relation Selectors & Parent Auto-Population in Generated Next.js Forms | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-268 | Subcollection Child Item Deletion & Mutation Feedback in Master-Detail Views | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-269 | Page Size Selector & Contextual Empty State CTAs in Generated Next.js Screens | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-270 | Bulk Selection & Batch Deletion in Generated Next.js Collection Screens | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-271 | CSV Data Export & Bulk Export in Generated Next.js Collection Screens | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-272 | Deep-Linking & Entity Lifecycle in Next.js Detail Screens | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-273 | Global Responsive Navigation Shell & Header Navbar in Generated Next.js Web App | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-274 | Form Screen Post-Submit Contextual CTAs, Record Navigation & Cancel Actions | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-08
R-275 | Rich App Dashboard Overview Page in Generated Next.js Web App | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-09
R-276 | Record Selector Dropdown, Prev/Next Record Navigation & Deep-Link Sync in Generated Next.js Detail Screens | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-09
R-277 | Form Screen Dirty State Tracking, Unsaved Changes Guard & Reset Confirmation in Generated Next.js Forms | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-09
R-278 | Collection Screen Boolean & Enum Field Filtering, Segmented Pill Controls & Filter Empty States in Generated Next.js Web App | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-09
R-279 | Global Notification Toast System & Action Feedback in Generated Next.js Web App | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-09
R-280 | Deep-Linked Collection List State + Debounced, Race-Safe Search in Generated Next.js Web App | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-09
R-281 | Pagination, Sort & Search Controls on Subcollection Master-Detail Lists in Generated Next.js Web App | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-09
R-282 | Server-Side Boolean/Enum Field Filters on Top-Level LIST Endpoints (Go + FastAPI + OpenAPI) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-09
R-283 | Wire Generated Next.js Collection Filters to Server-Side Query Parameters | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-09
R-284 | Server-Side Boolean/Enum Field Filters on FK-Scoped LIST_BY Endpoints | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-09
R-285 | Server-Side Subcollection Filter Wiring in Generated Next.js Screens | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-09
R-286 | Race-Safe Generated Subcollection Refetches | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-09
R-287 | Race-Safe Generated Detail Refetches in Generated Next.js Web App | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-288 | Deduplicated In-Flight Generated Mutation Requests in Generated Next.js Web App | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-289 | Debounced Live Subcollection Search in Generated Next.js Web App | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-290 | Optimistic Delete with Rollback in the Generated Collection Screen | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-291 | Optimistic Subcollection Child Delete with Rollback in Generated Next.js Screens | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-292 | Loading Skeletons for Generated Next.js Screens | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-293 | Loading Skeletons for Form Initial Load & Detail Record-Selector List | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-294 | Generated Next.js App Router Resilience: Error Boundary, Global Error, Not-Found & Loading Fallback | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-295 | Consistent Error + Retry Affordance Across Every Generated Fetch State | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-296 | Generated Web App Accessibility Pass: Semantic ARIA Roles, Live Regions, Table Sort State & Accessible Controls | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-297 | Generated Collection Keyboard Navigation & Shortcuts | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-298 | Generated Detail Screen Keyboard Navigation & Shortcuts | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-299 | Generated Form Screen Keyboard Shortcuts: Cmd/Ctrl+Enter, Cmd/Ctrl+S & Escape Cancel | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-300 | Generated Form Screen Input Constraints, Native HTML Validation & Live Character Counters | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-301 | Generated Web Search Input Clear Affordances & Form Screen First-Field AutoFocus | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-302 | Generated Collection Screen Boolean & Enum Visual Status Badges & Detail Screen One-Click Copy-to-Clipboard Affordances | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-303 | Generated Dashboard Overview Interactive Entity Links, Operational Health Badge & Metrics Chips | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-304 | Generated Accessible Confirmation Dialog — Replace window.confirm() with ConfirmDialog Component | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-305 | Generated Keyboard Shortcuts Help Modal & Global Discovery Affordance | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-306 | Generated Accessible Breadcrumb Navigation Component & Screen Hierarchy | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-307 | Generated Accessible EmptyState Component & Screen Zero-State Integrations | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-308 | Generated Collection Screen JSON Data Export & Bulk Selection Export Controls | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-309 | Generated Accessible Reusable Pagination Component (components/pagination.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-310 | Generated Accessible Reusable Tabs Component (components/tabs.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-311 | Generated Collection Table Display Density Toggle (Compact, Comfortable, Spacious) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-312 | Generated Accessible Reusable Badge & Status Pill Component (components/badge.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-313 | Generated Collection Table Column Visibility Dropdown / Selector Controls | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-314 | Generated Accessible Reusable Tooltip Component (components/tooltip.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-315 | Generated Accessible Reusable Card Component (components/card.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-316 | Generated Accessible Reusable Alert & Notification Component (components/alert.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-317 | Generated Accessible Reusable Skeleton Loader Component (components/skeleton.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-318 | Generated Accessible Reusable Drawer / Sheet Component (components/drawer.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-319 | Generated Accessible Reusable Avatar Component (components/avatar.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-320 | Generated Accessible Reusable Toggle Switch Component (components/toggle.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-321 | Generated Accessible Reusable Accordion Component (components/accordion.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-322 | Generated Accessible Reusable Dropdown Menu Component (components/dropdown-menu.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-323 | Generated Accessible Reusable Popover Component (components/popover.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-324 | Generated Design Tokens & CSS Custom Properties Theming Engine (styles/tokens.css) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-325 | Generated Theme Switcher / Mode Toggle Component (components/theme-toggle.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-326 | Generated Accessible Reusable Dialog / Modal Component (components/dialog.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-327 | Generated Accessible Reusable Form Controls & Input Primitives (components/form-controls.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-10
R-328 | Generated Accessible Reusable Date Picker Component (components/date-picker.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-329 | Generated Accessible Reusable Data Grid / Table Component (components/data-grid.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-330 | Generated Accessible Command Palette / Search Menu Component (components/command-palette.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-331 | Generated Accessible Reusable Slider & Range Component (components/slider.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-332 | Generated Accessible Reusable Progress & Spinner Component (components/progress.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-333 | Generated Accessible Reusable Rating & Review Component (components/rating.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-334 | Generated Accessible Reusable Stepper / Multi-step Wizard Component (components/stepper.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-335 | Generated Accessible Reusable File Upload / Dropzone Component (components/file-upload.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-336 | Generated Accessible Reusable Timeline / Activity Feed Component (components/timeline.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-337 | Generated Accessible Futuristic Reusable Stat & Metric KPI Card Component (components/stat-card.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-338 | Generated Accessible Reusable Hierarchical Tree View Component (components/tree-view.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-339 | Generated Accessible Futuristic Reusable Tag & Chip Input Tokenizer Component (components/tag-input.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-340 | Generated Accessible Futuristic Reusable Code Block & Syntax Presentation Component (components/code-block.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-341 | Generated Accessible Futuristic Reusable Radial Gauge & Activity Rings Component (components/radial-gauge.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed
R-342 | Generated Accessible Futuristic Reusable Segmented Control & Mode Switcher Component (components/segmented-control.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-343 | Generated Accessible Futuristic Reusable Carousel & Slider Showcase Component (components/carousel.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-344 | Generated Accessible Futuristic Reusable Resizable Panels & Splitter Component (components/resizable.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-345 | Generated Accessible Futuristic Reusable Color Picker & Palette Swatch Component (components/color-picker.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-346 | Generated Accessible Futuristic Reusable PIN & OTP Code Input Component (components/pin-input.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-347 | Generated Accessible Futuristic Reusable Speed Dial & Floating Action Button Component (components/speed-dial.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-348 | Generated Accessible Futuristic Reusable Context Menu Suite (components/context-menu.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-349 | Generated Accessible Futuristic Reusable Hover Card Suite (components/hover-card.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-350 | Generated Accessible Futuristic Reusable Scroll Area Suite (components/scroll-area.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-351 | Generated Accessible Futuristic Reusable Collapsible Component (components/collapsible.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-352 | Generated Accessible Futuristic Reusable Aspect Ratio Component (components/aspect-ratio.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-353 | Generated Accessible Futuristic Reusable Separator Component (components/separator.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-354 | Generated Accessible Futuristic Reusable Keyboard Keycap Component (components/kbd.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-355 | Generated Accessible Futuristic Reusable Radio Group Suite (components/radio-group.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-356 | Generated Accessible Futuristic Reusable Checkbox & Checkbox Group Primitive (components/checkbox.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-357 | Generated Accessible Futuristic Reusable Announcement Banner & Callout Suite (components/banner.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-358 | Generated Accessible Futuristic Reusable Searchable Combobox & Autocomplete Primitive (components/combobox.tsx) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-359 | Generated Accessible Futuristic Reusable Mobile Bottom Navigation Bar Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-360 | Accessible Futuristic Reusable Number Input & Numeric Stepper Primitive | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-361 | Accessible Futuristic Reusable Notification Center & Notification List Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-362 | Accessible Futuristic Reusable Sidebar & Side Navigation Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-363 | Accessible Futuristic Reusable Tour & Onboarding Spotlight Guide Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-364 | Accessible Futuristic Reusable Transfer / Dual Listbox Picker Primitive | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-365 | Accessible Futuristic Reusable Markdown & Rich Content Editor Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-366 | Accessible Futuristic Reusable Calendar & Event Scheduler Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-367 | Accessible Futuristic Reusable Kanban Board & Task Flow Matrix Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-368 | Accessible Futuristic High-Performance Infinite Virtual List & Windowed Scroller Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-369 | Accessible Futuristic Reusable Query Filter Builder & Dynamic Rule Bar Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-370 | Accessible Futuristic Reusable Data Visualization & SVG Chart Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-371 | Accessible Futuristic Reusable Time Picker & Time Range Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-372 | Accessible Futuristic Reusable Digital Signature Pad & Drawing Canvas Primitive | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-373 | Accessible Futuristic Reusable Diff Viewer & Code/Text Comparison Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-374 | Accessible Futuristic Reusable Org Chart & Hierarchy Flow Diagram Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-375 | Accessible Futuristic Reusable Heatmap & Activity Contribution Matrix Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-376 | Accessible Futuristic Reusable Media Player Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-377 | Accessible Futuristic Reusable Pivot Table & Cross-Tabulation Matrix Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-378 | Accessible Futuristic Reusable Image Cropper & Canvas Mask Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-379 | Accessible Futuristic Reusable Gantt Chart & Project Roadmap Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-380 | Accessible Futuristic Reusable Flowchart & Node-Based Workflow Canvas Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-381 | Accessible Futuristic Reusable Terminal & Command Console Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-382 | Accessible Futuristic Reusable QR Code & Barcode Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-383 | Accessible Futuristic Reusable Spreadsheet & Inline-Editable Data Sheet Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-384 | Accessible Futuristic Reusable Chat & Real-Time Messaging Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-385 | Accessible Futuristic Reusable Audio & Voice Recorder Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-386 | Accessible Futuristic Reusable File Explorer & Storage Browser Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-387 | Accessible Futuristic Reusable Interactive Geo Map & Location Pinpoint Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-388 | Accessible Futuristic Reusable PDF & Document Viewer Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-389 | Accessible Futuristic Reusable Audio Player & Frequency Equalizer Suite | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-390 | Accessible Futuristic Reusable Video Player & Streaming Theater Suite (`components/video-player.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-391 | Accessible Futuristic Reusable Whiteboard & Collaborative Canvas Suite (`components/whiteboard.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-392 | Accessible Futuristic Reusable Code Diff Editor & 3-Way Merge Conflict Resolver Suite (`components/merge-editor.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-393 | Accessible Futuristic Reusable Interactive JSON Viewer & Schema Tree Inspector Suite (`components/json-viewer.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-394 | Accessible Futuristic Reusable Image Gallery & Masonry Lightbox Suite (`components/image-gallery.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-395 | Accessible Futuristic Reusable Network Graph & Topology Map Suite (`components/network-graph.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-11
R-396 | Accessible Futuristic Reusable Live Log Viewer & Event Stream Inspector Suite (`components/log-viewer.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-397 | Accessible Futuristic Reusable Mind Map & Concept Tree Suite (`components/mind-map.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-398 | Accessible Futuristic Reusable Audio Waveform & Spectrum Visualizer Suite (`components/audio-visualizer.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-399 | Accessible Futuristic Reusable Particle Network & Interactive Constellation Canvas Suite (`components/particle-network.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-400 | Accessible Futuristic Reusable Before/After Image Comparison Slider Suite (`components/image-comparison.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-401 | Accessible Futuristic Reusable Countdown Timer, Stopwatch & Live Clock Suite (`components/countdown.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-402 | Accessible Futuristic Reusable Cookie Consent & Preferences Manager Suite (`components/cookie-consent.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-403 | Accessible Futuristic Reusable Password Strength Meter & Requirements Suite (`components/password-strength.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-404 | Accessible Futuristic Reusable Masked / Pattern Input Suite (`components/masked-input.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-405 | Accessible Futuristic Reusable Mention / @-Autocomplete Textarea Suite (`components/mention.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-406 | Accessible Futuristic Reusable Marquee / Ticker Suite (`components/marquee.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-407 | Accessible Futuristic Reusable Credit Card Payment Field Suite (`components/credit-card.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-408 | Accessible Futuristic Reusable Color Contrast Checker Suite (`components/color-contrast.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-409 | Accessible Futuristic Reusable Currency / Money Input Suite (`components/currency-input.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-410 | Accessible Futuristic Reusable Password Generator Suite (`components/password-generator.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-411 | Accessible Futuristic Reusable Slug / URL Input Suite (`components/slug-input.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-412 | Accessible Futuristic Reusable Character & Word Counter Textarea Suite (`components/character-counter.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-413 | Accessible Futuristic Reusable Copy-to-Clipboard Button Suite (`components/copy-button.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-414 | Accessible Futuristic Reusable Duration Input Suite (`components/duration-input.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-415 | Accessible Futuristic Reusable Phone Number Input Suite (`components/phone-input.tsx`) | Execution_Tracker_v6 | Builder | Delivered | Completed |  |  | 2026-09-12
R-416 | Prompt -> Application IR intake agent (`intake/nl_to_ir.py`) | Execution_Tracker_v6 | Front Door | Delivered | Completed |  |  | 2026-09-13
R-417 | Prompt -> generated app repo (chat-to-create front door, brick 2) | Execution_Tracker_v6 | Front Door | Delivered | Completed |  |  | 2026-09-13
R-418 | Chat studio web UI (chat-to-create front door, brick 3) | Execution_Tracker_v6 | Front Door | Delivered | Completed |  |  | 2026-09-13
R-419 | Turnkey local run for a generated app (chat-to-create front door, brick 4) | Execution_Tracker_v6 | Front Door | Delivered | Completed |  |  | 2026-09-13
R-420 | SQL-safe generated PostgreSQL identifiers and FK dependency order | Execution_Tracker_v6 | Codegen / Preview | Delivered | Completed |  |  | 2026-09-13
R-421 | Managed live generated-app preview inside the local Studio | Execution_Tracker_v6 | Codegen / Preview | Delivered | Completed |  |  | 2026-09-13
R-422 | Collision-free Studio preview ports + status/stop/restart controls | Execution_Tracker_v6 | Codegen / Preview | Delivered | Completed |  |  | 2026-09-13
R-423 | Studio build history + re-preview a recent build | Execution_Tracker_v6 | Codegen / Preview | Delivered | Completed |  |  | 2026-09-13
R-424 | Live preview status — liveness-aware status + Studio polling | Execution_Tracker_v6 | Codegen / Preview | Delivered | Completed |  |  | 2026-09-13
R-425 | Per-build repo actions — copy path + open folder | Execution_Tracker_v6 | Codegen / Preview | Delivered | Completed |  |  | 2026-09-13
R-426 | Remove a build from the Studio history | Execution_Tracker_v6 | Codegen / Preview | Delivered | Completed |  |  | 2026-09-13
R-427 | Fix malformed single-brace inline styles in generated Next.js screens | Execution_Tracker_v6 | Codegen / Preview | Delivered | Completed |  |  | 2026-09-13
R-428 | Generated web app compiles — opt-in TypeScript typecheck gate + fix the bugs it reveals | Execution_Tracker_v6 | Codegen / Preview | Delivered | Completed |  |  | 2026-09-13
R-429 | Generated web app passes strict `tsc --noEmit` — component-library type cleanup | Execution_Tracker_v6 | Codegen / Preview | Delivered | Completed |  |  | 2026-09-13
R-430 | Ecosystem Scope Compiler — deterministic domain classification + multi-app scope proposal | Execution_Tracker_v6 | Ecosystem | Delivered | Completed |  |  | 2026-09-13
R-431 | Scope → Application IRs — materialize a multi-app ecosystem from one prompt | Execution_Tracker_v6 | Ecosystem | Delivered | Completed |  |  | 2026-09-13
R-432 | Opt-in model refinement for tailored ecosystems outside curated domains | Execution_Tracker_v6 | Ecosystem | Delivered | Completed |  |  | 2026-09-13
R-433 | Surface-specific ecosystem data and capability scoping | Execution_Tracker_v6 | Ecosystem | Delivered | Completed |  |  | 2026-09-13
R-434 | Versioned baseline Solution Pack registry | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-14
R-435 | Exact-compatible Solution Pack recommendations in ecosystem planning | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-14
R-436 | Pinned declarative Solution Pack customization manifests | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-14
R-437 | Deterministic Solution Pack configuration application | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-14
R-438 | Task Contract: R-438 — Bounded Typed Solution Pack AI-Delta Proposal Schema & Local ModelProvider Boundary | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-14
R-439 | Safely Apply Validated AI-Delta Proposals to Application IR | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-14
R-440 | Standard AI Task Contract: R-440 | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-14
R-441 | Live Studio integration and UI controls for Solution Pack selection and modification | Execution_Tracker_v6 | Studio | Delivered | Completed |  |  | 2026-09-14
R-442 | Studio AI-delta feature modification controls above Solution Packs | Execution_Tracker_v6 | Studio | Delivered | Completed |  |  | 2026-09-14
R-443 | Solution Pack Packaging, Verification, and Export CLI | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-14
R-444 | Task Contract: R-444 — Solution Pack Multi-Surface Ecosystem Pack Synthesis | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-14
R-445 | Solution Pack Ecosystem Pack Registry Integration, Catalog Discovery, and Studio Multi-Surface Selection | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-14
R-446 | Solution Pack Ecosystem Studio Live Multi-Surface Preview and Process Orchestration | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-14
R-447 | Solution Pack Ecosystem Multi-Surface Cross-App Auth and Unified State Binding | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-14
R-448 | Solution Pack Ecosystem Cross-Surface Webhook and Event Bridge | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-14
R-449 | Solution Pack Ecosystem Cross-Surface Telemetry, Audit Trails, and Distributed Tracing | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-14
R-450 | Solution Pack Ecosystem Multi-Surface Export, Deployment Manifest, and Live Gateway Orchestration | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-14
R-451 | Solution Pack Ecosystem Cross-Surface Data Sync, Conflict Resolution, and Offline-First Sync Protocol | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-14
R-452 | Solution Pack Ecosystem Multi-Surface CI/CD Workflow & GitHub Actions Orchestration | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-14
R-453 | Solution Pack Ecosystem Comprehensive Multi-Surface Health Check, Smoke Testing, and Canary Verification | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-15
R-454 | Solution Pack Ecosystem Multi-Surface Disaster Recovery, Snapshot Backup, and Rollback Orchestration | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-15
R-455 | Solution Pack Ecosystem Multi-Surface Capacity Planning, Resource Quotas, and Unit Economics Budgeting | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-15
R-456 | Solution Pack Ecosystem Multi-Surface Alerting, Incident Runbooks, and Escalation Policies | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-15
R-457 | Solution Pack Ecosystem Multi-Surface SLA, SLO, and Error Budget Contracts | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-15
R-458 | Solution Pack Ecosystem Multi-Surface Governance, Compliance Policy, and Audit Evidence Contracts | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-15
R-459 | Solution Pack Ecosystem Multi-Surface Documentation, Architecture Runbooks, and OpenAPI Aggregator Contracts | Execution_Tracker_v6 | Solution Packs | Delivered | Completed |  |  | 2026-09-15
R-460 | Next.js Codegen End-to-End Route Handler Synthesis and Interactive CRUD Form Submission | Execution_Tracker_v6 | Codegen / Preview | Delivered | Completed |  |  | 2026-09-15
R-461 | Full-Stack Production Authentication Engine | Execution_Tracker_v6 | Codegen / Auth | Delivered | Completed |  |  | 2026-09-16
R-462 | Generative LLM-Powered UI Synthesis Engine with Deterministic Fallback | Execution_Tracker_v6 | Codegen / Generative UI | Delivered | Completed |  |  | 2026-09-16 | Status was blank in the tracker; it is in CHANGELOG.
R-463 | Auth Lifecycle Hardening, Unterminated Regexp Literal Webpack Fix & Forgot Password Workflow. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-16
R-464 | Full-Stack Platform Feature Completeness (4 Phases). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-16
R-465 | Grounded Hybrid UI Synthesis — the first brick of the founder-approved HYBRID generation engine: an LLM write… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-17
R-466 | Compile-Level Repair for LLM-Written UI + Rate-Limit-Aware Pacing — the second brick of the hybrid engine, dr… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-17
R-467 | Studio File Browser + Hybrid UI Toggle — wiring the R-465/R-466 hybrid engine into the product UI. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-17
R-468 | Multi-turn chat / "continue editing this app" in the Studio — every /api/build call used to be a fresh, state… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-17
R-469 | Control-plane foundation — users, auth, plans, credits. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-17
R-470 | Real Next.js console-web, wired to R-469's auth API. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-17
R-471 | Fix dev-mode hydration bug + add full name to registration. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-17
R-472 | Bridge the control-plane's Job API to the agent-engine — real credit debiting. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-18
R-473 | Studio v1 in the console — build an app from the product, not curl. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-18
R-474 | File browser in the console Studio — see what a build actually produced. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-18
R-475 | Studio visual foundation. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-476 | Backend — multi-turn edit bridge. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-477 | Console — chat UI. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-478 | Backend — live preview proxy (local-only). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-479 | Console — live preview UI. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-480 | Backend — Problems/compile-report support. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-481 | Tabbed workspace — the SEVENTH AND FINAL task of the founder-approved 7-task Phase D roadmap (R-475–R-481). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-482 | Model Provider settings UI. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-483 | Fix — dynamic-route slug collision & duplicate FK identifier in the edit-delta path. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-484 | Backend — real-time build streaming (SSE). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-485 | Console — streaming build UI. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-486 | Runtime — real sandbox lifecycle contract + E2B driver. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-487 | Runtime — real Vercel Sandbox driver. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-488 | Runtime — real Daytona driver. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-489 | Runtime — free, self-hosted gVisor sandbox driver. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-490 | Runtime — sandbox provider-selection surface. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-491 | Console — UI foundation (Tailwind v4 + shadcn/ui + Geist, dark-first tokens). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-492 | Console — auth screens + app shell (nav, user menu, skip link, branded 404, real dashboard). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-493 | Console — Studio core (chat rail + workspace shell on shadcn primitives and Lucide). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-494 | Console — Studio tabs (Preview chrome, Files tree, Code viewer, Problems on shadcn Tabs + Lucide). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-495 | Console — Settings + Fabric (provider cards, theme switcher, cost overview) and the legacy CSS sweep. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-496 | Console — motion, states & polish (loading/error states, streamed provider cards, OG/Twitter meta with a gene… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-497 | Console — Lovable-grade pass (prompt-first home, Studio ?prompt= auto-start, prose replies + follow-up chips,… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-498 | Platform buildout plan (15 specs) + single-command local runtime (scripts/omnistack.sh). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-19
R-499 | Projects & Workspaces Persistence (F-01-projects spec). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-20
R-500 | Multi-Process Preview & Diagnostics Service (F-02-preview spec). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-20
R-501 | Code ownership — download, connect GitHub, push (F-03-git spec). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-20
R-502 | Skills engine — custom instructions & domain templates (F-04-skills spec). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-20
R-503 | Secrets — encrypted per-project configuration (F-05-secrets spec). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-20
R-504 | AI — model configuration (BYOK) and usage per project/account (F-06-ai-usage spec). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-20
R-505 | SEO & AI search (F-07-seo spec). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-20
R-506 | Logs & live chat streaming (F-08-logs-chat spec). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-20
R-507 | Database explorer & SQL editor (F-09-database spec). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-20
R-508 | Security scanning & automated tests (F-10-security-tests spec). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-20
R-509 | Publish v1: GitHub -> Vercel / Netlify (G-01-publish spec). | CHANGELOG |  | Delivered | Completed - needs live proof | P0 | PC-008 | 2026-09-20 | Built and tested offline; prove it with a real account.
R-510 | Custom domain: bring your own (G-02-domains spec). | CHANGELOG |  | Delivered | Completed - needs live proof | P0 | PC-008 | 2026-09-20 | Built and tested offline; prove it with a real account.
R-511 | Connectors v1 (G-03-connectors spec). | CHANGELOG |  | Delivered | Completed - needs live proof | P0 | PC-013 | 2026-09-20 | Built and tested offline; prove it with a real account.
R-512 | Payment Gateways in Generated Apps — Stripe & Razorpay (G-04-payments spec). | CHANGELOG |  | Delivered | Completed - needs live proof | P0 | R-567 | 2026-09-20 | Built and tested offline; prove it with a real account.
R-513 | Analytics for published apps (G-05-analytics spec). | CHANGELOG |  | Delivered | Completed - needs live proof | P0 | PC-015 | 2026-09-20 | Built and tested offline; prove it with a real account.
R-514 | Mobile (React Native / Expo) Framework Adapter (R_&_D/OmniStackAI_Implementation_Brief_v6.md Section 37 & 6.4… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-21
R-515 | Team / Org model — multi-member workspaces & shared projects (R_&_D/OmniStackAI_Implementation_Brief_v6.md Se… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-21
R-516 | Email feature — SMTP / Resend integration in generated apps. | CHANGELOG |  | Delivered | Completed - needs live proof | P0 | PC-012 | 2026-09-21 | Built and tested offline; prove it with a real account.
R-517 | Node.js backend codegen — Express/Hono alongside Python/Go. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-21
R-518 | T-0 Stabilise the core. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-21
R-519 | T-1 Template format + registry. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-21
R-520 | T-2 Multi-app preview for template projects. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-21
R-521 | Core-loop hotfix: generated apps run again. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-21
R-522 | Google (Gemini) provider runs builds. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-21
R-523 | T-3 Template marketplace in the console: /templates (search, category filters, cards, empty state) and /templ… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-21
R-524 | Chat edits use the provider's output budget (never below 2,048 tokens). | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-21
R-525 | T-4 code-edit agent: template projects are edited by chat. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-21
R-526 | RideNow template part 1/4 (hidden draft): TypeScript API on Hono + pg with a trip state machine, real-driver-… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-22
R-527 | RideNow template part 2/4: packages/shared (typed API client with token refresh, SSE hook, formatters, offlin… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-22
R-528 | RideNow template part 3/4: apps/driver, an installable dark PWA (sign in, apply, home with online switch and… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-22
R-529 | Phase T handoff document (R_&_D/OmniStackAI_Template_Marketplace_Plan_v1.md: template method, publish checkli… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-22
R-530 | Follow-up: a machine-setup contract and the fixes that running on a local model exposed. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-23
R-531 | Bazaar template part 1/4 (hidden draft): multi-vendor commerce platform API, database migrations, domain serv… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-23
R-532 | Bazaar template part 2/4: shared library and storefront (apps/buyer) | PROJECT_STATE |  | Delivered | Completed |  |  | 2026-09-23 | Recorded in PROJECT_STATE.md; no CHANGELOG line.
R-533 | Bazaar template part 3/4 (hidden draft): artisan vendor portal (apps/seller on Next.js 16 + React 19 + Turbop… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-23
R-534 | Bazaar template part 4/4 and publish: Marketplace Operations Console (apps/admin), Playwright 48 screenshots… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-23
R-535 | CareClinic template part 1/4 (hidden draft): Clinical Care & Telemedicine API, database migrations, domain se… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-23
R-536 | CareClinic template part 2/4 (hidden draft): Shared Library (@careclinic/shared) and Patient Web App (apps/pa… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-23
R-537 | CareClinic template part 3/4 (hidden draft): Doctor Telehealth & Clinical Workstation (apps/doctor on Next.js… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-23
R-538 | CareClinic template part 4/4 and publish: the clinic operations console, 48 screenshots, and templates/catalo… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-23
R-539 | CareClinic doctor workstation rebuilt against the API, and the platform's own account commands. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-23
R-540 | Every published template audited, and Bazaar rebuilt against its own API. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-541 | One prompt now delivers every app it asked for, and each app looks like itself. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-542 | The admin console is reachable in the Studio. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-542b | The live journey, and the three defects it found. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-543 | A real archetype family, so different products get different pages. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-544 | The brand a user asks for now reaches the app they get. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-545 | The generated mobile app actually runs, and a phone can open it. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-546 | The generated Expo app can be built and submitted to the stores. | CHANGELOG |  | Delivered | Completed - needs live proof | P0 | R-574 | 2026-09-24 | Built and tested offline; prove it with a real account.
R-547 | Every credential gets a template entry, and the default icon stops looking unfinished. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-548 | One brand.json every generated surface derives from. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-549 | A rebrand now reaches the web app and the admin console too, not only the phone. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-550 | Before publishing, change anything; afterwards, one thing is refused — with the reason. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-551 | doctor now checks that the toolchain works, not that it matches a version string — and the command set is com… | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-552 | start and status now print every address a person needs, from one shared table. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-553 | The preview runs any number of apps, not the two it was told about. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-554 | A planned ecosystem assembles into one monorepo over one API and one database. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-555 | A prompt that names a second kind of user now builds the whole ecosystem. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-555b | The console's own build path takes the ecosystem branch, proven end to end. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-556 | Two products in one archetype no longer render the same page. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-557 | The console says why a project has four apps in it. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-558 | The deterministic pages use the design system they ship with. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-24
R-559 | Ask for something we cannot build and get the nearest thing we can, with a reason. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-25
R-560 | The build path compiles what it generated. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-25
R-561 | Every surface is compiled, not just the web app. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-25
R-562 | A request for an app is answered with an app. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-25
R-563 | A multi-app project can be changed after it is built. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-25
R-564 | The IR can describe what a product does, and older projects still open. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-25
R-565 | An ecosystem is built with the backend the user asked for. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-25
R-566 | An entity's lifecycle, and who may move it. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-26
R-584 | An edit can change a project, not only add to it. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-25
R-586 | The CareClinic seed generator stops reading the clock. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-25
R-587 | Generated Go is gofmt-clean. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-25
R-588 | A transition is describable and callable, not only implemented. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-26
R-589 | A lifecycle runs on every backend, not only the default one. | CHANGELOG |  | Delivered | Completed |  |  | 2026-09-26

## Summary
Status | 0 Foundation | 1 Vibe Mode live | 2 Maximum features | 3 Engineering Mode | 4 Production ops | 5 Native mobile (last) | 6 Go-live (credentials last) | 7 Win the category | Post-launch | Delivered | Total
Completed | 6 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 402 | 438
Completed - needs live proof | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8
In Progress | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pending | 0 | 11 | 66 | 7 | 7 | 0 | 0 | 0 | 0 | 6 | 97
Not Started | 0 | 6 | 335 | 43 | 57 | 25 | 6 | 7 | 0 | 28 | 507
Superseded | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 13
Deferred | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | 57
Dropped | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 9
Total | 6 | 47 | 402 | 50 | 64 | 25 | 6 | 7 | 66 | 456 | 1129
Open queue by priority | 0 Foundation | 1 Vibe Mode live | 2 Maximum features | 3 Engineering Mode | 4 Production ops | 5 Native mobile (last) | 6 Go-live (credentials last) | 7 Win the category | Post-launch | Delivered | Total
P0 | 0 | 1 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 4
P1 | 0 | 3 | 19 | 11 | 6 | 0 | 0 | 5 | 0 | 0 | 44
P2 | 0 | 1 | 13 | 3 | 7 | 6 | 0 | 2 | 0 | 0 | 32
P3 | 0 | 0 | 11 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 14

## Tracker Phases
Tracker phase | Dimension | Tracker asks | Covered by
MVP | Outcome | Reliable software factory | Delivered for generation; hardening in Phases 1 and 4.
MVP | Mobile | Flutter + Expo/RN; native beta | RN/Expo delivered (R-514, R-545, R-546); Flutter dropped; native in Phase 5 (R-575, R-576).
MVP | Web/Admin | Next.js | Delivered.
MVP | Backend/DB | Go/Python; Postgres default + DB recommender | Delivered (Python, Go, Node; PostgreSQL). MongoDB option PC-048.
MVP | Context/Memory | IR + Context Engine v1 | IR v2 delivered (R-564); memory R-581.
MVP | Runtime/Preview | Browser first + QR paths; Linux; iOS build | Local preview + QR delivered; in-browser PC-007; Linux sandboxes delivered (R-486..R-490); iOS build via EAS R-574.
MVP | Workflow/Agents | Temporal + model gateway | Gateway delivered; durable runs in R-577/PC-038 (Temporal itself deferred).
MVP | Git/Delivery | Task worktrees/PR | Push delivered (R-501); PRs PC-026.
MVP | Security | Isolation + secret broker + scans | Scans and secrets delivered; tenant isolation PC-009.
MVP | Cost | Cost per successful task | Ledger delivered; PC-010, PC-039.
MVP | Enterprise | Foundations only | Teams delivered (R-515).
MVP | Gate | Build/test/deploy evidence | Build/test evidence delivered (R-560, R-561); deploy evidence PC-008 + PC-071.
MID | Outcome | Professional developer / agency | Phases 2 and 3.
MID | Mobile | Native GA | Phase 5 (R-575, R-576, R-574, PC-044).
MID | Web/Admin | Enhanced | Phase 2 (R-572, PC-050, PC-019, PC-020).
MID | Backend/DB | Store APIs + more DB profiles | R-574 (stores), PC-048 (MongoDB).
MID | Context/Memory | Evidence-backed memory + richer graph | R-581, R-578.
MID | Runtime/Preview | Streamed emulators/simulators + Local Agent | PC-063, PC-064, PC-065, PC-066, PC-046.
MID | Workflow/Agents | Remote debug + BYOK | BYOK delivered (R-504); remote/time-travel debug deferred (R-197).
MID | Git/Delivery | Existing repo + handover | R-578, R-579; download/push delivered (R-501).
MID | Security | Visual/DAST/SBOM | PC-032, PC-035, PC-037.
MID | Cost | Native rebuild avoidance | PC-044 (build fingerprinting); Expo fingerprint in R-574.
MID | Enterprise | RBAC/SSO-ready | PC-029; SSO deferred (ARCH-ENTERPRISE).
MID | Gate | Quality + supportability | PC-037, PC-054, PC-015.
ADVANCED | Outcome | Enterprise flexibility | Deferred until after launch, on purpose. Pull any item forward if a customer needs it.
ADVANCED | Mobile | Device cloud + migration | Hosted emulators PC-065/PC-066; PWA/RN-to-native migration PC-045; physical device cloud deferred.
ADVANCED | Other dimensions | BYOC, private runners, multi-region, policy-as-code, private models, two-person approval, predictive scheduling | Deferred (R-081..R-093, R-130, R-166..R-168, R-201..R-209).
PRODUCTION | Outcome | Operational trust | Phase 4 + Phase 6; signed off by PC-067 against PG-01..PG-21.
PRODUCTION | Web/Admin | HA hosting | PC-041.
PRODUCTION | Backend/DB | HA/DR data, restore drills | PC-031.
PRODUCTION | Runtime | Multi-region as sold | Deferred (R-084) until a customer needs it.
PRODUCTION | Workflow | Workflow failover | PC-038.
PRODUCTION | Git/Delivery | Release qualification | PC-037.
PRODUCTION | Security | Pen test / SOC 2-ready controls | PC-032, PC-035.
PRODUCTION | Cost | Positive unit economics | PC-039.
PRODUCTION | Enterprise | SLA/process | PC-033.
PRODUCTION | Gate | Measured outcomes | PC-015 (beta KPIs), PC-067.
Tracker phase | Completed | Completed - needs live proof | In Progress | Pending | Not Started | Superseded | Deferred | Dropped | Total
MVP | 289 | 1 | 0 | 4 | 42 | 10 | 8 | 3 | 357
MID | 4 | 0 | 0 | 5 | 17 | 0 | 17 | 4 | 47
ADVANCED | 0 | 0 | 0 | 1 | 1 | 0 | 27 | 0 | 29
PRODUCTION | 0 | 0 | 0 | 0 | 24 | 0 | 4 | 1 | 29

## Pack Catalog
Layer | Category / industry | Pack | Provides | Surfaces / roles | Status | Priority | Wave task | Source | Notes
Horizontal | Core platform | database-pg | PostgreSQL schema, migrations, seeds, row-level security | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P1 | PC-073 | registry | Schema/migrations/seeds exist (R-238, R-248).
Horizontal | Core platform | database-mongo | MongoDB collections, schema validation, indexes, seeds | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | new | Founder decision D-8; built by PC-048.
Horizontal | Core platform | api-core | REST API, validation, OpenAPI, errors, rate limiting | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P1 | PC-073 | registry | Python/Go/Node APIs exist (R-229, R-230, R-517).
Horizontal | Core platform | auth-rbac | Login, register, roles, sessions, MFA, OAuth, passkeys | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P1 | PC-073 | spec, registry | Auth exists (R-461, R-241..R-243); Go login R-591.
Horizontal | Core platform | config-env | Typed env config, secret references, multi-environment | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | registry | Credential templates exist (R-547).
Horizontal | Core platform | admin-crud | Generated admin: tables, filters, bulk actions, exports | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P1 | PC-073 | spec | Admin app exists (R-542, R-270, R-271).
Horizontal | Core platform | multi-app | Shared API, cross-app auth, preview proxy, deploy coordination | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P1 | PC-073 | spec | Ecosystem monorepo exists (R-554, R-447, R-553).
Horizontal | Core platform | multi-tenancy | Tenant isolation, per-tenant data, tenant switching | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P1 | PC-073 | new (registry dependency)
Horizontal | Core platform | onboarding-invitations | Sign-up flows, invitations, first-run checklists | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | new (registry dependency)
Horizontal | Core platform | api-docs | OpenAPI, Swagger UI, Postman collection, SDKs | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | spec | OpenAPI exists (R-260, R-588).
Horizontal | Core platform | observability | Logs, metrics, traces, error tracking, alerting | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | spec, registry | PC-057.
Horizontal | Core platform | ci-cd | CI workflows, containers, Helm, preview environments | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | registry | CI/CD workflow generation exists (R-452).
Horizontal | Core platform | git-ops | Conventional commits, changelog, releases | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | registry
Horizontal | Core platform | custom-domains | Custom domains, DNS, TLS certificates | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | new (registry dependency 'dns') | Custom domains exist for published apps (R-510).
Horizontal | Security & compliance | rbac-advanced | Ownership rules, row-level and field-level permissions, org hierarchies, impersonation | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P1 | PC-073 | spec | R-570.
Horizontal | Security & compliance | security-headers | CSP, HSTS, permissions policy, nonces | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | registry
Horizontal | Security & compliance | audit-log | Append-only, tamper-evident audit log with query API | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | registry | PC-057.
Horizontal | Security & compliance | encryption | Field-level encryption, key rotation, KMS | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | registry
Horizontal | Security & compliance | secrets | Secret management, rotation, audit | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | spec | Platform secrets exist (R-503).
Horizontal | Security & compliance | compliance-gdpr | Data export, deletion, consent, retention | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | registry | PC-012.
Horizontal | Security & compliance | consent-management | Consent capture and ledger, cookie preferences | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | new (registry dependency) | Cookie consent component exists (R-402).
Horizontal | Security & compliance | compliance-hipaa | PHI masking, access audit, breach notification | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | registry
Horizontal | Security & compliance | compliance-soc2 | Control mapping, evidence collection, access reviews | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | registry
Horizontal | Security & compliance | identity-verification | KYC/KYB, document and selfie checks, verification status | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | new (registry dependency 'verification')
Horizontal | Security & compliance | moderation | Content moderation (AI + human queue), reports, bans | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | new (registry dependency)
Horizontal | Security & compliance | fraud-risk | Risk scoring, velocity rules, device fingerprints, blocklists | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | new
Horizontal | Data & storage | files-storage | S3-compatible uploads, presigned URLs, image transforms, CDN | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P1 | PC-073 | spec, registry | PC-052.
Horizontal | Data & storage | queue-jobs | Background jobs, retries, schedules, dead letter | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P1 | PC-073 | spec, registry | R-568.
Horizontal | Data & storage | search-engine | Meilisearch/Typesense, facets, typo tolerance | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P3 | PC-079 | spec, registry | Keyword search exists (R-261); PC-058.
Horizontal | Data & storage | cache-layer | Redis/Valkey caching, invalidation, locks | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | spec, registry
Horizontal | Data & storage | analytics-events | Event tracking, funnels, cohorts (PostHog/GA4) | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | spec, registry | Published-app analytics exists (R-513).
Horizontal | Data & storage | pdf-documents | Document templates, PDF generation, document store | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | new (registry dependencies 'documents', 'pdf-generation') | PDF viewer component exists (R-388).
Horizontal | Data & storage | data-import-export | CSV/Excel import with mapping and validation; bulk export | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | new | CSV/JSON export exists (R-271, R-308).
Horizontal | Data & storage | reporting | Scheduled reports, report builder, PDF/Excel delivery | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | new (registry dependency)
Horizontal | Data & storage | data-archival | Tiered storage, retention, legal hold | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | registry
Horizontal | Data & storage | backups-restore | Point-in-time backups and self-service restore for generated apps | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | new
Horizontal | Data & storage | vector-search | Embeddings and semantic search on pgvector | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | new
Horizontal | Realtime & communication | realtime-core | Live updates, presence, broadcast | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P1 | PC-073 | spec, registry | R-569.
Horizontal | Realtime & communication | notifications | Email, SMS, push, in-app centre, preferences, digests | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P1 | PC-073 | spec, registry | Email exists (R-516); PC-053.
Horizontal | Realtime & communication | communications | 1:1 and group chat, threads, mentions, reactions, attachments | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | spec, registry | Chat component exists (R-384).
Horizontal | Realtime & communication | activity-feed | Activity streams, timelines, follow/subscribe | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | new (registry dependency) | Timeline component exists (R-336).
Horizontal | Realtime & communication | video-calling | WebRTC calls, screen share, recording, transcripts | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | registry
Horizontal | Realtime & communication | webhooks | Outgoing webhooks, retries, signatures, replay | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | spec, registry | Cross-surface webhooks exist (R-448); PC-057.
Horizontal | Realtime & communication | support-helpdesk | Tickets, knowledge base, live-chat widget, SLAs | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | new
Horizontal | Business logic & workflow | workflows-core | State machines, transitions, guards, actions, audit | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P1 | PC-073 | spec, registry | Transitions done (R-566, R-588, R-589); guards R-571; buttons R-590.
Horizontal | Business logic & workflow | rules-engine | Business rules on create/update/transition | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P1 | PC-073 | new (architecture plan) | R-571.
Horizontal | Business logic & workflow | scheduling | Calendars, recurrence, conflicts, time zones, bookings, reminders | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P1 | PC-073 | spec, registry | Calendar/time-picker components exist (R-366, R-371).
Horizontal | Business logic & workflow | calendar-sync | Google/Outlook/iCal sync | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | new (registry dependency 'calendar')
Horizontal | Business logic & workflow | approvals | Multi-step approval chains, escalation, delegation | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | registry
Horizontal | Business logic & workflow | task-management | Tasks, assignees, due dates, boards | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | new (registry dependency 'tasks') | Kanban component exists (R-367).
Horizontal | Business logic & workflow | crm | Contacts, companies, leads, pipeline, activities | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | new (registry dependency)
Horizontal | Business logic & workflow | e-sign | Document signing, signer flows, certificates | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | new (registry dependency) | Signature pad exists (R-372).
Horizontal | Business logic & workflow | billing-metering | Usage metering, rating, invoicing, dunning | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | registry
Horizontal | Business logic & workflow | feature-flags | Flags, rollouts, experiments, kill switches | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | spec, registry | PC-056.
Horizontal | Business logic & workflow | audit-trail | Entity history, diffs, point-in-time queries | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | registry
Horizontal | Business logic & workflow | ratings-reviews | Stars, reviews, moderation, aggregates | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | spec | Rating component exists (R-333).
Horizontal | Business logic & workflow | referrals-affiliates | Referral codes, tracking, rewards | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | spec
Horizontal | Business logic & workflow | gamification | Points, badges, levels, leaderboards, streaks | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | new (registry dependency)
Horizontal | Business logic & workflow | pricing-engine | Price rules, tiers, dynamic pricing, quotes | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | new (registry dependencies 'pricing', 'rate-engine')
Horizontal | Business logic & workflow | forecasting | Demand and cash forecasts from history | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | new (registry dependency)
Horizontal | Commerce & payments | payments-core | Stripe/Razorpay/Paddle payments, refunds, disputes | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P1 | PC-073 | spec, registry, PRD | Checkout exists (R-512).
Horizontal | Commerce & payments | wallet-ledger | Double-entry ledger, accounts, transfers, reconciliation | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P1 | PC-073 | registry, PRD | R-567.
Horizontal | Commerce & payments | subscriptions | Plans, trials, proration, pausing, dunning | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | spec, registry | R-567.
Horizontal | Commerce & payments | marketplace-payments | Split payments, escrow, payouts, seller onboarding | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | spec ('marketplace-core'), registry | R-567; Bazaar shows the shape.
Horizontal | Commerce & payments | invoicing | Invoices, PDFs, recurring invoices, reminders | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | registry
Horizontal | Commerce & payments | tax-compliance | VAT/GST/sales tax calculation and validation | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | registry
Horizontal | Commerce & payments | coupons-promotions | Coupons, discounts, promotions, gift cards | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | new
Horizontal | Commerce & payments | multi-currency | Currencies, exchange rates, price lists | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | registry (listed under commerce) | Currency input exists (R-409).
Horizontal | UI & experience | design-system | Design tokens, components, motion, dark mode | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P1 | PC-073 | registry | Design system exists (R-558, R-324, R-491).
Horizontal | UI & experience | theming-branding | Brand kit applied to every surface | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | new | brand.json exists (R-548); PC-020.
Horizontal | UI & experience | pwa | Installable app, service worker, offline, push, QR | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P0 | PC-073 | spec | R-573.
Horizontal | UI & experience | forms-engine | Multi-step wizards, conditional fields, drafts | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | registry | PC-059.
Horizontal | UI & experience | data-tables | Virtualised tables, grouping, column picker, export | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | registry | Data grid exists (R-329).
Horizontal | UI & experience | charts-dashboards | Charts, dashboards, live series | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | registry | Chart suite exists (R-370).
Horizontal | UI & experience | rich-text | Rich text editor, mentions, slash commands | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | registry | Markdown editor exists (R-365).
Horizontal | UI & experience | maps-geo | Maps, geocoding, geofences, routes, address autocomplete | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P1 | PC-073 | registry ('mapping', listed under mobility), PRD | Geo-map component exists (R-387).
Horizontal | UI & experience | localization | i18n, RTL, currency and date formatting | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | spec | PC-055.
Horizontal | UI & experience | accessibility | WCAG 2.1 AA, automated axe checks | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | spec | Accessible UI exists (R-296).
Horizontal | UI & experience | performance | Bundle analysis, Core Web Vitals, Lighthouse CI | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | spec | PC-037.
Horizontal | UI & experience | seo | Metadata, sitemaps, structured data, AI-search readiness | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | new (registry dependency) | SEO exists (R-505).
Horizontal | UI & experience | cms-marketing-site | Landing pages, blog, CMS for non-developers | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | new
Horizontal | UI & experience | onboarding-tours | Product tours and spotlight guides | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P3 | PC-079 | new | Tour component exists (R-363).
Horizontal | UI & experience | storybook | Component docs and visual playground | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | spec
Horizontal | Mobile & device (stack-aware: React Native, Kotlin, Swift) | mobile-push | Push notifications (Expo, FCM, APNs), deep-link on tap | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P1 | PC-073 | PRD | PC-053.
Horizontal | Mobile & device (stack-aware: React Native, Kotlin, Swift) | secure-storage | Keychain/Keystore-backed storage for tokens and secrets | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P1 | PC-073 | PRD
Horizontal | Mobile & device (stack-aware: React Native, Kotlin, Swift) | geolocation | Foreground/background location, live tracking | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P1 | PC-073 | PRD | Needs R-569.
Horizontal | Mobile & device (stack-aware: React Native, Kotlin, Swift) | camera-qr | Camera, photo/video capture, QR and barcode scanning | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P1 | PC-073 | PRD (+ registry 'barcode') | QR generation exists (R-382).
Horizontal | Mobile & device (stack-aware: React Native, Kotlin, Swift) | biometrics | Face ID / Touch ID / BiometricPrompt, passkeys | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | PRD
Horizontal | Mobile & device (stack-aware: React Native, Kotlin, Swift) | offline-sync | Offline-first storage, sync queue, conflict resolution | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P1 | PC-073 | new
Horizontal | Mobile & device (stack-aware: React Native, Kotlin, Swift) | deep-links | Universal/app links, share links into screens | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P1 | PC-073 | new
Horizontal | Mobile & device (stack-aware: React Native, Kotlin, Swift) | in-app-purchases | Apple and Google in-app purchases and subscriptions | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P1 | PC-073 | new | Required by store rules for digital goods; keys at PC-070.
Horizontal | Mobile & device (stack-aware: React Native, Kotlin, Swift) | app-store-assets | Icons, splash, screenshots, store listing metadata | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P1 | PC-073 | new | Icons and EAS config exist (R-546, R-547); R-574.
Horizontal | Mobile & device (stack-aware: React Native, Kotlin, Swift) | ota-updates | Over-the-air updates and in-app update prompts | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | new
Horizontal | Mobile & device (stack-aware: React Native, Kotlin, Swift) | crash-reporting | Crash and ANR reporting with symbolication | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | new
Horizontal | Mobile & device (stack-aware: React Native, Kotlin, Swift) | background-tasks | Background fetch, scheduled local work | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P2 | PC-078 | new
Horizontal | Mobile & device (stack-aware: React Native, Kotlin, Swift) | media-player-device | Audio/video playback, background audio, casting | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P3 | PC-079 | new | Web media players exist (R-376, R-390).
Horizontal | Mobile & device (stack-aware: React Native, Kotlin, Swift) | health-fitness-data | HealthKit and Health Connect | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | new
Horizontal | Mobile & device (stack-aware: React Native, Kotlin, Swift) | bluetooth-nfc | Bluetooth LE and NFC | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | new
Horizontal | Mobile & device (stack-aware: React Native, Kotlin, Swift) | share-contacts | Share sheet, contacts picker, calendar events | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | new (registry dependency 'sharing')
Horizontal | Integration & AI | ai-assistant | In-app AI: chat assistant, summarise, extract, generate, over the app's own data | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P1 | PC-073 | new | Uses the platform's model gateway pattern; keys at PC-070.
Horizontal | Integration & AI | integration-hub | Connectors (Slack, HubSpot, Salesforce ...), workflow builder | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Pending | P2 | PC-078 | registry | Connectors v1 exist (R-511).
Horizontal | Integration & AI | ml-inference | Model inference endpoints for scoring and classification | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | new (registry dependency)
Horizontal | Integration & AI | api-gateway | Rate limits, API keys, transformations | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | registry
Horizontal | Integration & AI | developer-portal | API keys, docs, usage for third-party developers | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | new (registry dependency)
Horizontal | Integration & AI | plugin-system | Sandboxed plugins and extension marketplace | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | registry
Horizontal | Integration & AI | mcp-gateway | MCP server exposing the app's tools to AI agents | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | registry
Horizontal | Integration & AI | iot-telematics | Device registry, telemetry ingestion, alerts | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P3 | PC-079 | new (registry dependencies 'iot', 'telematics')
Horizontal | Quality | testing | Generated unit, contract and end-to-end tests | API + Web + App + Admin, each stack (RN first; Kotlin/Swift in PC-082) | Not Started | P1 | PC-073 | spec | PC-054.
Vertical | Healthcare & life sciences (healthcare-core) | patients | Patients, records, insurance, consent | Patient: App + Web; Doctor / provider: Web + App; Pharmacy / lab: Web; Clinic operator: Admin | Pending | P1 | PC-074 | registry | CareClinic template.
Vertical | Healthcare & life sciences (healthcare-core) | providers | Providers, specialties, licences, schedules | Patient: App + Web; Doctor / provider: Web + App; Pharmacy / lab: Web; Clinic operator: Admin | Pending | P1 | PC-074 | registry | CareClinic template.
Vertical | Healthcare & life sciences (healthcare-core) | appointments | Appointments, slots, reminders, waitlist | Patient: App + Web; Doctor / provider: Web + App; Pharmacy / lab: Web; Clinic operator: Admin | Pending | P1 | PC-074 | registry | CareClinic template.
Vertical | Healthcare & life sciences (healthcare-core) | emr | Encounters, notes, diagnoses, vitals | Patient: App + Web; Doctor / provider: Web + App; Pharmacy / lab: Web; Clinic operator: Admin | Pending | P1 | PC-074 | registry | CareClinic template (partial).
Vertical | Healthcare & life sciences (healthcare-core) | prescriptions | Prescriptions, medications, pharmacies | Patient: App + Web; Doctor / provider: Web + App; Pharmacy / lab: Web; Clinic operator: Admin | Pending | P1 | PC-074 | registry | CareClinic template (partial).
Vertical | Healthcare & life sciences (healthcare-core) | lab-orders | Lab orders, specimens, results | Patient: App + Web; Doctor / provider: Web + App; Pharmacy / lab: Web; Clinic operator: Admin | Not Started | P1 | PC-074 | registry
Vertical | Healthcare & life sciences (healthcare-core) | telehealth | Video consults, consent, technical checks | Patient: App + Web; Doctor / provider: Web + App; Pharmacy / lab: Web; Clinic operator: Admin | Pending | P1 | PC-074 | registry | CareClinic template.
Vertical | Healthcare & life sciences (healthcare-core) | billing-codes | Claims, codes, payers, remittance | Patient: App + Web; Doctor / provider: Web + App; Pharmacy / lab: Web; Clinic operator: Admin | Not Started | P1 | PC-074 | registry
Vertical | Healthcare & life sciences (healthcare-core) | hipaa-compliance | Access logs, breach reports, risk assessments | Patient: App + Web; Doctor / provider: Web + App; Pharmacy / lab: Web; Clinic operator: Admin | Not Started | P1 | PC-074 | registry
Vertical | Healthcare & life sciences (healthcare-core) | clinical-trials | Trials, protocols, enrolment, adverse events | Patient: App + Web; Doctor / provider: Web + App; Pharmacy / lab: Web; Clinic operator: Admin | Not Started | P1 | PC-074 | registry
Vertical | Healthcare & life sciences (healthcare-core) | pharmacy-integration | Formulary, dispense, interaction checks | Patient: App + Web; Doctor / provider: Web + App; Pharmacy / lab: Web; Clinic operator: Admin | Not Started | P1 | PC-074 | registry
Vertical | Healthcare & life sciences (healthcare-core) | lab-integration | Lab interfaces, HL7 mapping, QC | Patient: App + Web; Doctor / provider: Web + App; Pharmacy / lab: Web; Clinic operator: Admin | Not Started | P1 | PC-074 | registry
Vertical | Healthcare & life sciences (healthcare-core) | dental-clinic | Dental charts, treatment plans, recalls | Patient: App + Web; Doctor / provider: Web + App; Pharmacy / lab: Web; Clinic operator: Admin | Not Started | P1 | PC-074 | new
Vertical | Healthcare & life sciences (healthcare-core) | mental-health | Therapy sessions, journals, assessments | Patient: App + Web; Doctor / provider: Web + App; Pharmacy / lab: Web; Clinic operator: Admin | Not Started | P1 | PC-074 | new
Vertical | Mobility & on-demand (mobility-core) | rides | Rides, routes, fares, matching, receipts | Rider: App + Web; Driver: App; Dispatcher: Web; Operator: Admin | Pending | P1 | PC-074 | registry | RideNow template.
Vertical | Mobility & on-demand (mobility-core) | drivers | Drivers, vehicles, documents, earnings | Rider: App + Web; Driver: App; Dispatcher: Web; Operator: Admin | Pending | P1 | PC-074 | registry | RideNow template.
Vertical | Mobility & on-demand (mobility-core) | dispatch | Zones, assignment rules, heatmaps | Rider: App + Web; Driver: App; Dispatcher: Web; Operator: Admin | Pending | P1 | PC-074 | registry | RideNow template (partial).
Vertical | Mobility & on-demand (mobility-core) | fleet | Fleet, vehicles, maintenance, inspections | Rider: App + Web; Driver: App; Dispatcher: Web; Operator: Admin | Not Started | P1 | PC-074 | registry (+ dependencies 'vehicles', 'maintenance')
Vertical | Mobility & on-demand (mobility-core) | deliveries | Packages, pickups, drop-offs, proof of delivery | Rider: App + Web; Driver: App; Dispatcher: Web; Operator: Admin | Not Started | P1 | PC-074 | registry (+ dependency 'proof-of-delivery')
Vertical | Mobility & on-demand (mobility-core) | last-mile | Route plans, stop sequencing, time windows | Rider: App + Web; Driver: App; Dispatcher: Web; Operator: Admin | Not Started | P1 | PC-074 | registry (+ dependency 'routing')
Vertical | Mobility & on-demand (mobility-core) | surge-pricing | Demand/supply signals, multipliers | Rider: App + Web; Driver: App; Dispatcher: Web; Operator: Admin | Not Started | P1 | PC-074 | registry
Vertical | Mobility & on-demand (mobility-core) | background-checks | Driver checks, adverse actions | Rider: App + Web; Driver: App; Dispatcher: Web; Operator: Admin | Not Started | P1 | PC-074 | registry
Vertical | Mobility & on-demand (mobility-core) | insurance-commercial | Commercial policies, claims | Rider: App + Web; Driver: App; Dispatcher: Web; Operator: Admin | Not Started | P1 | PC-074 | registry (+ dependency 'insurance')
Vertical | Mobility & on-demand (mobility-core) | vehicle-rentals | Car/bike/scooter rental, unlock, trip billing | Rider: App + Web; Driver: App; Dispatcher: Web; Operator: Admin | Not Started | P1 | PC-074 | new
Vertical | Mobility & on-demand (mobility-core) | parking | Parking spots, bookings, enforcement | Rider: App + Web; Driver: App; Dispatcher: Web; Operator: Admin | Not Started | P1 | PC-074 | new
Vertical | Marketplace & commerce (commerce-core) | listings | Listings, categories, variants, media | Buyer: App + Web; Seller / vendor: Web + App; Marketplace operator: Admin | Pending | P1 | PC-074 | registry | Bazaar template.
Vertical | Marketplace & commerce (commerce-core) | cart-checkout | Cart, coupons, checkout sessions | Buyer: App + Web; Seller / vendor: Web + App; Marketplace operator: Admin | Pending | P1 | PC-074 | registry | Bazaar template.
Vertical | Marketplace & commerce (commerce-core) | orders | Orders, line items, timelines | Buyer: App + Web; Seller / vendor: Web + App; Marketplace operator: Admin | Pending | P1 | PC-074 | new (registry dependency) | Bazaar template.
Vertical | Marketplace & commerce (commerce-core) | inventory | Stock levels, reservations, reorder points | Buyer: App + Web; Seller / vendor: Web + App; Marketplace operator: Admin | Not Started | P1 | PC-074 | registry
Vertical | Marketplace & commerce (commerce-core) | fulfillment | Fulfilment orders, shipments, labels, tracking | Buyer: App + Web; Seller / vendor: Web + App; Marketplace operator: Admin | Not Started | P1 | PC-074 | registry (+ dependency 'shipping')
Vertical | Marketplace & commerce (commerce-core) | vendors | Vendors, storefronts, verification | Buyer: App + Web; Seller / vendor: Web + App; Marketplace operator: Admin | Pending | P1 | PC-074 | registry | Bazaar template.
Vertical | Marketplace & commerce (commerce-core) | commissions | Commission rules, splits, payout cycles | Buyer: App + Web; Seller / vendor: Web + App; Marketplace operator: Admin | Pending | P1 | PC-074 | registry | Bazaar ledger.
Vertical | Marketplace & commerce (commerce-core) | reviews | Verified-purchase reviews, moderation | Buyer: App + Web; Seller / vendor: Web + App; Marketplace operator: Admin | Not Started | P1 | PC-074 | registry
Vertical | Marketplace & commerce (commerce-core) | returns | Returns, inspections, refunds, exchanges | Buyer: App + Web; Seller / vendor: Web + App; Marketplace operator: Admin | Not Started | P1 | PC-074 | registry
Vertical | Marketplace & commerce (commerce-core) | subscriptions-commerce | Subscription boxes, physical + digital | Buyer: App + Web; Seller / vendor: Web + App; Marketplace operator: Admin | Not Started | P1 | PC-074 | registry
Vertical | Marketplace & commerce (commerce-core) | affiliates | Affiliate links, conversions, tiers | Buyer: App + Web; Seller / vendor: Web + App; Marketplace operator: Admin | Not Started | P1 | PC-074 | registry
Vertical | Marketplace & commerce (commerce-core) | marketplace-seo | Programmatic SEO, structured data | Buyer: App + Web; Seller / vendor: Web + App; Marketplace operator: Admin | Not Started | P1 | PC-074 | registry
Vertical | Marketplace & commerce (commerce-core) | purchase-orders | B2B purchase orders and approvals | Buyer: App + Web; Seller / vendor: Web + App; Marketplace operator: Admin | Not Started | P1 | PC-074 | new (registry dependency)
Vertical | Marketplace & commerce (commerce-core) | wishlists-recommendations | Wishlists, recently viewed, recommendations | Buyer: App + Web; Seller / vendor: Web + App; Marketplace operator: Admin | Not Started | P1 | PC-074 | new
Vertical | Marketplace & commerce (commerce-core) | auctions-bidding | Auctions, bids, reserve prices | Buyer: App + Web; Seller / vendor: Web + App; Marketplace operator: Admin | Not Started | P1 | PC-074 | new
Vertical | Quick commerce & grocery (quick-commerce-core) | dark-stores | Dark stores, picking, packing | Customer: App + Web; Picker / packer: App; Rider: App; Store manager: Web; Operator: Admin | Not Started | P2 | PC-080 | PRD
Vertical | Quick commerce & grocery (quick-commerce-core) | grocery-catalog | Grocery catalogue, weights, substitutions | Customer: App + Web; Picker / packer: App; Rider: App; Store manager: Web; Operator: Admin | Not Started | P2 | PC-080 | PRD
Vertical | Quick commerce & grocery (quick-commerce-core) | delivery-slots | Delivery slots and capacity | Customer: App + Web; Picker / packer: App; Rider: App; Store manager: Web; Operator: Admin | Not Started | P2 | PC-080 | PRD
Vertical | Quick commerce & grocery (quick-commerce-core) | rider-batching | Batching orders per rider | Customer: App + Web; Picker / packer: App; Rider: App; Store manager: Web; Operator: Admin | Not Started | P2 | PC-080 | PRD
Vertical | Quick commerce & grocery (quick-commerce-core) | substitutions | Out-of-stock substitution approval | Customer: App + Web; Picker / packer: App; Rider: App; Store manager: Web; Operator: Admin | Not Started | P2 | PC-080 | new
Vertical | Quick commerce & grocery (quick-commerce-core) | basket-reorder | Reorder, smart baskets | Customer: App + Web; Picker / packer: App; Rider: App; Store manager: Web; Operator: Admin | Not Started | P2 | PC-080 | new
Vertical | FinTech & banking (fintech-core) | accounts | Accounts, holders, beneficiaries, limits | Customer: App + Web; Merchant: Web + App; Compliance officer: Web; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | FinTech & banking (fintech-core) | ledger-core | Journals, periods, reconciliation | Customer: App + Web; Merchant: Web + App; Compliance officer: Web; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | FinTech & banking (fintech-core) | transfers | Transfers, ACH/SEPA/UPI, FX | Customer: App + Web; Merchant: Web + App; Compliance officer: Web; Operator: Admin | Not Started | P2 | PC-080 | registry (+ dependency 'transactions')
Vertical | FinTech & banking (fintech-core) | cards | Card issuing, authorisations, disputes | Customer: App + Web; Merchant: Web + App; Compliance officer: Web; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | FinTech & banking (fintech-core) | lending | Loan origination, underwriting, amortisation | Customer: App + Web; Merchant: Web + App; Compliance officer: Web; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | FinTech & banking (fintech-core) | credit-scoring | Score models, decisions | Customer: App + Web; Merchant: Web + App; Compliance officer: Web; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | FinTech & banking (fintech-core) | compliance-aml | AML alerts, cases, watchlists | Customer: App + Web; Merchant: Web + App; Compliance officer: Web; Operator: Admin | Not Started | P2 | PC-080 | registry (+ dependency 'case-management')
Vertical | FinTech & banking (fintech-core) | compliance-kyc | KYC profiles, verification, risk rating | Customer: App + Web; Merchant: Web + App; Compliance officer: Web; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | FinTech & banking (fintech-core) | treasury | Cash positions, forecasts, sweeps | Customer: App + Web; Merchant: Web + App; Compliance officer: Web; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | FinTech & banking (fintech-core) | trade-finance | Letters of credit, guarantees | Customer: App + Web; Merchant: Web + App; Compliance officer: Web; Operator: Admin | Not Started | P2 | PC-080 | registry (+ dependency 'letters-of-credit')
Vertical | FinTech & banking (fintech-core) | digital-assets | Wallets, custody, transfers | Customer: App + Web; Merchant: Web + App; Compliance officer: Web; Operator: Admin | Not Started | P2 | PC-080 | registry (+ dependency 'custody')
Vertical | FinTech & banking (fintech-core) | open-banking | Consent, data access, payment initiation | Customer: App + Web; Merchant: Web + App; Compliance officer: Web; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | FinTech & banking (fintech-core) | regulatory-reporting | Regulatory reports and filings | Customer: App + Web; Merchant: Web + App; Compliance officer: Web; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | FinTech & banking (fintech-core) | wealth-management | Portfolios, rebalancing, goals | Customer: App + Web; Merchant: Web + App; Compliance officer: Web; Operator: Admin | Not Started | P2 | PC-080 | registry (+ dependency 'portfolio')
Vertical | FinTech & banking (fintech-core) | bill-payments-upi | Bill payments, UPI, QR payments | Customer: App + Web; Merchant: Web + App; Compliance officer: Web; Operator: Admin | Not Started | P2 | PC-080 | new
Vertical | FinTech & banking (fintech-core) | personal-finance | Budgets, expense categorisation, savings goals | Customer: App + Web; Merchant: Web + App; Compliance officer: Web; Operator: Admin | Not Started | P2 | PC-080 | new (registry dependencies 'budgeting', 'expenses')
Vertical | Food delivery & hospitality (food-delivery-core) | restaurants | Restaurants, hours, locations | Customer: App + Web; Restaurant: Web + App; Courier: App; Operator: Admin | Not Started | P2 | PC-080 | registry (+ dependency 'multi-location')
Vertical | Food delivery & hospitality (food-delivery-core) | menus | Menus, modifiers, allergens, nutrition | Customer: App + Web; Restaurant: Web + App; Courier: App; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | Food delivery & hospitality (food-delivery-core) | food-orders | Orders, kitchen tickets, timelines | Customer: App + Web; Restaurant: Web + App; Courier: App; Operator: Admin | Not Started | P2 | PC-080 | registry ('orders')
Vertical | Food delivery & hospitality (food-delivery-core) | kitchen | Kitchen display, stations, prep times | Customer: App + Web; Restaurant: Web + App; Courier: App; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | Food delivery & hospitality (food-delivery-core) | couriers | Couriers, shifts, earnings, incentives | Customer: App + Web; Restaurant: Web + App; Courier: App; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | Food delivery & hospitality (food-delivery-core) | delivery-tracking | Live location, ETA, share links | Customer: App + Web; Restaurant: Web + App; Courier: App; Operator: Admin | Not Started | P2 | PC-080 | registry (+ dependency 'tracking')
Vertical | Food delivery & hospitality (food-delivery-core) | loyalty | Points, tiers, rewards | Customer: App + Web; Restaurant: Web + App; Courier: App; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | Food delivery & hospitality (food-delivery-core) | catering | Catering orders, proposals, deposits | Customer: App + Web; Restaurant: Web + App; Courier: App; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | Food delivery & hospitality (food-delivery-core) | ghost-kitchens | Virtual brands, capacity | Customer: App + Web; Restaurant: Web + App; Courier: App; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | Food delivery & hospitality (food-delivery-core) | table-reservations | Tables, reservations, waitlist | Customer: App + Web; Restaurant: Web + App; Courier: App; Operator: Admin | Not Started | P2 | PC-080 | new
Vertical | Real estate & proptech (real-estate-core) | properties | Properties, units, amenities, valuations | Buyer / tenant: App + Web; Agent / broker: Web + App; Landlord: Web; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | Real estate & proptech (real-estate-core) | listings-re | Property listings, price history, disclosures | Buyer / tenant: App + Web; Agent / broker: Web + App; Landlord: Web; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | Real estate & proptech (real-estate-core) | tours | Tour scheduling, self-guided, virtual | Buyer / tenant: App + Web; Agent / broker: Web + App; Landlord: Web; Operator: Admin | Not Started | P2 | PC-080 | registry (+ dependency 'virtual-tours')
Vertical | Real estate & proptech (real-estate-core) | offers | Offers, counters, contingencies | Buyer / tenant: App + Web; Agent / broker: Web + App; Landlord: Web; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | Real estate & proptech (real-estate-core) | contracts | Contracts, clauses, addenda | Buyer / tenant: App + Web; Agent / broker: Web + App; Landlord: Web; Operator: Admin | Not Started | P2 | PC-080 | registry (+ dependency 'compliance-re')
Vertical | Real estate & proptech (real-estate-core) | escrow | Escrow accounts, disbursements | Buyer / tenant: App + Web; Agent / broker: Web + App; Landlord: Web; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | Real estate & proptech (real-estate-core) | property-mgmt | Leases, tenants, maintenance, rent | Buyer / tenant: App + Web; Agent / broker: Web + App; Landlord: Web; Operator: Admin | Not Started | P2 | PC-080 | registry (+ dependencies 'portals', 'accounting')
Vertical | Real estate & proptech (real-estate-core) | investment-analysis | Pro formas, cash flow, IRR | Buyer / tenant: App + Web; Agent / broker: Web + App; Landlord: Web; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | Real estate & proptech (real-estate-core) | agent-crm | Agent leads, pipelines, follow-ups | Buyer / tenant: App + Web; Agent / broker: Web + App; Landlord: Web; Operator: Admin | Not Started | P2 | PC-080 | new (template Estately)
Vertical | Real estate & proptech (real-estate-core) | co-living-rentals | Rooms, short stays, house rules | Buyer / tenant: App + Web; Agent / broker: Web + App; Landlord: Web; Operator: Admin | Not Started | P2 | PC-080 | new
Vertical | Education & edtech (edtech-core) | courses | Courses, modules, lessons, prerequisites | Learner: App + Web; Instructor: Web + App; Parent: App; Institution admin: Admin | Not Started | P2 | PC-080 | registry
Vertical | Education & edtech (edtech-core) | enrollments | Enrolments, progress, completion | Learner: App + Web; Instructor: Web + App; Parent: App; Institution admin: Admin | Not Started | P2 | PC-080 | registry
Vertical | Education & edtech (edtech-core) | assignments | Assignments, submissions, rubrics, peer review | Learner: App + Web; Instructor: Web + App; Parent: App; Institution admin: Admin | Not Started | P2 | PC-080 | registry (+ dependencies 'submissions', 'plagiarism')
Vertical | Education & edtech (edtech-core) | grading | Gradebooks, schemes, exports | Learner: App + Web; Instructor: Web + App; Parent: App; Institution admin: Admin | Not Started | P2 | PC-080 | registry (+ dependency 'gradebook')
Vertical | Education & edtech (edtech-core) | certificates | Certificates, verifiable credentials | Learner: App + Web; Instructor: Web + App; Parent: App; Institution admin: Admin | Not Started | P2 | PC-080 | registry
Vertical | Education & edtech (edtech-core) | lms-admin | Schools, departments, instructors | Learner: App + Web; Instructor: Web + App; Parent: App; Institution admin: Admin | Not Started | P2 | PC-080 | registry
Vertical | Education & edtech (edtech-core) | video-streaming | Video lessons, captions, DRM | Learner: App + Web; Instructor: Web + App; Parent: App; Institution admin: Admin | Not Started | P2 | PC-080 | registry (+ dependency 'drm')
Vertical | Education & edtech (edtech-core) | cohorts | Cohorts, mentors, leaderboards | Learner: App + Web; Instructor: Web + App; Parent: App; Institution admin: Admin | Not Started | P2 | PC-080 | registry
Vertical | Education & edtech (edtech-core) | compliance-education | FERPA/COPPA consent and audit | Learner: App + Web; Instructor: Web + App; Parent: App; Institution admin: Admin | Not Started | P2 | PC-080 | registry
Vertical | Education & edtech (edtech-core) | quizzes-exams | Question banks, timed exams, proctoring | Learner: App + Web; Instructor: Web + App; Parent: App; Institution admin: Admin | Not Started | P2 | PC-080 | new
Vertical | Education & edtech (edtech-core) | live-classes | Live classes, attendance, recordings | Learner: App + Web; Instructor: Web + App; Parent: App; Institution admin: Admin | Not Started | P2 | PC-080 | new
Vertical | SaaS & B2B (saas-b2b-core) | organizations | Organisations, memberships, domains | End user: Web + App; Customer admin: Web; Platform operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | SaaS & B2B (saas-b2b-core) | teams | Teams, members, channels | End user: Web + App; Customer admin: Web; Platform operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | SaaS & B2B (saas-b2b-core) | seats | Seats, assignment, true-ups | End user: Web + App; Customer admin: Web; Platform operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | SaaS & B2B (saas-b2b-core) | entitlements | Per-feature and per-seat entitlements | End user: Web + App; Customer admin: Web; Platform operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | SaaS & B2B (saas-b2b-core) | sso-saml | SAML SSO, JIT provisioning | End user: Web + App; Customer admin: Web; Platform operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | SaaS & B2B (saas-b2b-core) | sso-oidc | OIDC SSO | End user: Web + App; Customer admin: Web; Platform operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | SaaS & B2B (saas-b2b-core) | usage-metering | Meters, quotas, alerts | End user: Web + App; Customer admin: Web; Platform operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | SaaS & B2B (saas-b2b-core) | api-management | API products, keys, monetisation | End user: Web + App; Customer admin: Web; Platform operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | SaaS & B2B (saas-b2b-core) | marketplace-saas | App listings, provisioning | End user: Web + App; Customer admin: Web; Platform operator: Admin | Not Started | P2 | PC-080 | registry (+ dependency 'provisioning')
Vertical | SaaS & B2B (saas-b2b-core) | white-label | Brands, custom domains, rollouts | End user: Web + App; Customer admin: Web; Platform operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | SaaS & B2B (saas-b2b-core) | scim-provisioning | SCIM user provisioning | End user: Web + App; Customer admin: Web; Platform operator: Admin | Not Started | P2 | PC-080 | new
Vertical | SaaS & B2B (saas-b2b-core) | customer-success | Health scores, renewals, churn signals | End user: Web + App; Customer admin: Web; Platform operator: Admin | Not Started | P2 | PC-080 | new
Vertical | Logistics & supply chain (logistics-core) | shipments | Shipments, legs, bills of lading | Shipper: Web + App; Driver / carrier: App; Warehouse staff: App; Dispatcher: Web; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | Logistics & supply chain (logistics-core) | warehouses | Warehouses, zones, slotting, labour | Shipper: Web + App; Driver / carrier: App; Warehouse staff: App; Dispatcher: Web; Operator: Admin | Not Started | P2 | PC-080 | registry (+ dependencies 'warehouse', 'slotting', 'labor')
Vertical | Logistics & supply chain (logistics-core) | inventory-wms | Locations, cycle counts, pick paths | Shipper: Web + App; Driver / carrier: App; Warehouse staff: App; Dispatcher: Web; Operator: Admin | Not Started | P2 | PC-080 | registry (+ dependencies 'rfid', 'voice-picking')
Vertical | Logistics & supply chain (logistics-core) | transportation | Loads, carriers, tenders, rates | Shipper: Web + App; Driver / carrier: App; Warehouse staff: App; Dispatcher: Web; Operator: Admin | Not Started | P2 | PC-080 | registry (+ dependency 'compliance-dot')
Vertical | Logistics & supply chain (logistics-core) | customs | Entries, HS classification, duty | Shipper: Web + App; Driver / carrier: App; Warehouse staff: App; Dispatcher: Web; Operator: Admin | Not Started | P2 | PC-080 | registry (+ dependency 'hs-codes')
Vertical | Logistics & supply chain (logistics-core) | freight-forwarding | Quotes, bookings, milestones | Shipper: Web + App; Driver / carrier: App; Warehouse staff: App; Dispatcher: Web; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | Logistics & supply chain (logistics-core) | last-mile-logistics | Routes, stops, exceptions | Shipper: Web + App; Driver / carrier: App; Warehouse staff: App; Dispatcher: Web; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | Logistics & supply chain (logistics-core) | supply-chain-visibility | Control tower, ETAs, risk scores | Shipper: Web + App; Driver / carrier: App; Warehouse staff: App; Dispatcher: Web; Operator: Admin | Not Started | P2 | PC-080 | registry
Vertical | Logistics & supply chain (logistics-core) | procurement | Requisitions, POs, three-way match | Shipper: Web + App; Driver / carrier: App; Warehouse staff: App; Dispatcher: Web; Operator: Admin | Not Started | P2 | PC-080 | registry (+ dependency 'spend-analysis')
Vertical | Logistics & supply chain (logistics-core) | fleet-management | Assets, fuel, utilisation, TCO | Shipper: Web + App; Driver / carrier: App; Warehouse staff: App; Dispatcher: Web; Operator: Admin | Not Started | P2 | PC-080 | registry (+ dependency 'fuel-cards')
Vertical | Logistics & supply chain (logistics-core) | yard-management | Yard slots, gate check-in, docks | Shipper: Web + App; Driver / carrier: App; Warehouse staff: App; Dispatcher: Web; Operator: Admin | Not Started | P2 | PC-080 | new
Vertical | On-demand home services (home-services-core) | service-catalog | Services, pricing, service areas | Customer: App + Web; Service pro: App; Business owner: Web; Operator: Admin | Not Started | P2 | PC-080 | PRD
Vertical | On-demand home services (home-services-core) | provider-matching | Match jobs to nearby qualified pros | Customer: App + Web; Service pro: App; Business owner: Web; Operator: Admin | Not Started | P2 | PC-080 | PRD
Vertical | On-demand home services (home-services-core) | job-quotes | Quotes, estimates, approvals | Customer: App + Web; Service pro: App; Business owner: Web; Operator: Admin | Not Started | P2 | PC-080 | PRD
Vertical | On-demand home services (home-services-core) | job-lifecycle | Booked -> en route -> in progress -> done | Customer: App + Web; Service pro: App; Business owner: Web; Operator: Admin | Not Started | P2 | PC-080 | PRD
Vertical | On-demand home services (home-services-core) | service-warranty | Warranties, callbacks, disputes | Customer: App + Web; Service pro: App; Business owner: Web; Operator: Admin | Not Started | P2 | PC-080 | new
Vertical | Beauty, salon & wellness (beauty-wellness-core) | salon-booking | Service booking with staff and chairs | Client: App + Web; Stylist / therapist: App; Salon owner: Web; Operator: Admin | Not Started | P2 | PC-080 | PRD
Vertical | Beauty, salon & wellness (beauty-wellness-core) | staff-schedules | Stylist schedules, commissions | Client: App + Web; Stylist / therapist: App; Salon owner: Web; Operator: Admin | Not Started | P2 | PC-080 | PRD
Vertical | Beauty, salon & wellness (beauty-wellness-core) | service-menu | Services, durations, add-ons | Client: App + Web; Stylist / therapist: App; Salon owner: Web; Operator: Admin | Not Started | P2 | PC-080 | PRD
Vertical | Beauty, salon & wellness (beauty-wellness-core) | memberships-packages | Memberships, packages, prepaid sessions | Client: App + Web; Stylist / therapist: App; Salon owner: Web; Operator: Admin | Not Started | P2 | PC-080 | new
Vertical | Beauty, salon & wellness (beauty-wellness-core) | client-profiles | Client history, preferences, before/after photos | Client: App + Web; Stylist / therapist: App; Salon owner: Web; Operator: Admin | Not Started | P2 | PC-080 | new
Vertical | HR & recruiting (hr-core) | jobs-ats | Job posts, applicant tracking | Candidate: Web + App; Employee: App + Web; Recruiter / HR: Web; HR admin: Admin | Not Started | P2 | PC-080 | spec
Vertical | HR & recruiting (hr-core) | candidate-pipeline | Stages, interviews, scorecards, offers | Candidate: Web + App; Employee: App + Web; Recruiter / HR: Web; HR admin: Admin | Not Started | P2 | PC-080 | new
Vertical | HR & recruiting (hr-core) | employee-onboarding | Onboarding checklists, documents | Candidate: Web + App; Employee: App + Web; Recruiter / HR: Web; HR admin: Admin | Not Started | P2 | PC-080 | spec
Vertical | HR & recruiting (hr-core) | payroll | Payroll runs, payslips, deductions | Candidate: Web + App; Employee: App + Web; Recruiter / HR: Web; HR admin: Admin | Not Started | P2 | PC-080 | spec
Vertical | HR & recruiting (hr-core) | attendance-leave | Attendance, shifts, leave requests | Candidate: Web + App; Employee: App + Web; Recruiter / HR: Web; HR admin: Admin | Not Started | P2 | PC-080 | spec
Vertical | HR & recruiting (hr-core) | performance-reviews | Goals, reviews, feedback | Candidate: Web + App; Employee: App + Web; Recruiter / HR: Web; HR admin: Admin | Not Started | P2 | PC-080 | spec (+ registry dependencies 'people', 'skills')
Vertical | Professional services & agencies (professional-services-core) | projects | Projects, phases, milestones, budgets | Client: Web + App; Consultant: Web + App; Partner / manager: Web; Firm admin: Admin | Not Started | P3 | PC-081 | registry
Vertical | Professional services & agencies (professional-services-core) | time-tracking | Time entries, timers, approvals | Client: Web + App; Consultant: Web + App; Partner / manager: Web; Firm admin: Admin | Not Started | P3 | PC-081 | registry
Vertical | Professional services & agencies (professional-services-core) | invoicing-ps | Progress and milestone invoicing | Client: Web + App; Consultant: Web + App; Partner / manager: Web; Firm admin: Admin | Not Started | P3 | PC-081 | registry
Vertical | Professional services & agencies (professional-services-core) | retainers | Retainer balances, drawdowns | Client: Web + App; Consultant: Web + App; Partner / manager: Web; Firm admin: Admin | Not Started | P3 | PC-081 | registry (+ dependency 'retainer')
Vertical | Professional services & agencies (professional-services-core) | resource-planning | Allocations, capacity, skills | Client: Web + App; Consultant: Web + App; Partner / manager: Web; Firm admin: Admin | Not Started | P3 | PC-081 | registry
Vertical | Professional services & agencies (professional-services-core) | client-portal | Client portal, approvals, reports | Client: Web + App; Consultant: Web + App; Partner / manager: Web; Firm admin: Admin | Not Started | P3 | PC-081 | registry (+ dependencies 'customer-portal', 'clients')
Vertical | Professional services & agencies (professional-services-core) | proposals | Proposals, SOWs, e-sign | Client: Web + App; Consultant: Web + App; Partner / manager: Web; Firm admin: Admin | Not Started | P3 | PC-081 | registry (+ dependency 'crm-integration')
Vertical | Professional services & agencies (professional-services-core) | compliance-ps | Engagement letters, conflict checks | Client: Web + App; Consultant: Web + App; Partner / manager: Web; Firm admin: Admin | Not Started | P3 | PC-081 | registry
Vertical | Content, media & publishing (content-core) | articles-cms | Articles, authors, categories, SEO | Reader: App + Web; Writer / editor: Web; Publisher: Admin | Not Started | P3 | PC-081 | new
Vertical | Content, media & publishing (content-core) | editorial-workflow | Draft -> review -> scheduled -> published | Reader: App + Web; Writer / editor: Web; Publisher: Admin | Not Started | P3 | PC-081 | new
Vertical | Content, media & publishing (content-core) | paywall-membership | Paywalls, memberships, metered access | Reader: App + Web; Writer / editor: Web; Publisher: Admin | Not Started | P3 | PC-081 | new
Vertical | Content, media & publishing (content-core) | newsletters | Newsletters, subscribers, campaigns | Reader: App + Web; Writer / editor: Web; Publisher: Admin | Not Started | P3 | PC-081 | new
Vertical | Content, media & publishing (content-core) | podcasts-video | Episodes, feeds, players | Reader: App + Web; Writer / editor: Web; Publisher: Admin | Not Started | P3 | PC-081 | new
Vertical | Content, media & publishing (content-core) | community-comments | Comments, reactions, moderation | Reader: App + Web; Writer / editor: Web; Publisher: Admin | Not Started | P3 | PC-081 | new
Vertical | Travel & hospitality (travel-core) | hotel-pms | Rooms, reservations, housekeeping, folios | Traveller: App + Web; Host / hotel staff: Web + App; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Travel & hospitality (travel-core) | channel-manager | Rates and availability across channels | Traveller: App + Web; Host / hotel staff: Web + App; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Travel & hospitality (travel-core) | travel-booking | Flights/stays/packages search and booking | Traveller: App + Web; Host / hotel staff: Web + App; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Travel & hospitality (travel-core) | itineraries | Trips, itineraries, documents | Traveller: App + Web; Host / hotel staff: Web + App; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Travel & hospitality (travel-core) | tours-activities | Experiences, guides, capacity | Traveller: App + Web; Host / hotel staff: Web + App; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Events & ticketing (events-core) | events | Events, agendas, speakers, venues | Attendee: App + Web; Organiser: Web; Door staff: App; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Events & ticketing (events-core) | ticketing | Ticket types, sales, QR tickets | Attendee: App + Web; Organiser: Web; Door staff: App; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Events & ticketing (events-core) | seating-maps | Seat maps and reservations | Attendee: App + Web; Organiser: Web; Door staff: App; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Events & ticketing (events-core) | check-in | Scan-in, badges, capacity | Attendee: App + Web; Organiser: Web; Door staff: App; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Events & ticketing (events-core) | sponsors-exhibitors | Sponsors, booths, leads | Attendee: App + Web; Organiser: Web; Door staff: App; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Fitness & sports (fitness-core) | gym-memberships | Memberships, access, freezes | Member: App + Web; Trainer: App; Gym manager: Web; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Fitness & sports (fitness-core) | class-booking | Classes, instructors, capacity, waitlists | Member: App + Web; Trainer: App; Gym manager: Web; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Fitness & sports (fitness-core) | workout-plans | Programs, workouts, progress | Member: App + Web; Trainer: App; Gym manager: Web; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Fitness & sports (fitness-core) | personal-training | Trainers, sessions, packages | Member: App + Web; Trainer: App; Gym manager: Web; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Fitness & sports (fitness-core) | clubs-leagues | Teams, fixtures, standings | Member: App + Web; Trainer: App; Gym manager: Web; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Social & community (social-core) | profiles-social | Profiles, follows, blocks | Member: App + Web; Creator: App + Web; Moderator: Admin | Not Started | P3 | PC-081 | new
Vertical | Social & community (social-core) | feeds-posts | Posts, media, feeds, ranking | Member: App + Web; Creator: App + Web; Moderator: Admin | Not Started | P3 | PC-081 | new
Vertical | Social & community (social-core) | groups-communities | Groups, roles, rules | Member: App + Web; Creator: App + Web; Moderator: Admin | Not Started | P3 | PC-081 | new
Vertical | Social & community (social-core) | creator-monetization | Tips, subscriptions, paid content | Member: App + Web; Creator: App + Web; Moderator: Admin | Not Started | P3 | PC-081 | new
Vertical | Social & community (social-core) | dating-matching | Matching, swipes, safety tools | Member: App + Web; Creator: App + Web; Moderator: Admin | Not Started | P3 | PC-081 | new
Vertical | Social & community (social-core) | forums-qa | Forums, Q&A, accepted answers | Member: App + Web; Creator: App + Web; Moderator: Admin | Not Started | P3 | PC-081 | new
Vertical | Insurance (insurance-core) | policies | Policies, coverages, endorsements | Policyholder: App + Web; Agent / broker: Web + App; Adjuster / underwriter: Web; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Insurance (insurance-core) | quotes-underwriting | Quotes, rating, underwriting rules | Policyholder: App + Web; Agent / broker: Web + App; Adjuster / underwriter: Web; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Insurance (insurance-core) | claims | FNOL, adjusting, settlement | Policyholder: App + Web; Agent / broker: Web + App; Adjuster / underwriter: Web; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Insurance (insurance-core) | agents-brokers | Agents, commissions, books | Policyholder: App + Web; Agent / broker: Web + App; Adjuster / underwriter: Web; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Insurance (insurance-core) | premium-billing | Premium schedules, collections | Policyholder: App + Web; Agent / broker: Web + App; Adjuster / underwriter: Web; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Automotive (automotive-core) | dealer-inventory | Vehicles for sale, specs, photos | Buyer / owner: App + Web; Sales / service advisor: Web + App; Dealer admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Automotive (automotive-core) | test-drives | Test-drive booking | Buyer / owner: App + Web; Sales / service advisor: Web + App; Dealer admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Automotive (automotive-core) | service-center | Service bookings, job cards, parts | Buyer / owner: App + Web; Sales / service advisor: Web + App; Dealer admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Automotive (automotive-core) | parts-catalog | Parts catalogue, fitment | Buyer / owner: App + Web; Sales / service advisor: Web + App; Dealer admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Automotive (automotive-core) | vehicle-history | Ownership and service history | Buyer / owner: App + Web; Sales / service advisor: Web + App; Dealer admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Retail & restaurant POS (pos-core) | pos-terminal | Point of sale, receipts, cash drawer | Cashier: App (tablet); Store manager: Web; Owner: Admin | Not Started | P3 | PC-081 | new
Vertical | Retail & restaurant POS (pos-core) | store-inventory | Store stock, transfers, counts | Cashier: App (tablet); Store manager: Web; Owner: Admin | Not Started | P3 | PC-081 | new
Vertical | Retail & restaurant POS (pos-core) | shift-cash-management | Shifts, cash-ups, variances | Cashier: App (tablet); Store manager: Web; Owner: Admin | Not Started | P3 | PC-081 | new
Vertical | Retail & restaurant POS (pos-core) | customer-loyalty-pos | In-store loyalty and offers | Cashier: App (tablet); Store manager: Web; Owner: Admin | Not Started | P3 | PC-081 | new
Vertical | Manufacturing & field operations (manufacturing-core) | production-orders | Work orders, routings | Operator on the floor: App; Planner / QC: Web; Field technician: App; Plant admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Manufacturing & field operations (manufacturing-core) | bill-of-materials | BOMs, versions, costing | Operator on the floor: App; Planner / QC: Web; Field technician: App; Plant admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Manufacturing & field operations (manufacturing-core) | quality-control | Inspections, non-conformances | Operator on the floor: App; Planner / QC: Web; Field technician: App; Plant admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Manufacturing & field operations (manufacturing-core) | maintenance-cmms | Assets, preventive maintenance | Operator on the floor: App; Planner / QC: Web; Field technician: App; Plant admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Manufacturing & field operations (manufacturing-core) | field-service | Technician dispatch, job sheets, signatures | Operator on the floor: App; Planner / QC: Web; Field technician: App; Plant admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Legal (legal-core) | matters-cases | Matters, parties, deadlines | Client: Web + App; Lawyer / paralegal: Web; Firm admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Legal (legal-core) | legal-documents | Templates, clause library, versions | Client: Web + App; Lawyer / paralegal: Web; Firm admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Legal (legal-core) | client-intake | Intake forms, conflict checks | Client: Web + App; Lawyer / paralegal: Web; Firm admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Legal (legal-core) | court-calendar | Hearings, filings, reminders | Client: Web + App; Lawyer / paralegal: Web; Firm admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Nonprofit & civic (civic-core) | donations-fundraising | Donations, campaigns, receipts | Citizen / donor: App + Web; Case worker / volunteer: Web + App; Agency admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Nonprofit & civic (civic-core) | volunteers | Volunteer shifts and hours | Citizen / donor: App + Web; Case worker / volunteer: Web + App; Agency admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Nonprofit & civic (civic-core) | grants | Grant applications and reporting | Citizen / donor: App + Web; Case worker / volunteer: Web + App; Agency admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Nonprofit & civic (civic-core) | citizen-services | Service requests, status tracking | Citizen / donor: App + Web; Case worker / volunteer: Web + App; Agency admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Nonprofit & civic (civic-core) | permits-licensing | Applications, inspections, licences | Citizen / donor: App + Web; Case worker / volunteer: Web + App; Agency admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Utilities & energy (utilities-core) | meter-reading | Meters, readings, anomalies | Customer: App + Web; Field crew: App; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Utilities & energy (utilities-core) | utility-billing | Tariffs, bills, payments | Customer: App + Web; Field crew: App; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Utilities & energy (utilities-core) | outage-management | Outages, crews, notifications | Customer: App + Web; Field crew: App; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Utilities & energy (utilities-core) | ev-charging | Chargers, sessions, billing | Customer: App + Web; Field crew: App; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Pets & veterinary (pets-core) | pet-profiles | Pets, vaccinations, records | Pet owner: App + Web; Vet / groomer: Web + App; Clinic admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Pets & veterinary (pets-core) | vet-clinic | Vet appointments, treatments | Pet owner: App + Web; Vet / groomer: Web + App; Clinic admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Pets & veterinary (pets-core) | pet-services | Grooming, boarding, walking | Pet owner: App + Web; Vet / groomer: Web + App; Clinic admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Schools & childcare (K-12) (schools-core) | school-admin | Students, classes, timetables, fees | Parent: App + Web; Teacher: Web + App; Student: App; School admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Schools & childcare (K-12) (schools-core) | attendance-school | Attendance and absence alerts | Parent: App + Web; Teacher: Web + App; Student: App; School admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Schools & childcare (K-12) (schools-core) | parent-portal | Parent messages, report cards, payments | Parent: App + Web; Teacher: Web + App; Student: App; School admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Schools & childcare (K-12) (schools-core) | school-transport | Bus routes and live tracking | Parent: App + Web; Teacher: Web + App; Student: App; School admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Construction & property services (construction-core) | construction-projects | Projects, phases, site teams | Site supervisor: App; Project manager: Web; Subcontractor: App + Web; Company admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Construction & property services (construction-core) | bids-estimates | Estimates, bids, change orders | Site supervisor: App; Project manager: Web; Subcontractor: App + Web; Company admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Construction & property services (construction-core) | site-diary | Daily logs, photos, safety incidents | Site supervisor: App; Project manager: Web; Subcontractor: App + Web; Company admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Construction & property services (construction-core) | subcontractors | Subcontractors, compliance, payments | Site supervisor: App; Project manager: Web; Subcontractor: App + Web; Company admin: Admin | Not Started | P3 | PC-081 | new
Vertical | Agriculture (agri-core) | farms-fields | Farms, fields, crops, seasons | Farmer: App; Buyer: Web + App; Field advisor: App; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Agriculture (agri-core) | agri-marketplace | Produce listings, buyers, logistics | Farmer: App; Buyer: Web + App; Field advisor: App; Operator: Admin | Not Started | P3 | PC-081 | new
Vertical | Agriculture (agri-core) | farm-advisory | Weather, advisories, input orders | Farmer: App; Buyer: Web + App; Field advisor: App; Operator: Admin | Not Started | P3 | PC-081 | new

## Targets
Measure | Target
Vibe: prompt -> live preview | under 90 seconds
Vibe: prompt -> deployed URL | under 3 minutes
Engineering: prompt -> multi-app monorepo | under 3 minutes
Graduation Vibe -> Engineering | under 30 seconds, nothing lost
Generated code | TypeScript strict 0 errors; every surface builds
Generated tests | over 80% coverage
Project import success | over 90%

## Decisions
ID | Question | Why it matters | Blocks | Recommendation | Founder answer
D-1 | Pricing: free-tier credits and paid plans | Plans, entitlements and top-up cannot be built without numbers. | PC-011, PC-015 | Keep 100 signup credits and 1 credit = $0.001 for the beta; set paid plans after beta usage data. | Accepted 2026-09-26 for the beta.
D-2 | Hosting cloud and region for the live service | New infrastructure needs sign-off. | PC-009, PC-008, Phase 4 | One region, one managed Postgres, container hosting; decide after cost quotes. | Keys last (founder, 2026-09-26): all code and integrations are finished first; the account and keys are plugged in at PC-070.
D-3 | Payment processor for platform billing | Paid cloud service needs sign-off. | PC-011 | Stripe (global) with Razorpay for India, as generated apps already support both. | Keys last (founder, 2026-09-26): all code and integrations are finished first; the account and keys are plugged in at PC-070.
D-4 | Email verification and password reset required for beta? | Changes PC-012 scope. | PC-012 | Yes: strangers are signing up. | Accepted 2026-09-26.
D-5 | What does an app request produce? | R-562 answers an app request with React Native today. | PC-003, R-573, R-574 | React Native plus PWA + QR. | 2026-09-26: when the user names no stack, a React Native (Expo) app ready to publish on Google Play and the App Store AND an installable PWA with a QR code. When the user asks for native, Kotlin/Compose and Swift/SwiftUI are generated (R-575/R-576).
D-10 | Native mobile preview approach | The founder asked for emulators and simulators without Android Studio or Xcode GUIs, open source first. | PC-063, PC-064, PC-065, PC-066 | See NATIVE_MOBILE_PREVIEW_PLAN.md. | 2026-09-26: open source first; Android Studio, Xcode GUI and paid services only later.
D-6 | In-browser preview engine (WebContainers needs a commercial licence; alternatives exist) | PC-007 cannot start without it. | PC-007 | Evaluate licence cost vs a server-side sandbox preview. | Open source first (founder, 2026-09-26). Keys last (founder, 2026-09-26): all code and integrations are finished first; the account and keys are plugged in at PC-070.
D-7 | Apple Developer and Google Play accounts; go-ahead for Kotlin/Swift native | Store publishing needs real accounts; standing rule: stop and ask before native work. | R-574, PC-042 and all of Phase 5 | Accounts when R-574 is reached; native when Phases 1-4 are done. | Keys last (founder, 2026-09-26): all code and integrations are finished first; the account and keys are plugged in at PC-070.
D-8 | Database options beyond PostgreSQL | Changes every backend adapter. | PC-048 | PostgreSQL default; add MongoDB as an option. | 2026-09-26: PostgreSQL by default; MongoDB as an option (more later if they are the best choice).
D-9 | Which LLM the platform uses for builds | Quality and cost of every build. | PC-047 | Use the founder's NVIDIA key. | 2026-09-26: NVIDIA nemotron-3-ultra via the NVIDIA API; key, model and base URL are in .env.

## Legend
Term | Meaning
Completed | Built, tested and in CHANGELOG.md.
Completed - needs live proof | Built and tested offline, never run against a real account (Vercel, Stripe, app stores ...). Done in code, not proven in the world.
In Progress | Being worked on now.
Pending | Partly built, or waiting on a founder decision. Something exists to build on.
Not Started | Nothing built yet.
Superseded | Replaced by a different task that already did the job another way.
Deferred | Useful, but only after launch. Do not start until the queue is empty.
Dropped | Against the current stack policy or no longer wanted. Will not be built.
P0 | Launch blocker. Vibe Mode cannot go live with real users without it.
P1 | Core promise. Needed for 'maximum features per prompt' and Engineering Mode.
P2 | Hardening and depth. Production trust, native apps, quality.
P3 | Nice to have. Do when everything above is done.
0 Foundation | Reconcile, decide, set the stack policy.
1 Vibe Mode live | Prompt -> running app with real API + DB -> live URL, for real users.
2 Maximum features | Every prompt yields the most complete product the IR can express.
3 Engineering Mode | Plan, stack choice, repo import, diffs, verification report, PRs, memory.
4 Production ops | Security audits, backup/recovery, compliance, observability.
5 Native mobile (last) | Kotlin/Compose + Swift/SwiftUI, through to Play Store and App Store.
6 Go-live (credentials last) | The founder supplies accounts and keys; every live proof is run; the platform opens to real users.
7 Win the category | Measure against every competitor and close each gap until we lead. Done last, after native and go-live, by founder decision (2026-09-26).
Post-launch | Deferred until the platform is live and the queue above is empty.
Delivered | Already built.